## Time Per Location
Including Road watch
Labour Hrs/Day | 8 |  | 8 | 16 | 24 | 32 | 40 | 48
|  | Hours | Days
Installation Location | Time Estimate | Time w/33% Buffer | 1 Installer | 2 Installers | 3 Installers | 4 Installers | 5 Installers | 6 Installers | Weeks | Phase | Teams
Carson City | 865 | 1150.45 | 143.8 | 71.9 | 47.9 | 36 | 28.8 | 24 | 5 | Phase 2 | T-1
Elko | 623.75 | 829.5875 | 103.7 | 51.8 | 34.6 | 25.9 | 20.7 | 17.3 | 4 | Phase 1 | T-2
Ely | 467.5 | 621.775 | 77.7 | 38.9 | 25.9 | 19.4 | 15.5 | 13 | 3 | Phase 2 | T-2
Fallon | 375.75 | 499.7475 | 62.5 | 31.2 | 20.8 | 15.6 | 12.5 | 10.4 | 3 | Phase 3 | T-1
Las Vegas | 1529.75 | 2034.5675 | 254.3 | 127.2 | 84.8 | 63.6 | 50.9 | 42.4 | 9 | Phase 4 | T-2
Reno | 1372.25 | 1825.0925 | 228.1 | 114.1 | 76 | 57 | 45.6 | 38 | 8 | Phase 1 | T-1
Tonopah | 459.75 | 611.4675 | 76.4 | 38.2 | 25.5 | 19.1 | 15.3 | 12.7 | 3 | Phase 4 | T-1
Wells | 243 | 323.19 | 40.4 | 20.2 | 13.5 | 10.1 | 8.1 | 6.7 | 2 | Phase 3 | T-2
Winnemucca | 424.25 | 564.2525 | 70.5 | 35.3 | 23.5 | 17.6 | 14.1 | 11.8 | 3 | Phase 4 | T-2
Grand Total | 6361 | 8460.13 | 1057.4 | 528.8 | 352.5 | 264.3 | 211.5 | 176.3 | 36

## Detail1-Elko
Federal MCC | NDOT Class code | Installation Location | Year | Make | Model | Description | Existing OBDII/J1939 | Existing Roadwatch SS | Existing Parker/CIRUS/FORCE AMERICA/EPOKE | Existing Associations/Hardware | Telematic Device / Telematics device for Winter Operations needed | Sensors needed | Wi-Fi HotSpot needed | Cameras needed | Check | OBDII | J1939 (9 pin) | Direct Wiring (3 wire) | Winter Operations With J1939 (9 pin) | Wi-Fi HotSpot | Forward Cameras | Rear Cameras | Attenuator Up Down | Wing Plow Up/Down Down | Front Plow Up/Down | Belly Plow Up Down | Broom Up Down | Hopper full indication | Pump on/off | Snow Blower Activation | Light Bar Activation | Barometric Pressure | Humidity | Total Sensors | IOX-SATIRDV2 | IOX - AUXM | IOX - WRKS | IOX - BT | Roadwatch (Integration) | Sensor exc humidity | Phase | Estimated Time
8 | 13 | Elko | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | PLOW REVERSIBLE ALASKAN,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW,2019 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | PLOW,SANDER,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2018 HENKE NOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8
8 | 13S | Elko | 2017 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER 8 CUBIC YARDS,WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 900 GALLON DE-ICING SPRAYER,PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25
8 | 13 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TWO-WAY SWING PLOW,FLINK SANDER 8 CU YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | VARITECH 1750 GALLON TANK,SANDER 8 YARD,HEAVY DUTY WING PLOW,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25
5 | 24 | Elko | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 3 | POC | 4.5
5 | 24 | Elko | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 3 | POC | 4.5
8 | 13 | Elko | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,FLINK 8 YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 1 | 1 | 3 | POC | 6.75
8 | 13 | Elko | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | PLOW WING,SANDER 8 YARD,2000 PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 1 | 1 | 3 | POC | 6.75
8 | 13 | Elko | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 1 | 1 | 3 | POC | 6.75
5 | 24 | Elko | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 3 | POC | 4.5
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,SPRATRONICS DE ICER,PLOW REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 | POC | 6.25
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 | POC | 6.25
5 | 24 | Elko | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 | POC | 4
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 | POC | 6.25
5 | 24 | Elko | 2020 | ELGIN | EAGLE | 2020 SELF PROPELLED TENNANT BR | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 | POC | 4
8 | 13S | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD,SLIDE IN PRAYER,PLOW,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REBUILD 2000 SANDER,REBUILD 2000 PLOWS,REBUILD 1999 PLOWS | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE 11FT REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 CU YD FLINK LMC1H SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5
6 | 20 | Elko | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 3.25
8 | 12 | Elko | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE 11 FT REVERSABLE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
8 | 12 | Elko | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE,2001 SANDER 5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 6.5
8 | 13 | Elko | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
6 | 11B | Elko | 2003 | INTL | 7600 | FLATRACK TRUCK W/CRANE | J1939 |  |  | 2018 ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 6
8 | 12 | Elko | 2009 | PETERBILT | 367 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | BONNELL SANDER 5 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.5
6 | 20 | Elko | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 3.25
8 | 12 | Elko | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.5
8 | 12 | Elko | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 PLOW,1995 SANDER,2021 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 6.5
8 | 12 | Elko | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
6 | 11B | Elko | 2019 | WESTERN ST | 4900SF | 2019 WESTERN STAR FLAT RACK | J1939 |  |  | 2021 SCORPION ATTENUATOR,2021 LITEREADER ARROWBOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 6
OFF ROAD / NA | 42 | Elko | 1997 | KODIAK | CR400 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 4.25
6 | 11B | Elko | 1998 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | ARROW SIGNBOARD, T/M,SCORPION ATTENUATOR TRK MNT | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 6
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 SANDER HOPPER-TYPE 8 CU YD,PLOW REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
8 | 12 | Elko | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,5 YD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
8 | 12 | Elko | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 FLINK SANDER,11 REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5
8 | 12 | Elko | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW,SANDER 5 CU YD,2020 SCORPION VEH MNT ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 6.5
8 | 25 | Elko | 1976 | PETERBILT | MD359 | TRACTOR TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.75
8 | 25 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.75
8 | 25 | Elko | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.75
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
2 | 1 | Elko | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
2 | 01A | Elko | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 4 | Elko | 2002 | GMC | SAVANA | PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 3 | Elko | 2006 | FORD | F-250 | 3/4 TON PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11E | Elko | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11E | Elko | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11A | Elko | 2017 | FORD | F-550 | AERIAL TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11A | Elko | 2020 | DODGE | 5500 | 2020 DODGE RAM 5500 FLATRACK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
6 | 77 | Elko | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
2 | 01A | Elko | 2004 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11F | Elko | 1989 | INTL | 2574 | SERVICE TRUCK W/CRANE | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
6 | 20 | Elko | 1998 | INTL | 4900 | 1998 CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11J | Elko | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
OFF ROAD / NA | 55B | Elko | 2009 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11F | Elko | 2018 | DODGE | RAM 5500 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
2 | 01A | Elko | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 3.5L V6 4WD | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
5 | 11H | Elko | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
2 | 01A | Elko | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25
5 | 11E | Elko | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
6 | 28 | Elko | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11H | Elko | 2013 | FORD | F-450 | FLATRACK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11J | Elko | 2013 | FORD | F-450 | UTILITY TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11F | Elko | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11H | Elko | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11H | Elko | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11J | Elko | 2018 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11A | Elko | 2005 | FORD | F-550 | FLANNIGAN SHOP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2019 | FORD | F-150 | 2019 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
9 | 14 | Elko | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11F | Elko | 2008 | FORD | F-650 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2018 | CHEVROLET | SILVERADO | 2018 CHEVEROLET SIVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
6 | 20 | Elko | 2005 | INTL | 7600 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 3 | Elko | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11H | Elko | 2007 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11J | Elko | 2006 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11H | Elko | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  | HENKE 11 FT REV SNOW PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11E | Elko | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11E | Elko | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11H | Elko | 2019 | FORD | F-450 | 2019 FLATRACK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11H | Elko | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
6 | 28 | Elko | 1990 | MACK | MR690 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
9 | 14 | Elko | 2019 | WESTERN | 4900SF | TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11F | Elko | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 UTILITY TRUCK WITH CRANE ASSEMBLY | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
2 | 1 | Elko | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
2 | 1 | Elko | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11A | Elko | 2018 | DODGE | 5500 | 2018 AERIAL LIFT TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
5 | 11F | Elko | 2001 | INTL | 4700 | FLAT RACK W/CRANE | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 3 | Elko | 1998 | GMC | SIERRA | 3/4 TON PICKUP TRUCK W/SVC BODY AWD | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75
5 | 11A | Elko | 2002 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | POC | 1
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | POC | 1

## Install Team Routing
TOTAL Install Hours
Install Hours
Install Team 1 | Reno (Pilot) | Reno | Carson | Fallon | Tonopah
Install Team 2 |  | Winnemucca | Elko | Ely | Wells | Las Vegas
Install Hours

## OLD - UnitMaster - Phase1 (hidden)
Federal MCC | NDOT Class code | Installation Location | Year | Make | Model | Description | Existing OBDII/J1939 | Existing Roadwatch SS | Existing Parker/CIRUS/FORCE AMERICA/EPOKE | Existing Associations/Hardware | Telematic Device / Telematics device for Winter Operations needed | Sensors needed | Wi-Fi HotSpot needed | Cameras needed | Check
2 | 01A | Carson City | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Las Vegas | 2016 | FORD | EXPLORER | SUV 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Las Vegas | 2019 | CHEVROLET | MALIBU HYB | 2019 SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2007 | GMC | ENVOY | GMC ENVOY SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Las Vegas | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Las Vegas | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 6 | Tonopah | 2016 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2001 | TOYOTA | PRIUS | HYBRID SEDAN 4 DOOR | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor | EPOKE | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Las Vegas | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Tonopah | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE-WAY PLOW,2017 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Las Vegas | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,ONE WAY PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
2 | 1 | Las Vegas | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Ely | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Las Vegas | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Reno | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Winnemucca | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
6 | 15 | Reno | 2017 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | EPOKE | SANDER EPOKE,HEAVY DUTY PATROL WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
2 | 01A | Ely | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE TRUCK | J1939 | Roadwatch Sensor | EPOKE | PLOW WING,JENSEN REVERSIBLE PLOW,SANDER EPOKE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2001 | GMC | TC15903 | 1/2 TON PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | EPOKE | SANDER 8 YARD,PLOW ONE WAY,EPOKE SANDER,2021 HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
6 | 15 | Reno | 2007 | PETERBILT | 357 | AWD TRUCK W/EPOKE SANDER | J1939 | Roadwatch Sensor | EPOKE | PLOW SLOTTED TRIP,PLOW ONE WAY,JENSEN 12 FT ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Reno | 1998 | GMC | JIMMY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 15 | Reno | 2016 | PETERBILT | 367 | AWD TANDEM AXLE PLOW TRUCK | J1939 | Roadwatch Sensor | EPOKE | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Winnemucca | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Las Vegas | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 15 | Reno | 2016 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | J1939 | Roadwatch Sensor | EPOKE |  | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Elko | 2018 | MACK | GR64FR | 2018 MACK GRANITE TANDEM AXLE HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA |  | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2019 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | FLAT RACK SWAPLOADER | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13S | Reno | 2020 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | SANDER, REVERSIBLE PLOW, DUMP BODY | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
2 | 01A | Reno | 2005 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | WATER TANK SWAPLOADER,PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,FLAT RACK, SWAPLOADER,2014 LITE READER 1230F-4,TRUCK MOUNTED ATTENUATOR | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 10 | Reno | 2001 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Ely | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2007 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Ely | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Fallon | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Reno | 2008 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Las Vegas | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11A | Ely | 2001 | FREIGHTLNR | 25K GVW | AERIAL LIFT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2018 HENKE NOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | REVERSIBLE PLOW,8 CU YD HENDERSON,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Las Vegas | 1998 | FORD | ESCORT | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Carson City | 2001 | FORD | F-350 | 4X4 SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
OFF ROAD / NA | 42 | Carson City | 2020 | KODIAK | 1200 | 2020 KODIAK ROTARY BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
5 | 11J | Carson City | 2001 | FORD | F-350 | 4X4 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,PLOW WING,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 YD SANDER,PLOW,2006 HENKE PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 1994 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HEAVY DUTY PATROL WING PLOW,11' REVERSIBLE LEWTON MDL RO1144NV,FLINK MDL #LMC5H-15NV-39 | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Tonopah | 1994 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 1994 PLOW,HENKE WING PLOW,8 YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/ HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | 15 FOOT SWAPLOADER DUMP BODY,2006 HENKE PLOW REVERSIBLE,2006 FLINK SANDER 8 YARD,SWAPLOADER WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Las Vegas | 2018 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2018 REVERSIBLE PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD,SLIDE IN PRAYER,PLOW,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 900 GALLON DE-ICING SPRAYER,PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Fallon | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE TRK MTED WING PLOW,SANDER 8 YARD,PLOW REVERSIBLE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 4 | Carson City | 2018 | CHEVROLET | EXPRESS | 2018 CHEV EXP 1T 15 PASS VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Carson City | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
6 | 28 | Tonopah | 2001 | INTL | 2574 | 2001 REBUILD INTL F2574 DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW UNDERBODY,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11H | Carson City | 2007 | FREIGHTLNR | FLD120 | FLATRACK TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Las Vegas | 2007 | FORD | F-550 | SERVICE TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
OFF ROAD / NA | 42 | Reno | 2020 | KODIAK | 1200 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
8 | 13 | Fallon | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11A | Tonopah | 2006 | GMC | SIERRA | SIGNSHOP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK WORKMAN SWAPLOADER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11A | Reno | 2008 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 11B | Las Vegas | 2007 | FREIGHTLNR | FDL120 | CRANE TRUCK W/FLATBED | J1939 |  |  | ATTENUATOR W/VERTICAL LIFT ARROW BOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 13S | Tonopah | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | SWAPLOADER WATER TANK,ONE WAY PLOW,SANDER 8 YARD,DUMP BODY SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2014 VARITECH 403 V | Telematics device for Winter Operations |  | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SPRATRONICS DE ICER,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 1989 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,REVERSIBLE 11' SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 1996 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,1990 HENDERSON SANDER 10 YD,ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER,HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Elko | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 4 | Carson City | 2018 | CHEVROLET | EXPRESS | 2018 3/4 TON VAN 12 PASSENGER | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Fallon | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2000 PLOW PLOWS,REBUILD 2006 SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE 12FT RGHT HAND DISCHARGE,REVERSIBLE,REBUILD 2008 HENDERSON SANDER/HOPPER TYP | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REBUILD 2000 SANDER,REBUILD 2000 PLOWS,REBUILD 1999 PLOWS | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TWO-WAY SWING PLOW,FLINK SANDER 8 CU YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Las Vegas | 1998 | FORD | ESCORT | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Winnemucca | 2001 | WITTKE | WIZARD FC-70 | SELF PROPELLED ROAD BROOM | J1939 |  |  | BUCKET, 71 DITCH CLEANING | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 2018 1/2 TON CHEVY SILVERADO 1500 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,REVERSIBLE PLOW,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Tonopah | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | FLINK SANDER,HEAVY DUTY WING PLOW,PLOW REVERSIBLE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 CHEVY 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Ely | 2007 | FORD | F-350 | SERVICE TRUCK 4X4 | OBDII |  |  | 2018 REAR BUMPER CRANE | Telematics Device |  |  |  | X
2 | 01A | Tonopah | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,8 YD STAINLESS STEEL SANDER,PLOW ONE WAY,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Wells | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Reno | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE 11FT REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Tonopah | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW,SANDER W/PREWET SYSTEM | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REVERSIBLE PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REVERSIBLE PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Tonopah | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD,2012 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | VARITECH 1750 GALLON TANK,SANDER 8 YARD,HEAVY DUTY WING PLOW,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | VARITECH BRINE DISTRIBUTION TANK,PLOW REVERSIBLE,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11J | Carson City | 2016 | FORD | F-550 | UTILITY TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Las Vegas | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | DUMP BODY SWAP-LOADER,WATER TANK WRKMAN SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Ely | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Tonopah | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
6 | 20 | Reno | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
9 | 14 | Reno | 1993 | KENW | T800 | KENWORTH T800 REBUILD | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 76 | Carson City | 2001 | FORD | E-350 | 1 TON VAN W/FALLING WEIGHT DEFLECT | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Fallon | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Las Vegas | 2002 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Winnemucca | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 01A | Elko | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Las Vegas | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER 8 YARD,REVERSABLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 20 | Las Vegas | 2016 | PETERBILT | 567 | VACTOR 2100 CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 13 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | JENSEN REVERSIBLE,8 CU YD | Telematics device for Winter Operations |  | Yes | Yes - Forward only | x
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Elko | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
6 | 15 | Reno | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2011 HENKE 10 ONE-WAY SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
6 | 15 | Reno | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW TRUCK PATROL | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 4 | Reno | 1999 | GMC | TG3140 | 1 TON CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Elko | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Wells | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Reno | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TENCO 11FT REVERSIBLE PLOW,8 YARD FLINK SANDER,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,1991 PLOW,1991 SANDER,TENCO 11 FT. REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 4 | Reno | 1999 | CHEVROLET | CG21406 | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 77 | Tonopah | 1988 | MACK | MR688 | MACK STRIPER REBUILD | J1939 |  |  |  | Telematics Device |  | Yes |  | X
5 | 6 | Ely | 2008 | FORD | F-350 | ONE TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Elko | 2002 | GMC | SAVANA | PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Las Vegas | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW,2001 FLINK SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
6 | 20 | Tonopah | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
5 | 24 | Fallon | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Reno | 2017 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13H | Las Vegas | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR TANDEM AXLE SIDE DUMP | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Reno | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2002 | GMC | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Tonopah | 2016 | PETERBILT | 367 | TANDEM AXLE SWAP LOADER | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER,DUMP BODY | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
6 | 20 | Elko | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
OFF ROAD / NA | 55B | Winnemucca | 2006 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Carson City | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Wells | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Elko | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Wells | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TENKO 1 WAY PLOW,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,VARITECH 1750 GAL BRINE TANK,PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11H | Reno | 2008 | FORD | F-650 | FLATRACK TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 CU YD FLINK LMC1H SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2000 SANDER,SPRATRONICS DE ICER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TENCO PLOW,FLINK SANDER 8 CU YRD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE SINGEL AUGER CARTRIDGE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | FLINK 8 CU YD SANDER,11' TENCO PLOW,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 11B | Tonopah | 1992 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | 2014 LITEREADER 1230F-4 SIGN BOARD,2007 SCORPION TL-3TRUCK MNTD. ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11H | Reno | 1992 | INTL | 4700 | FLATRACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE TRK MTED WING PLOW,PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Wells | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REVERSIBLE,FLINK 8 CUBIC YARD SANDER,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE HEAVY DUTY PATROL,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Reno | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Reno | 2016 | FORD | F-350 | SHOP SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,TENCO,FLINK,SPRATRONICS | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE AUGER CARTRIDGE SANDER,2020 REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Tonopah | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY HENKE,2000 SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Wells | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 1991 PLOW,2000 SANDER,HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 CU YD FLINK LMC1H SANDER,REVERSIBLE PLOW, TENCO TC-132,DE-ICING SPRAYER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Elko | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | PLOW REVERSIBLE ALASKAN,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER 8 CU YD HOPPER TYPE F,PLOW REVERSIBLE, TENCO TC-132 | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SANDER,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Las Vegas | 2007 | WESTERN ST | 4900FA | DUMP TRUCK W/SIDE DUMP BODY | J1939 | Roadwatch Sensor | Parker Iqan | 2020 REBUILD -ATTENUATOR VEH MNT,2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11E | Las Vegas | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Reno | 1992 | GMC | TC7H0 | FLATRACK TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Elko | 2006 | FORD | F-250 | 3/4 TON PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Ely | 2017 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Wells | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Ely | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Reno | 1992 | INTL | 4700 | FLATRACK TRUCK | J1939 |  |  | 2021 LITEREADER ARROW BOARD | Telematics Device | No |  |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Ely | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 77 | Las Vegas | 2006 | PETERBILT | 320 | LINE STRIPER TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Elko | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Wells | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE SINGLE SANDER,2020 HENKE ONE WAY PLOW,2020 HENKE WING PLAY | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Wells | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Winnemucca | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE SINGLE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Elko | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Wells | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Las Vegas | 2001 | FORD | F-450 | REBUILD FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Winnemucca | 2001 | FORD | F-450 | FLAT RACK TRUCK | OBDII | Roadwatch Sensor |  | DEICING UNIT,325 GALLON DE-ICING UNIT | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Elko | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Las Vegas | 2001 | FORD | F-450 | FLAT RACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Wells | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Fallon | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Elko | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE 11 FT REVERSABLE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Elko | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE,2001 SANDER 5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Las Vegas | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11E | Winnemucca | 2008 | FORD | F-250 | DUMP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Winnemucca | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | J1939 | Roadwatch Sensor |  | PLOW,HEAVY DUTY PATROL WING,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11F | Reno | 2009 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DSL | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Las Vegas | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Winnemucca | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | WING PLOW,8 YD,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11J | Reno | 2007 | FORD | F-450 | 4X4 UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13S | Elko | 2017 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER 8 CUBIC YARDS,WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER 8 YD,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Elko | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 7532,WING PLOW,HENKE 12' RIGHTHAND,2014 VARITECH AI-1850 BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11F | Ely | 1994 | GMC | TC310 | AWD 1 TON TRUCK W/ WELDING BODY | OBDII |  |  | 2019 TRAILBLAZER 302 WELDER | Telematics Device |  |  |  | X
5 | 11E | Carson City | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1988 SANDER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Ely | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ONE WAY PLOW,SANDER,DE-ICING SPRAYER,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Elko | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,FLINK 8 YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13 | Las Vegas | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Reno | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 8 YD SANDER,JENSEN SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
OFF ROAD / NA | 42 | Reno | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
OFF ROAD / NA | 42 | Carson City | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  | PROGRAMMABLE MESSAGE SIGN,2014 LITE READER 1030F-4 | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Tonopah | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE 4422,FLINK 7511,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Elko | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Ely | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW WING,ONE WAY,8 YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2002 | INTL | 2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor |  | SANDER SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 15 | Reno | 2001 | INTL | F5000 | AWD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Reno | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  | TRAILER OFFICE 60' X 24',2014 SNOW DOGG SNOW PLOW KIT EX-80,2014 SALT DOGG MODEL SHIP 2000X | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2007 | FORD | F-450 | 1 TON DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Las Vegas | 2017 | CHEVROLET | EXPRESS | 15 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 77 | Reno | 2002 | EZ LINER | 320 | FREEWAY LINE STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Carson City | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Carson City | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Tonopah | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11E | Las Vegas | 2007 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
9 | 14 | Ely | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
9 | 14 | Fallon | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Tonopah | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
2 | 01A | Ely | 2017 | FORD | EXPLORER | 4X4 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
9 | 14 | Wells | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 1987 | CHEVROLET | CR209 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
9 | 14 | Ely | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Reno | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Las Vegas | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2014 PROFILING SYSTEM | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Carson City | 2016 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Elko | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Tonopah | 2016 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 4 | Carson City | 2003 | GMC | SAVANA | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 4 | Carson City | 2003 | GMC | SAVANA | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Carson City | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 15 | Reno | 2017 | PETERBILT | 367 | TANDEM AXLE PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Carson City | 1998 | CHEVROLET | CC209 | 3/4 TON PICKUP TRUCK W/SVC BODY | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2003 | GMC | SIERRA | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Winnemucca | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Reno | 2016 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Elko | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Ely | 2008 | FORD | F-450 | 1 TON FLATRACH TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Winnemucca | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,1993 SANDER 5 YD 10',ATTENUATOR, V/M | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 5 | Tonopah | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11J | Las Vegas | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Ely | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Reno | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X
8 | 12 | Reno | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK SANDER,CLEDHILL PLOW MDL 20931 | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Winnemucca | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11S | Las Vegas | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | 400 GAL SPRAY TANK/SLIDE-IN | Telematics Device | No | Yes |  | X
5 | 11H | Las Vegas | 1996 | INTL | 4700 | FLAT RACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Elko | 2003 | INTL | 7600 | FLATRACK TRUCK W/CRANE | J1939 |  |  | 2018 ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11H | Las Vegas | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11A | Elko | 2017 | FORD | F-550 | AERIAL TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11S | Las Vegas | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11A | Reno | 2003 | INTL | 7600 | AERIAL LIFT TRUCK BIO-DSL | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11H | Winnemucca | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Fallon | 2002 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Carson City | 2002 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | SALTDOGG SHPE2000X SANDER,SNOWDOGG EX-85 PLOW | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  | JENSEN-MODEL 43058 | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11S | Las Vegas | 2002 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOKLIFT | OBDII | Roadwatch Sensor |  | ARROW BOARD, T/M,DUMPBED SL95 | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2002 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | No | Yes |  | X
8 | 12 | Ely | 2002 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,5 CU YD SANDER W/PRE WET & GUARD,FRONT BROOM ATTACHMENT | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Reno | 2002 | INTL | 5500 | SINGLE AXLE DUMP TRUCK AWD | J1939 | Roadwatch Sensor |  | HENKE PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Wells | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,FLINK SANDER,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
5 | 6 | Reno | 2008 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Winnemucca | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE REVERSIBLE,PLOW WING,FLINK SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2003 | MACK | RD6885 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REV PLOW REBUILD,1850 GALLON SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE PLOW,8 YRD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11H | Tonopah | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
8 | 13 | Reno | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' ONE WAY HENKE,FLINK Model #LMC5H15-NVS4E01 | Telematics Device | Plow Up Down Sensor |  |  | x
5 | 11E | Tonopah | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Reno | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,HENKE,HENKE WING PLOW,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
8 | 13 | Wells | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,SANDER FLINK W PREWET | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Reno | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2014 SNOW DOGG SNOW PLOW EX-80,2014 SNOW DOGG SHPE 2000 | Telematics Device | No | Yes |  | X
8 | 13S | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor |  | HENKE REVERSIBLE,SANDER,DUMP BED | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13 | Wells | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,11 ' REV HENKE PLOW,FLINK 8 CU YD SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11A | Elko | 2020 | DODGE | 5500 | 2020 DODGE RAM 5500 FLATRACK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Tonopah | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ONE WAY PLOW,FLINK,PLOW WING,BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 8 YD W/PRE WET SYSTEM,PLOW,WING PLOW,VARITECH A1-1750-GAS-1LB | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Tonopah | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Fallon | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' ONE WAY PLOW,8 YRD FLINK SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Ely | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 8 CU YD SANDER,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
9 | 14 | Reno | 2003 | KENW | W900B | TRACTOR TRUCK | J1939 |  |  | 1995 SANDER | Telematics Device |  |  |  | X
5 | 11H | Carson City | 1991 | INTL | 4700 | SINGLE AXLE FLATRACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
8 | 13 | Winnemucca | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 8 CU YD,HENKE REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Fallon | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 4 | Carson City | 2017 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Winnemucca | 2002 | WITTKE | FC-70 | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Ely | 2003 | TYMCO | 600 | SWEEPER DUSTLESS | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
2 | 1 | Tonopah | 2013 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Las Vegas | 2013 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Wells | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Winnemucca | 2020 | RAM | 5500 | 2020 RAM 5500 4X4 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Fallon | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 11B | Carson City | 1986 | INTL | 2574 | REBUILD CRANE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | HINKER C-PLOW 8802 | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | ARROW BOARD, T/M/LITEREADER | Telematics Device | No | Yes |  | X
5 | 11J | Las Vegas | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
3 | 5 | Carson City | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Carson City | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Elko | 2009 | PETERBILT | 367 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | BONNELL SANDER 5 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13 | Wells | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | 5 CU YD SANDER,PLOW WING,PLOW REVERSIBLE ALASKAN,5 CU YD FLINK SANDER HOPPER-TYPE W,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Tonopah | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SCHMIDT 12' PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Tonopah | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SWENSON SANDER,11' ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Reno | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YRD SANDER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Elko | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | PLOW WING,SANDER 8 YARD,2000 PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Winnemucca | 2009 | PETERBILT | 367 | TANDEM AXLE HYDRAULICS W/HOOK LIFT | J1939 | Roadwatch Sensor |  | LARSON 5 CU YD,SANDER,REVERSIBLE PLOW,FLATRACK SWAPLOADER,2006 WORKMAN WATER TANK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11F | Tonopah | 1991 | GMC | TC31A | SERVICE TRUCK W/FLATBED | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Tonopah | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE PLOW,SANDER,FLINK 8 CU YD SANDER,SANDER 8 YARD,PLOW WING,SALT BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Tonopah | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1986 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Tonopah | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENDERSON SANDER,1986 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Tonopah | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Winnemucca | 1987 | INTL | F2574 | CRANE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Reno | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,HIGHSPEED 11' PLOW,SANDER 5 YD | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 77 | Reno | 2003 | MACK | MR688S | LINE STRIPER 700 GALLON | J1939 |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 77 | Elko | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICK UP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
7 | 83 | Carson City | 2003 | PETERBILT | 357 | UNDERBRIDGE INSPECTION TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Elko | 2004 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Wells | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Ely | 1994 | INTL | 2574 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 01A | Carson City | 2004 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Winnemucca | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Ely | 1994 | FORD | F-700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Las Vegas | 1995 | INTL | 2574 | TRUCK W/ASPHALT PATCHER | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Reno | 1999 | INTL | F257A | CRANE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
8 | 13 | Las Vegas | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | HENKE SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11D | Las Vegas | 1999 | GMC | TC31403 | COMPACTOR TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13S | Las Vegas | 2009 | PETERBILT | 367 | TANDEM AXLE DUMB TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 4 | Carson City | 2004 | FORD | ECONO | CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Ely | 2004 | CHEVROLET | EXPRESS | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13S | Tonopah | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | SWAPLOADER SANDER,ONE WAY PLOW,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Carson City | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  | 2014 PROFILING SYSTEM PANASONIC TOUGHBOO | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Wells | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2017 | FORD | EXPLORER | 4X4 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK AFV | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Fallon | 1994 | INTL | F2574 | REBUILD SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' RIGHT HAND PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2004 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Ely | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Ely | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Fallon | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,TENCO,5 YRD HENDERSON SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 5 | Winnemucca | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11G | Las Vegas | 1984 | INTL | F2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 13 | Ely | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
8 | 12 | Reno | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 3 | Reno | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Reno | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ONE WAY PLOW,5 YARD SLIDE IN SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11J | Las Vegas | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Elko | 1989 | INTL | 2574 | SERVICE TRUCK W/CRANE | J1939 |  |  |  | Telematics Device | No |  |  | X
8 | 12 | Reno | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,5 YRD FLINK MOD 10 LMC .5H | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Elko | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 6 | Reno | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 10 | Reno | 2013 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 20 | Elko | 1998 | INTL | 4900 | 1998 CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW,2019 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS |  | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Reno | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Wells | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Fallon | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Tonopah | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1986 SANDER,1985 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Tonopah | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 SANDER,1995 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Las Vegas | 2020 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS |  | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CU YARD | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 1995 | GMC | ACL64 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE 11' PLOW,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 4X2 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 20 | Las Vegas | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 12 | Reno | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 CU. YD SANDER,TYNCO REVERSIBLE | Telematics Device | Plow Up Down Sensor |  |  | x
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
6 | 20 | Elko | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2013 | FORD | F-150 | 2013 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 20 | Reno | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Winnemucca | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Reno | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,PLOW,SANDER,8 YARD FLINK SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,1994 SANDER,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Reno | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1994 WING PLOW,PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,ONE WAY PLOW,WING PLOW PPW9HD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11A | Winnemucca | 2005 | INTL | 7400 | AERIAL TRUCK W/PLATFORM | J1939 |  |  |  | Telematics Device | No |  |  | X
9 | 14 | Reno | 1991 | GMC | WG42 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Ely | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 11B | Reno | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Reno | 2003 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 15 | Carson City | 2019 | PETERBILT | 367 | 2019 AWDTANDEM AXLE SANDER/PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS |  | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 12 | Reno | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1996 SANDER,1996 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
6 | 11B | Ely | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  | LITEREADER ARROW BOARD V/M,2020 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Carson City | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER DSL | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Tonopah | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13H | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 12 | Tonopah | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK REBUILD | J1939 | Roadwatch Sensor |  | 10FT PLOW REVERSIBLE,MESSAGE BOARD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Tonopah | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11H | Reno | 2003 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Tonopah | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE 1-WAY PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11E | Winnemucca | 2017 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Reno | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE EXP11NV REV PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE EXP11NV REV SNOW PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE PPW9HD POSTLESS WING PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11F | Ely | 2017 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2018 WESTERN MULE REAR BUMPER CRANE | Telematics Device | No | Yes |  | X
6 | 11B | Fallon | 1988 | INTL | 2574 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | Telematics Device | No |  |  | X
6 | 11G | Las Vegas | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 2021 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11H | Ely | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  | 2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11J | Reno | 2003 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11J | Reno | 2003 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Wells | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | REVERSIBLE PLOW,2018 HENKE SAND SPREADER,2019 HENKE WING PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11J | Las Vegas | 2003 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11J | Elko | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11J | Ely | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 11G | Las Vegas | 1990 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11F | Winnemucca | 2004 | FORD | F-450 | UTILITY TRUCK W/CRANE 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Carson City | 2009 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13H | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXEL DUMP TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Las Vegas | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2007 HENKE PLOW REVERSIBLE,FLINK SANDER 8 YARD | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
7 | 83 | Carson City | 2009 | PETERBILT | 367 | UNDER BRIDGE TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11F | Reno | 1996 | GMC | SIERRA | SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 12 | Ely | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD,1996 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Carson City | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE EXP11NV REV SNOW PLOW | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE EXP11NV REVERSIBLE SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 3 | Fallon | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Elko | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,2020 HENKE PLOW,2020 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
OFF ROAD / NA | 55B | Elko | 2009 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Fallon | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Fallon | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Elko | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Carson City | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Tonopah | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
9 | 14 | Reno | 2004 | PETERBILT | 378 | TRUCK TRACTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11F | Las Vegas | 1999 | DODGE | 3500 | 1 TON SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Fallon | 2018 | ELGIN | EAGLE | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Las Vegas | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Fallon | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Las Vegas | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11F | Las Vegas | 1999 | DODGE | 3500 | SERVICE TRUCK W/CRANE | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Elko | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 PLOW,1995 SANDER,2021 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11J | Reno | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Reno | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Reno | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Las Vegas | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 12 | Tonopah | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1996 SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Ely | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Elko | 2018 | DODGE | RAM 5500 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 FORD F150 1/2 TON EXT CAB S/B | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Winnemucca | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
9 | 14 | Ely | 1991 | INTL | 9300 | REBUILD TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SWENSON 1996 SANDER,ONE WAY | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 12 | Reno | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,8 Yard Sander | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13 | Ely | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | MODEL #12-99 TENCO 12' REVERSIBLE,8 YARD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK SANDER MODEL 15LMC5H | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Winnemucca | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Winnemucca | 2018 | FORD | F-250 | 2018 FORD F-250 LB EXT CAB 4X4 FFUEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Carson City | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ATTENUATOR TRUCK MOUNTED,FLINK 8CU YD-15 LMC 5H | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 3 | Winnemucca | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Winnemucca | 1999 | GMC | TK310 | AWD SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON VHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Las Vegas | 2017 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Carson City | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 SANDER,HEAVY DUTY PATROL WING,FRINK 12' PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Las Vegas | 1999 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Reno | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11A | Reno | 2011 | PETERBILT | 367 | PETERBILT 6X6 AERIAL LIFT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | OBDII | Roadwatch Sensor |  | SANDER | Telematics Device | No | Yes |  | X
8 | 13 | Reno | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' ONE WAY,11 FT REVERSIBLE SNOW PLOW,SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 24 | Reno | 2011 | FREIGHTLNR | M2 | 2011 FREIGHTLINER M2 | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Reno | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVRADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Reno | 2011 | FREIGHTLNR | M2 | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Carson City | 1998 | GMC | TK109 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Las Vegas | 2018 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Reno | 2017 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 01A | Elko | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 3.5L V6 4WD | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Elko | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Las Vegas | 1989 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 PLOW,SWENSON | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
2 | 01A | Elko | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Wells | 2013 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2012 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2019 | JEEP | CHEROKEE | 2019 JEEP CHEROKEE SUV 4X4 UNLEAD | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2019 JEEP GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2018 JEEP GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Wells | 2013 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | X
5 | 11E | Elko | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | X
2 | 01A | Reno | 2018 | JEEP | CHEROKEE | 2019 JEEP LATITUDE CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2018 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Elko | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
2 | 01A | Carson City | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Reno | 2017 | FORD | F-450 | 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA,2018 SNOWDOGG EX80II SNOW PLOW,2018 SALTDOGG SANDER SHPE2000 | Telematics Device | No | Yes |  | X
5 | 24 | Carson City | 2014 | TYMCO | DST6 | INTL TYMCO SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
6 | 28 | Wells | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11H | Elko | 2013 | FORD | F-450 | FLATRACK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11J | Elko | 2013 | FORD | F-450 | UTILITY TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Winnemucca | 2013 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2021 ASPHALT HOTBOX | Telematics Device | No | Yes |  | X
5 | 11E | Ely | 2013 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Wells | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Wells | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Winnemucca | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
6 | 11G | Ely | 1986 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 1986 SANDER | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 24 | Ely | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
6 | 77 | Ely | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Fallon | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2018 | FORD | EXPEDITION | 2018 FORD EXPEDITION SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 28 | Ely | 1996 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 18 CHEVY SILVERADO 1/2 T CREW CAB 4X2 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 2500 | 2018 CHEVY SILVERADO 1/2T CREW CAB SB V8 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 10 | Reno | 2005 | FORD | F-450 | SURVEY UNIT | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 2500 | 2018 CHEV SILVERADO 1/2T CREW CAB SB V8 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11A | Las Vegas | 2017 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Wells | 1996 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11J | Reno | 2019 | FORD | F-350 | 2019 FORD F-350 4X4 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2017 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Las Vegas | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | FORD | 150 | 2018 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Las Vegas | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | MESSAGE SIGN, VEHICLE MOUNTED | Telematics Device | No | Yes |  | X
2 | 01A | Tonopah | 2018 | FORD | EXPLORER | 2018 FORD EXPL SUV 1/2T 5.3 4WD 6 PASS | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 15 | Reno | 2020 | PETERBILT | 567 | 2020 TANDEM AXLE 4X4 SANDER/PLOW TRUCK | J1939 | Roadwatch Sensor |  | 2018 HENKE 40-65-12NV ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
9 | 14 | Reno | 2020 | KENWORTH | W900L | 2020 KENWORTH W900L TRANSPORT TRACTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11D | Las Vegas | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11S | Las Vegas | 2005 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | SWAPLOADER DUMP BODY,SWAPLOADER FLATRACK | Telematics Device | No | Yes |  | X
6 | 28 | Winnemucca | 1986 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON PICK UPS | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2018 | FORD | F-150 | 2018 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Tonopah | 2005 | FORD | F-450 | SERVICE TRUCK W/CRANE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Elko | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW WING,SANDER 8 CUBIC YARDS,REVERSIBLE | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
2 | 01A | Las Vegas | 2005 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Las Vegas | 2005 | GMC | ENVOY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11H | Las Vegas | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  | 2015 ARROW BOARD | Telematics Device | No | Yes |  | X
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13S | Las Vegas | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 4 | Winnemucca | 2019 | CHEVROLET | EXPRESS | PASSANGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Las Vegas | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Reno | 1992 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,SPRATRONICS DE ICER,PLOW REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Winnemucca | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X
2 | 1 | Carson City | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
6 | 28 | Winnemucca | 1993 | INTL | 2574 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2018 GRAND CHAEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2019 | CHEVROLET | MALIBU | 2019 CHEV MALIBU 1.5L TURBO | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Winnemucca | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X
5 | 11J | Carson City | 2006 | FORD | F-350 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 15 | Ely | 1995 | INTL | D3057 | AWD DUMP TRUCK | J1939 | Roadwatch Sensor |  | STAINLESS 7 YD SANDER,1995 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
9 | 14 | Carson City | 2000 | INTL | 9900 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
6 | 20 | Las Vegas | 2000 | INTL | 2674 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X
6 | 15 | Reno | 1995 | INTL | D3057 | AWD SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X
9 | 14 | Tonopah | 1994 | INTL | F9200 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11J | Las Vegas | 2018 | FORD | F-450 | 2018 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11D | Las Vegas | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11D | Las Vegas | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2018 | FORD | F-450 | 2018 FORD F-450 DUMP CREW V10 DRW 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1969 BOUMAN SANDER,1996 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
OFF ROAD / NA | 42 | Reno | 1996 | KODIAK | 6060- | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
5 | 11E | Winnemucca | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Winnemucca | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 76 | Carson City | 1996 | CYBR | SFT50 | REBUILT 2021 INTERNATIONAL CYBERNETICS SKID TRAILER | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 11' LAWTON STR DBL SWING,FLINK 10' LMC5H 5CU YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
3 | 5 | Fallon | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Elko | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Elko | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Elko | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11J | Elko | 2018 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Reno | 1991 | INTL | F2574 | TANDEM AXLE CRANE TRUCK REBUILD | J1939 |  |  | SPRATRONICS DE ICER | Telematics Device | No |  |  | X
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 FORD 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Wells | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE,1996 SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 FORD F450 SNGL AXEL DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
5 | 11A | Elko | 2005 | FORD | F-550 | FLANNIGAN SHOP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Reno | 1992 | FORD | L9000 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | JENSEN 3/38/60 PLOW,5 YRD SANDER | Telematics Device | Plow Up Down Sensor |  |  | x
5 | 24 | Elko | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Elko | 2019 | FORD | F-150 | 2019 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Tonopah | 1986 | INTL | F2574 | CRANE TRUCK CONVERTED | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Las Vegas | 2018 | FORD | F-250 | 2018 FORD F250 3/4T 4X4 CREW | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11C | Las Vegas | 2005 | PETERBILT | 335 | FUEL LUBE TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Winnemucca | 2018 | FORD | F-250 | 2018 FORD F250 3/4T TRUCK 4X4 CREW CAB | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11A | Ely | 2018 | FORD | F-450 | AERIAL TRUCK F-450 1 TON | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
2 | 01A | Reno | 2018 | FORD | EXPLORER | 2018 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Winnemucca | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
9 | 14 | Elko | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
9 | 14 | Carson City | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2011 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Las Vegas | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Las Vegas | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Ely | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X
5 | 11E | Reno | 2018 | FORD | F-450 | 2018 FORD F-450 1 TON DUMP 4X4 | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' STRAIGHT PLOW,2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X
8 | 12 | Winnemucca | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X
5 | 11E | Fallon | 2018 | FORD | F-450 | 2018 1 - 2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X
5 | 11F | Elko | 2008 | FORD | F-650 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Reno | 2005 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Ely | 1990 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YD | Telematics Device |  | Yes | Yes - Forward only | X
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 FORD F-450 1T V10 DUMP EXT CAB 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Reno | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YRD HENDERSON CHIEF,2000 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Reno | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1988 SANDER,1988 REV PLOW,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 12 | Winnemucca | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SNOW PLOW,ATTENUATOR, V/M,2000 SNOW PLOW | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 5 | Carson City | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Reno | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
9 | 14 | Tonopah | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | 1500 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 15 | Carson City | 1989 | INTL | 5070 | AWD DUMP TRUCK | J1939 | Roadwatch Sensor |  | 11' REVERSIBLE PLOW,MONROE A39-52-10 ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Las Vegas | 2012 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Reno | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | MODEL #12-99 TENCO,1999 SANDER | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 12 | Las Vegas | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 11' SWING PLOW,SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
8 | 13 | Reno | 1996 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENDERSON CHIEF 5 YARD,1996 PLOW,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11A | Las Vegas | 2016 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
9 | 14 | Winnemucca | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 11A | Las Vegas | 2015 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Fallon | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11S | Las Vegas | 2014 | FORD | F-450 | DUMP TRUCK W/SWAPLOADER BIODSL | OBDII | Roadwatch Sensor |  | 2014 WILLIAMSEN SWAPLOADER BED | Telematics Device | No | Yes |  | X
3 | 3 | Elko | 2018 | CHEVROLET | SILVERADO | 2018 CHEVEROLET SIVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  | SKIDSTER PICKUP BROOM | Telematics Device |  |  |  | X
8 | 12 | Elko | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
6 | 11B | Las Vegas | 2015 | WESTERN ST | 4900SF | FLATRACK W/CRANE | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 11G | Las Vegas | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 2001 ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2016 WING PLOW,1991 PLOW,FLINK 8 YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YRD FLINK,REVERSIBLE JENSEN MDL 34058 | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | VARITECH 1750 GAL BRINE TANK,MONROE 11' REVERSIBLE PLOW 540-58-11,PLOW REVERSIBLE ALASKA EXPRESSWAY,2014 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11D | Las Vegas | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Carson City | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENDERSEN 5 CU YD SANDER,11' SNOW PLOW, REVERSIBLE, LAWTON EQUIPM | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 24 | Las Vegas | 2015 | ELGIN | EAGLE | SELF PROPELLED DUSTLESS SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,BRINE DISTRIBUTOR | Telematics Device | Plow Up Down Sensor |  |  | x
5 | 11F | Reno | 2015 | FORD | F-350 | 1 TON SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Winnemucca | 2019 | FORD | 250 | 2019 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11A | Reno | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11G | Las Vegas | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
3 | 3 | Carson City | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Fallon | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YRD FLINK SANDER,12' PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11A | Fallon | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Tonopah | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Wells | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YD SANDER,SPRATRONICS DE ICER,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Reno | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Fallon | 2019 | FORD | 250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
6 | 20 | Elko | 2005 | INTL | 7600 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11J | Ely | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' TE STRAIGHT PLOW | Telematics Device | No | Yes |  | X
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Elko | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Fallon | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Fallon | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE JENSEN PLOW,8 YRD FLIMK SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11F | Fallon | 2016 | FORD | F-550 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Reno | 2016 | PETERBILT | 337 | SINGLE AXLE FLATRACK TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Reno | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Ely | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Ely | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICKUP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 01A | Carson City | 2015 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Elko | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Elko | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Elko | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 4 | Carson City | 2015 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | No | Yes |  | X
3 | 5 | Winnemucca | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Elko | 2007 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
OFF ROAD / NA | 55B | Ely | 2005 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  | 6 WAY STRAIGHT BLADE | Telematics Device |  |  |  | X
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Las Vegas | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Carson City | 2006 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 01A | Reno | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Tonopah | 2005 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
2 | 01A | Reno | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 11B | Elko | 2019 | WESTERN ST | 4900SF | 2019 WESTERN STAR FLAT RACK | J1939 |  |  | 2021 SCORPION ATTENUATOR,2021 LITEREADER ARROWBOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11D | Las Vegas | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Tonopah | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11D | Las Vegas | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 01A | Las Vegas | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Carson City | 2019 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW,2020 ASPHALT HOTBOX | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | PLOW,SANDER,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
2 | 01A | Carson City | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x
5 | 11 | Reno | 2019 | KENWORTH | T440 | 2021 KENWORTH T400 | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Reno | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Carson City | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11 | Carson City | 2016 | FREIGHTLNR | M2 112 | HERBICIDE SPRAY TRUCK | J1939 |  |  | INJECTION SPRAYER | Telematics Device |  |  |  | X
5 | 11E | Reno | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11C | Reno | 2016 | FORD | F-550 | LUBE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11D | Las Vegas | 2019 | FORD | F-450 | 2019 FORD COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 FORD 1/2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Ely | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11S | Las Vegas | 2007 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | FLATRACK BODY SWAPLOADER,DUMP BODY SWAPLOADER,ARROWBOARD VEHICLE MOUNTED | Telematics Device | No | Yes |  | X
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Ely | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Reno | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Winnemucca | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Elko | 2006 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Carson City | 2019 | FORD | F-450 | 2019 FORD F-450 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 1 | Reno | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Ely | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Ely | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Ely | 2019 | FORD | F-450 | 2019 1/2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITEREADER ARROWBOARD | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Las Vegas | 2006 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Tonopah | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | ARROW BOARD | Telematics Device | No | Yes |  | X
5 | 11H | Tonopah | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | ARROW BOARD | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Tonopah | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Tonopah | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Reno | 2015 | FORD | F-350 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Reno | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11D | Reno | 2015 | FORD | F-450 | TRASH COMPACTOR 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11D | Reno | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11D | Carson City | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Fallon | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Fallon | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 28 | Las Vegas | 1988 | FORD | 9000 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Ely | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | SNOWPLOW 8' | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | SNOW PLOW,ARROW BOARD | Telematics Device | No | Yes |  | X
5 | 11E | Carson City | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2014 SNOW PLOW SNOW DOGG,2014 SALT DOGG SPREADER | Telematics Device | No | Yes |  | X
3 | 5 | Carson City | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11C | Fallon | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11E | Fallon | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | ROCK PLOW | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Elko | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  | HENKE 11 FT REV SNOW PLOW | Telematics Device | No | Yes |  | X
5 | 11H | Wells | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Wells | 2015 | FORD | F-450 | FLATRACK TRUCK W/LIFT GATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Elko | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 1 | Las Vegas | 2015 | FORD | FOCUS | ELECTRIC SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Elko | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X
2 | 1 | Las Vegas | 2015 | FORD | FOCUS | ELECTRIC SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Elko | 2019 | FORD | F-450 | 2019 FLATRACK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11J | Las Vegas | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/ CAMPERSHELL 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Carson City | 2015 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Elko | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Carson City | 2008 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Carson City | 2019 | FORD | F-450 | 2019 1 TON SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Las Vegas | 2019 | FORD | F-450 | 2019 SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11J | Winnemucca | 2008 | FORD | F-350 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 13 | Tonopah | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Reno | 2020 | WESTERN ST | 4900SF | 2020 TANDEM DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Las Vegas | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11H | Reno | 2016 | FORD | F-550 | 1 1/2 TON FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK W/CAMPERSHELL | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11C | Ely | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Reno | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  | 2013 LIGHT READER 1230 F-4 | Telematics Device |  |  |  | X
5 | 11 | Las Vegas | 1990 | INTL | 4700 | T/M WEED SPRAYER | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11 | Reno | 1990 | INTL | 4700 | INTL TRUCK W/WEED SPRAYER | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11C | Las Vegas | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Reno | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Tonopah | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Tonopah | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Fallon | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Carson City | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Fallon | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Winnemucca | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 15 | Reno | 1988 | INTL | F5070 | AWD 6X6 DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW WING,1988 SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Elko | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Winnemucca | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
9 | 14 | Las Vegas | 2007 | PETERBILT | 378 | TRACTOR TRUCK W/MANUAL TRANS | J1939 |  |  |  | Telematics Device |  |  |  | X
9 | 14 | Las Vegas | 2007 | PETERBILT | 378 | TRUCK TRACTOR W/MANUAL TRANS | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Reno | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
6 | 28 | Elko | 1990 | MACK | MR690 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Ely | 1990 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
2 | 01A | Reno | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Fallon | 1991 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X
9 | 14 | Elko | 2019 | WESTERN | 4900SF | TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  | PROFILING SYSTEM | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Las Vegas | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Elko | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 UTILITY TRUCK WITH CRANE ASSEMBLY | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Carson City | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Winnemucca | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Carson City | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Winnemucca | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Ely | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 10 | Carson City | 2016 | FORD | F-350 | 1 TON TRUCK W/UTILITY BODY | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Ely | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Fallon | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 77 | Winnemucca | 1991 | MACK | MR688 | LINE STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X
6 | 28 | Winnemucca | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Ely | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | No | Yes |  | X
5 | 24 | Elko | 2020 | ELGIN | EAGLE | 2020 SELF PROPELLED TENNANT BR | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
2 | 1 | Elko | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Elko | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Winnemucca | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Las Vegas | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS 15 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
OFF ROAD / NA | 42 | Reno | 1999 | KODIAK | CR65 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
OFF ROAD / NA | 55B | Reno | 2007 | PSTN BULLY | SCOUT | SNOW CAT | None- wired direct |  |  | BLADE 6-WAY | Telematics Device |  |  |  | X
5 | 76 | Carson City | 1992 | DYNA | TEST | FALLING WEIGHT DEFLECTOMETER | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Fallon | 2008 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 76 | Carson City | 2018 | DYNA | 8000 | 2018 SKID TESTER | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11A | Las Vegas | 1997 | GMC | 3500H | AERIAL TRUCK W/MAN LIFT | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Winnemucca | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Reno | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
9 | 14 | Las Vegas | 1996 | FORD | 9501 | TRACTOR TRUCK | J1939 |  |  | BREAKER ATTACHMENT | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Fallon | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
6 | 28 | Reno | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 28 | Tonopah | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
OFF ROAD / NA | 42 | Elko | 1997 | KODIAK | CR400 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
5 | 10 | Las Vegas | 1998 | GMC | K3094 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X
6 | 11B | Elko | 1998 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | ARROW SIGNBOARD, T/M,SCORPION ATTENUATOR TRK MNT | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11J | Reno | 1998 | GMC | TK314 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Reno | 1998 | GMC | TC31003 | DUMP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Reno | 1998 | GMC | TC31003 | DUMP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Las Vegas | 1998 | GMC | W5R04 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | HINKER C- PLOW | Telematics Device | No | Yes |  | X
5 | 11H | Tonopah | 2008 | FORD | F-450 | 1 TON FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | MESSAGE BOARD | Telematics Device | No | Yes |  | X
3 | 3 | Reno | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 3 | Las Vegas | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11J | Tonopah | 2008 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Carson City | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Tonopah | 2008 | FORD | F-450 | 1 TON SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 12 | Las Vegas | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Las Vegas | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Reno | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SKID MOUNTED STAINLESS WATER TANK 1200,SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Fallon | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Carson City | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW REVERSIBLE,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 SANDER HOPPER-TYPE 8 CU YD,PLOW REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 8 CUBIC YARDS,PLOW ALASKAN EXPRESSWAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Reno | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CUBIC YARDS,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Winnemucca | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW REVERSIBLE,5 CUBIC YARD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
9 | 14 | Winnemucca | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
9 | 14 | Carson City | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
9 | 14 | Reno | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,SANDER 8 CUBIC YARDS | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
3 | 3 | Reno | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 24 | Reno | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 1998 | MOBILE | M-8A | SP PICKUP BROOM HIGH DUMP | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
6 | 28 | Carson City | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
6 | 28 | Tonopah | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
OFF ROAD / NA | 55B | Tonopah | 1981 | TUCKER | SNOWCAT | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X
OFF ROAD / NA | 42 | Reno | 1998 | KODIAK | CR65 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x
5 | 11A | Las Vegas | 2019 | FREIGHTLNR | M2 | 2019 AERIAL LIFT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 1999 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11A | Elko | 2018 | DODGE | 5500 | 2018 AERIAL LIFT TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11A | Carson City | 2019 | FORD | F-550 | 2019 ARIEL LIFT TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 01A | Las Vegas | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 4 | Las Vegas | 2021 | FORD | T-350 | 2021 FORD T-350 12 PASSENGER TRANSIT VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Reno | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Carson City | 2016 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
2 | 01A | Las Vegas | 2000 | GMC | JIMMY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
8 | 13 | Reno | 1992 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,SANDER,2001 HENKE REV WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
3 | 4 | Tonopah | 2000 | GMC | TG31405 | AWD CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 5 | Winnemucca | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Winnemucca | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Elko | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 5 | Reno | 2000 | GMC | SIERRA | 1/2 TON PICKUP AWD | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 10 | Las Vegas | 2000 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 10 | Las Vegas | 2000 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Reno | 2001 | INTL | 4700 | FLAT RACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Elko | 2001 | INTL | 4700 | FLAT RACK W/CRANE | J1939 |  |  |  | Telematics Device | No |  |  | X
6 | 11B | Winnemucca | 2001 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 12 | Las Vegas | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 SANDER,HENKE 11' REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 12 | Reno | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,5 YRD | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 12 | Las Vegas | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,1997 SANDER | Telematics Device | Plow Up Down Sensor |  |  | x
3 | 3 | Elko | 1998 | GMC | SIERRA | 3/4 TON PICKUP TRUCK W/SVC BODY AWD | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
8 | 12 | Elko | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,5 YD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Elko | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 FLINK SANDER,11 REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Elko | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW,SANDER 5 CU YD,2020 SCORPION VEH MNT ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 12 | Ely | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Wells | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD Flink,11 FT. REVERSIBLE SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Reno | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE JENSEN PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Wells | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK LCM 10NV-59 SANDER,PLOW,ATTENUATOR, TM,ARROW SIGNBOARD, T/M | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 12 | Wells | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
8 | 12 | Ely | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 CU YD SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 12 | Las Vegas | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X
8 | 13 | Winnemucca | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW TENCO WING,8 CU YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Wells | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,8 YD FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Winnemucca | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE TRK MTED WING PLOW,SANDER 8 CU YD,PLOW REVERSIBLE,PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2011 HENKE ONE-WAY 10 SNOW PLOW,FLINK/MDL 15 LM C5H 8 CU YRD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Carson City | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD SANDER,PLOW,11FT JENSEN REVERSIBLE SNOW PLOW,8 YRD,SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13 | Wells | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YD,HENKE REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
6 | 15 | Las Vegas | 1999 | INTL | F5000 | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
6 | 15 | Reno | 1999 | INTL | F5000 | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 11J | Reno | 2000 | FORD | F-450 | AWD SIGN SHOP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Las Vegas | 2008 | TYMCO | D3T6 | SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11E | Las Vegas | 2000 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11S | Las Vegas | 2000 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | SWAPLOADER DUMP BODY | Telematics Device | No | Yes |  | X
5 | 24 | Las Vegas | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Wells | 2000 | MOBILE | M-8A | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 5 | Las Vegas | 2000 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11 | Reno | 2000 | FORD | F-450 | REBUILD MISC TRUCK - BOX TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 11B | Las Vegas | 2001 | FREIGHTLNR | FL70 | CRANE TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Las Vegas | 2008 | FORD | F-350 | UTILITY TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2000 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  | ARROW BOARD | Telematics Device | No | Yes |  | X
3 | 5 | Reno | 2000 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Carson City | 2000 | DODGE | GRAND CARAVA | 7 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Las Vegas | 2001 | TOYOTA | PRIUS | 4 DOOR SEDAN/HYBRID ELECTRIC | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11J | Reno | 2001 | GMC | SIERRA | UTILITY TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Carson City | 2002 | TOYOTA | PRIUS | HYBRID ELECTRIC SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
2 | 1 | Las Vegas | 2002 | TOYOTA | PRIUS | HYBRID SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Tonopah | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD FLINK,HENKE 4530 | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
5 | 6 | Las Vegas | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11F | Las Vegas | 2002 | FORD | F-550 | SHOP SERVICE TRUCK W/CRANE | OBDII |  |  |  | Telematics Device |  |  |  | X
8 | 12 | Ely | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13H | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
6 | 15 | Carson City | 2001 | INTL | 5600I | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  | HENKE SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
8 | 13H | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
8 | 13H | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x
5 | 11H | Las Vegas | 2000 | FORD | F-450 | 1 TON FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Las Vegas | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Las Vegas | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 11A | Elko | 2002 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11 | Las Vegas | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11 | Las Vegas | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | J1939 |  |  |  | Telematics Device | No |  |  | X
2 | 01A | Las Vegas | 2002 | GMC | ENVOY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
5 | 6 | Reno | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 24 | Carson City | 2003 | GMC | T7500 | GMC T7500 W/WAYNE SWEEPER | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
5 | 24 | Carson City | 2002 | GMC | T7500 | WAYNE WARRIOR SWEEPER | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
8 | 13 | Las Vegas | 2001 | PETERBILT | 320 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11E | Las Vegas | 2002 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
8 | 13 | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSABLE PLOW,SANDER,WATERTANK | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13S | Las Vegas | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | Telematics Device | Plow Up Down Sensor |  |  | x
5 | 11A | Las Vegas | 2005 | FORD | F-550 | AERIAL TRUCK W/ARTICULATING DEVICE | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2004 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11F | Las Vegas | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
6 | 20 | Las Vegas | 2004 | VECTOR | 58055VD | T/M CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x
5 | 11F | Las Vegas | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Las Vegas | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X
3 | 5 | Carson City | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11E | Las Vegas | 2005 | FORD | F-450 | DUMP TRUCK W/ARROWBOARD BIO-DSL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11D | Las Vegas | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,2012 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x
5 | 11E | Reno | 2005 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2019 SNOWDOG SNOW PLOW 9',2019 SALTDOG SAND SPREADER 2.0 CU YD | Telematics Device | No | Yes |  | X
5 | 11H | Reno | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
9 | 14 | Fallon | 2004 | PETERBILT | 378 | TRUCK TRACTOR | J1939 |  |  |  | Telematics Device |  |  |  | X
6 | 20 | Carson City | 2004 | INTL | 7600 6X4 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X
5 | 11H | Carson City | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X
5 | 11H | Fallon | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X
5 | 11H | Reno | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X
5 | 11H | Fallon | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X
5 | 11H | Reno | 2005 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11H | Carson City | 2005 | FORD | F-450 | 1 TON FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2006 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2 YARD SANDER,SNOW PLOW | Telematics Device | No | Yes |  | X
5 | 11E | Reno | 2006 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11F | Carson City | 2005 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
3 | 5 | Carson City | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 6 | Las Vegas | 2006 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  | SPREADER BED MOUNT,SNOW V PLOW 4 WAY, | Telematics Device | No | Yes |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11 | Las Vegas | 2007 | INTL | 7400 | WEED SPRAYER TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X
3 | 3 | Reno | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11 | Las Vegas | 2006 | INTL | 4200 | BUTTON TRUCK W/UTILITY BODY | J1939 |  |  | ARROW BOARD | Telematics Device | No |  |  | X
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
5 | 11H | Las Vegas | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 24 | Reno | 2006 | FREIGHTLNR | SC-8000 | SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x
3 | 3 | Carson City | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Carson City | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Las Vegas | 2007 | FORD | EXPLORER | SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X
2 | 01A | Las Vegas | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
2 | 1 | Carson City | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 4 | Carson City | 2008 | GMC | SAVANA | CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X
5 | 11J | Reno | 2008 | FORD | F-450 | UTILITY TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2012 HINKER C-PLOW | Telematics Device | No | Yes |  | X
5 | 11S | Las Vegas | 2008 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X
8 | 13 | Las Vegas | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X
8 | 13S | Reno | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | SPRAYTRONIC DE-ICER,PLOW REVERSIBLE,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13S | Reno | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | PLOW REVERSIBLE,2003 SANDERS,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,WATER TANK, SWAPLOADER,PLOW | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 13S | Tonopah | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | HENKE ONEWAY PLOW,SANDER SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x
7 | 83 | Carson City | 2020 | WESTERN ST | 4900 | UNDERBRIDGE INSPECTION TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X
8 | 25 | Las Vegas | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Elko | 1976 | PETERBILT | MD359 | TRACTOR TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Reno | 2006 | INTL | 5900I | 2006 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Carson City | 2007 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Las Vegas | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Tonopah | 2002 | INTL | F2574 | TANDEM AXLE WATER TRUCK REBUILD | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Reno | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Las Vegas | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Ely | 1983 | AUTOCAR | KM64F | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Tonopah | 1980 | MACK | RS685 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Reno | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Wells | 1989 | MACK | RD688 | 3500 GALLON WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Winnemucca | 1990 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Wells | 1991 | INTL | F2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Las Vegas | 2018 | MACK | GR64F | 2018 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Tonopah | 2018 | MACK | GR64F | 2018 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Las Vegas | 2019 | INTL | HX620 | 2019 INT'L HX 620 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Las Vegas | 1987 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Ely | 1991 | INTL | F2574 | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Ely | 1990 | INTL | 2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Winnemucca | 1991 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Elko | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Tonopah | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Reno | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Las Vegas | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Ely | 1997 | INTL | 2574 | 1997 REBUILT TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  | PLOW,8 YRD SANDER CHIEF | Telematics Device | Plow Up Down Sensor |  |  | x
8 | 25 | Las Vegas | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Reno | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Carson City | 2006 | INTL | 5900I | TRUCK , W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Carson City | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
8 | 25 | Reno | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x
5 | 11F | Fallon | 2019 | FORD | F-550 | F-550 SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X
3 | 3 | Fallon | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X

## Install Location Total
NDOT Vehicle Installation Locations

## OLD - UnitMaster - Phase Calcul (hidden)
Installer Type (0=Geotab, 1=Gofleet) | [15 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
Time Requirement (hrs) | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1 | 0.75 | 1 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0
Qty of Components (ea.) | [15 empty] | 990 | 418 | 13 | 152 | 881 | 314 | 25 | 25 | 124 |  | 328 | 66 | 66 | 44 | 8 | 1514 | 59 | 59 | 2295 | 32 | 1376 | 152 | 758 | 702 | 2236 |  |  |  | Geotab (TBD) | GoFleet
Rate | [41 empty] | 5730.75 |  | 110 | 110 | 457352.5 | 630382.5
AUX TYPE | [22 empty] | AUX 1-4 - IOX-AUXM - AUX 5-7 - IOX-WRKS
Aux Channel (1-8) | [22 empty] | 4 | 7 | 6 | 5 | 1 | 2 | 3 | 4 | 8
[21 empty] | Cameras |  | Digital Sensors | [8 empty] | Analog Sensors
Federal MCC | NDOT Class code | Installation Location | Year | Make | Model | Description | Existing OBDII/J1939 | Existing Roadwatch SS | Existing Parker/CIRUS/FORCE AMERICA/EPOKE | Existing Associations/Hardware | Telematic Device / Telematics device for Winter Operations needed | Sensors needed | Wi-Fi HotSpot needed | Cameras needed | Check | OBDII | J1939 (9 pin) | Direct Wiring (3 wire) | Winter Operations With J1939 (9 pin) | Wi-Fi HotSpot | Forward Cameras | Rear Cameras | Attenuator Up Down | Wing Plow Up/Down Down | Front Plow Up/Down | Belly Plow Up Down | Broom Up Down | Hopper full indication | Pump on/off | Snow Blower Activation | Light Bar Activation | Barometric Pressure | Humidity | Total Sensors | IOX-SATIRDV2 | IOX - AUXM | IOX - WRKS | IOX - BT | Roadwatch (Integration) | Sensor exc humidity | Phase | Estimated Time | POC Hrs | Geotab Install (hrs) | Gofleet Install (hrs) | Cost Minus 1hr GO Install Cost | Our Cost w/1hr GO Install Cost | Install Package | Packages | Hrs | Price | Notes | Phase | Unit Number | Locations
8 | 13 | Carson City | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE SINGEL AUGER CARTRIDGE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 |  | 8.75 | 0 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 2 | 3198 | Carson City
8 | 13 | Reno | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE AUGER CARTRIDGE SANDER,2020 REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Pilot | 3199 | Reno
8 | 13 | Elko | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | PLOW REVERSIBLE ALASKAN,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75 | 8.75 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 584 | Elko
8 | 13 | Reno | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SANDER,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75 | 8.75 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Pilot | 3200 | Reno
8 | 13 | Ely | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE SINGLE SANDER,2020 HENKE ONE WAY PLOW,2020 HENKE WING PLAY | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 |  | 8.75 | 0 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 2 | 616 | Ely
8 | 13 | Winnemucca | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | 2020 HENKE SINGLE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 |  | 8.75 | 0 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 623 | Winnemucca
8 | 13 | Carson City | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 841 | Carson City
8 | 13 | Wells | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 3 | 964 | Wells
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW,2019 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75 | 8.75 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 1220 | Elko
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS |  | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 1221 | Ely
8 | 13 | Las Vegas | 2020 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS |  | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 1 | 1232 | Las Vegas
8 | 13 | Ely | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,ONE WAY PLOW,WING PLOW PPW9HD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 1264 | Ely
8 | 13 | Reno | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE EXP11NV REV PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Pilot | 1317 | Reno
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE EXP11NV REV SNOW PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 3 | 1318 | Fallon
8 | 13 | Carson City | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE PPW9HD POSTLESS WING PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 1319 | Carson City
8 | 13 | Wells | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | REVERSIBLE PLOW,2018 HENKE SAND SPREADER,2019 HENKE WING PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 3 | 1333 | Wells
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 3 | 1352 | Fallon
8 | 13 | Tonopah | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 |  | 8.75 | 0 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 2059 | Tonopah
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 3 | 2060 | Fallon
8 | 13 | Carson City | 2019 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 2064 | Carson City
8 | 13 | Carson City | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW,2020 ASPHALT HOTBOX | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 2065 | Carson City
8 | 13 | Reno | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Pilot | 2067 | Reno
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | PLOW,SANDER,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 | POC | 8.75 | 8.75 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 2068 | Elko
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 4 |  | 8.25 | 0 | 0 | 8.25 | 797.5 | 907.5 | [5 empty] | Phase 2 | 2071 | Ely
8 | 13 | Winnemucca | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 |  | 8.75 | 0 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 2072 | Winnemucca
8 | 13 | Winnemucca | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 FLINK SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 1 | 0 | 1 | 1 | 0 | 4 |  | 8.75 | 0 | 0 | 8.75 | 852.5 | 962.5 | [5 empty] | Phase 4 | 2073 | Winnemucca
8 | 13 | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 YD SANDER,PLOW,2006 HENKE PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 1 | 0 | 1 | 1 | 1 | 4 |  | 6.75 | 0 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Phase 4 | 301 | Winnemucca
8 | 13 | Winnemucca | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 |  | Assumptions |  |  |  | Phase 4 | 3025 | Winnemucca
8 | 13 | Wells | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE-WAY PLOW,2017 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 |  | Geotab is able to install all IOX devices |  |  |  | Phase 3 | 3026 | Wells
8 | 13 | Reno | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 |  | Cameras possibly being done by Geotab - at Geotab Rate |  |  |  | Pilot | 3028 | Reno
8 | 13 | Fallon | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 3 | 559 | Fallon
6 | 13 | Tonopah | 2017 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 4 | 3029 | Tonopah
8 | 13 | Wells | 2020 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | SANDER, REVERSIBLE PLOW, DUMP BODY | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 1 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 3 | 3033 | Wells
8 | 13 | Winnemucca | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8 | 8 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 3034 | Winnemucca
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2018 HENKE NOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8 | 8 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 575 | Elko
8 | 13 | Winnemucca | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | REVERSIBLE PLOW,8 CU YD HENDERSON,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8 | 8 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 3037 | Winnemucca
8 | 13 | Elko | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,REVERSIBLE PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8 | 8 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 593 | Elko
8 | 13S | Elko | 2017 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER 8 CUBIC YARDS,WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8 | 8 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 679 | Elko
8 | 13 | Tonopah | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 4 | 779 | Tonopah
8 | 13 | Fallon | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 3 | 836 | Fallon
6 | 15 | Reno | 2017 | PETERBILT | 367 | TANDEM AXLE PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Pilot | 848 | Reno
8 | 13 | Winnemucca | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 |  | 8 | 0 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 952 | Winnemucca
8 | 13 | Las Vegas | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | HENKE SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 1 | 1137 | Las Vegas
6 | 15 | Carson City | 2019 | PETERBILT | 367 | 2019 AWDTANDEM AXLE SANDER/PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS |  | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 2 | 1280 | Carson City
8 | 13 | Tonopah | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 4 | 1301 | Tonopah
8 | 13 | Tonopah | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 4 | 1305 | Tonopah
8 | 13 | Tonopah | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE 1-WAY PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 4 | 1314 | Tonopah
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 3 | 1332 | Fallon
8 | 13 | Elko | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 | POC | 8 | 8 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 1334 | Elko
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 2 | 1336 | Ely
8 | 13 | Ely | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 2 | 1341 | Ely
8 | 13 | Winnemucca | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 0 | 1 | 1 | 0 | 3 |  | 8 | 0 | 0 | 8 | 770 | 880 | [5 empty] | Phase 4 | 1342 | Winnemucca
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 3 | 1358 | Fallon
8 | 13 | Fallon | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 0 | 1 | 1 | 0 | 3 |  | 7.5 | 0 | 0 | 7.5 | 715 | 825 | [5 empty] | Phase 3 | 1361 | Fallon
8 | 13 | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE EXP11NV REV SNOW PLOW | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 1 | 0 | 1 | 0 | 3 |  | 7.5 | 0 | 1 | 6.5 | 715 | 825 | [5 empty] | Phase 1 | 1364 | Las Vegas
8 | 13 | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | 2019 HENKE EXP11NV REVERSIBLE SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 1 | 0 | 1 | 0 | 3 |  | 7.5 | 0 | 1 | 6.5 | 715 | 825 | [5 empty] | Phase 1 | 1366 | Las Vegas
8 | 13 | Las Vegas | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 | 1 | 0 | 1 | 0 | 3 |  | 7.5 | 0 | 1 | 6.5 | 715 | 825 | [5 empty] | Phase 1 | 2014 | Las Vegas
8 | 13 | Carson City | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor | EPOKE | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 761 | Carson City
8 | 13 | Tonopah | 2006 | WESTERN ST | 4900 | TANDEM AXLE TRUCK | J1939 | Roadwatch Sensor | EPOKE | PLOW WING,JENSEN REVERSIBLE PLOW,SANDER EPOKE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 34 | Tonopah
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 82 | Reno
8 | 15 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 2909 | Reno
8 | 13S | Las Vegas | 2019 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | FLAT RACK SWAPLOADER | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.75 | 0 | 1 | 5.75 | 632.5 | 742.5 | [5 empty] | Phase 1 | 2007 | Las Vegas
8 | 13S | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Pilot | 552 | Reno
8 | 13S | Tonopah | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,PLOW WING,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 297 | Tonopah
8 | 13S | Tonopah | 1994 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HEAVY DUTY PATROL WING PLOW,11' REVERSIBLE LEWTON MDL RO1144NV,FLINK MDL #LMC5H-15NV-39 | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 304 | Tonopah
8 | 13 | Fallon | 1994 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 1994 PLOW,HENKE WING PLOW,8 YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 309 | Fallon
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 900 GALLON DE-ICING SPRAYER,PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 170 | Elko
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 333 | Reno
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE TRK MTED WING PLOW,SANDER 8 YARD,PLOW REVERSIBLE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 1 | 1 | 3 |  | 6.75 | 0 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Phase 1 | 339 | Reno
8 | 13 | Ely | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 340 | Ely
8 | 13S | Winnemucca | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Phase 4 | 954 | Winnemucca
8 | 13 | Carson City | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Phase 2 | 956 | Carson City
8 | 13S | Fallon | 1989 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,REVERSIBLE 11' SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 979 | Fallon
8 | 13 | Winnemucca | 1996 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,1990 HENDERSON SANDER 10 YD,ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 985 | Winnemucca
8 | 13 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TWO-WAY SWING PLOW,FLINK SANDER 8 CU YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1355 | Elko
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Pilot | 1356 | Reno
8 | 13 | Fallon | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,REVERSIBLE PLOW,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Phase 3 | 1362 | Fallon
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | FLINK SANDER,HEAVY DUTY WING PLOW,PLOW REVERSIBLE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1518 | Ely
8 | 13 | Ely | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 1 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 0 | 6.75 | 632.5 | 742.5 | [5 empty] | Phase 2 | 1628 | Ely
5 | 24 | Winnemucca | 2001 | WITTKE | WIZARD FC-70 | SELF PROPELLED ROAD BROOM | J1939 |  |  | BUCKET, 71 DITCH CLEANING | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 271 | Winnemucca
8 | 13 | Carson City | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REVERSIBLE PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1915 | Carson City
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1918 | Elko
8 | 13S | Winnemucca | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1925 | Winnemucca
8 | 13 | Reno | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD,2012 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Pilot | 1956 | Reno
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | VARITECH 1750 GALLON TANK,SANDER 8 YARD,HEAVY DUTY WING PLOW,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1966 | Elko
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1968 | Elko
8 | 13 | Tonopah | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2162 | Tonopah
8 | 13 | Reno | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Pilot | 2163 | Reno
8 | 13 | Tonopah | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TENCO 11FT REVERSIBLE PLOW,8 YARD FLINK SANDER,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2270 | Tonopah
8 | 13 | Reno | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,1991 PLOW,1991 SANDER,TENCO 11 FT. REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Pilot | 2272 | Reno
8 | 13 | Reno | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW,2001 FLINK SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Pilot | 2274 | Reno
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 366 | Las Vegas
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 367 | Las Vegas
5 | 24 | Tonopah | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 368 | Tonopah
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TENKO 1 WAY PLOW,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2279 | Winnemucca
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,VARITECH 1750 GAL BRINE TANK,PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2280 | Winnemucca
8 | 13 | Las Vegas | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER 8 YARD,REVERSABLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 2282 | Las Vegas
5 | 24 | Elko | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 3 | POC | 4.5 | 4.5 | 1 | 3.5 | 385 | 495 | [5 empty] | Phase 4 | 420 | Elko
5 | 24 | Elko | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 3 | POC | 4.5 | 4.5 | 1 | 3.5 | 385 | 495 | [5 empty] | Phase 4 | 428 | Elko
5 | 24 | Wells | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 430 | Wells
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | FLINK 8 CU YD SANDER,11' TENCO PLOW,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 2779 | Reno
8 | 13 | Las Vegas | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE TRK MTED WING PLOW,PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 2920 | Las Vegas
5 | 24 | Fallon | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 453 | Fallon
5 | 24 | Reno | 2017 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Pilot | 456 | Reno
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 462 | Las Vegas
8 | 13 | Tonopah | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REVERSIBLE,FLINK 8 CUBIC YARD SANDER,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2928 | Tonopah
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 494 | Las Vegas
5 | 24 | Carson City | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 495 | Carson City
8 | 13 | Wells | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE HEAVY DUTY PATROL,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 2998 | Wells
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 498 | Las Vegas
8 | 13 | Wells | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE WING PLOW,TENCO,FLINK,SPRATRONICS | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 3004 | Wells
8 | 13 | Carson City | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 1991 PLOW,2000 SANDER,HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 3020 | Carson City
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Pilot | 526 | Reno
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 3 |  | 6.25 | 0 | 0 | 6.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 3024 | Reno
8 | 13 | Winnemucca | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SANDER,ONE WAY PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 1 | 1 | 0 | 2 |  | 6.75 | 0 | 0 | 6.75 | 632.5 | 742.5 |  | Geotab hourly rate $100 - TBD |  |  |  | Phase 4 | 3027 | Winnemucca
8 | 13 | Winnemucca | 2018 | MACK | GR64FR | 2018 MACK GRANITE TANDEM AXLE HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA |  | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 0 | 1 | 1 | 1 | 2 | POC | 7.25 | 7.25 | 0 | 7.25 | 687.5 | 797.5 | [5 empty] | Phase 4 | 3030 | Winnemucca
5 | 24 | Las Vegas | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 662 | Las Vegas
8 | 13 | Carson City | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | J1939 | Roadwatch Sensor |  | PLOW,HEAVY DUTY PATROL WING,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 206 | Carson City
5 | 24 | Las Vegas | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 673 | Las Vegas
8 | 13 | Winnemucca | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | WING PLOW,8 YD,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 223 | Winnemucca
8 | 13 | Tonopah | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER 8 YD,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 226 | Tonopah
8 | 13 | Tonopah | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 7532,WING PLOW,HENKE 12' RIGHTHAND,2014 VARITECH AI-1850 BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 236 | Tonopah
8 | 13 | Ely | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ONE WAY PLOW,SANDER,DE-ICING SPRAYER,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 246 | Ely
8 | 13 | Elko | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,FLINK 8 YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 1 | 5.75 | 632.5 | 742.5 | [5 empty] | Phase 4 | 248 | Elko
8 | 13 | Tonopah | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE 4422,FLINK 7511,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 256 | Tonopah
8 | 13 | Ely | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW WING,ONE WAY,8 YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 265 | Ely
5 | 24 | Tonopah | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 787 | Tonopah
8 | 13 | Tonopah | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,FLINK SANDER,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 4 | 585 | Tonopah
8 | 13 | Winnemucca | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE REVERSIBLE,PLOW WING,FLINK SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 587 | Winnemucca
8 | 13 | Reno | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,HENKE,HENKE WING PLOW,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Pilot | 611 | Reno
8 | 13 | Wells | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,11 ' REV HENKE PLOW,FLINK 8 CU YD SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 622 | Wells
8 | 13 | Tonopah | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ONE WAY PLOW,FLINK,PLOW WING,BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 625 | Tonopah
8 | 13 | Tonopah | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 8 YD W/PRE WET SYSTEM,PLOW,WING PLOW,VARITECH A1-1750-GAS-1LB | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 626 | Tonopah
8 | 13 | Ely | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 8 CU YD SANDER,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 633 | Ely
5 | 24 | Winnemucca | 2002 | WITTKE | FC-70 | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 994 | Winnemucca
5 | 24 | Ely | 2003 | TYMCO | 600 | SWEEPER DUSTLESS | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 996 | Ely
8 | 13 | Wells | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | 5 CU YD SANDER,PLOW WING,PLOW REVERSIBLE ALASKAN,5 CU YD FLINK SANDER HOPPER-TYPE W,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 675 | Wells
8 | 13 | Elko | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | PLOW WING,SANDER 8 YARD,2000 PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 1 | 5.75 | 632.5 | 742.5 | [5 empty] | Phase 4 | 682 | Elko
8 | 13 | Elko | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 1 | 1 | 3 | POC | 6.75 | 6.75 | 1 | 5.75 | 632.5 | 742.5 | [5 empty] | Phase 4 | 684 | Elko
8 | 12 | Tonopah | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE PLOW,SANDER,FLINK 8 CU YD SANDER,SANDER 8 YARD,PLOW WING,SALT BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 691 | Tonopah
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 702 | Fallon
8 | 13 | Wells | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 706 | Wells
8 | 13 | Reno | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 707 | Reno
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 749 | Fallon
8 | 13 | Carson City | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 763 | Carson City
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 776 | Fallon
8 | 13 | Ely | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 2 | 780 | Ely
8 | 12 | Reno | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ONE WAY PLOW,5 YARD SLIDE IN SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Pilot | 794 | Reno
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1254 | Las Vegas
8 | 13 | Reno | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,PLOW,SANDER,8 YARD FLINK SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 873 | Reno
8 | 13 | Reno | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,1994 SANDER,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 890 | Reno
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1258 | Las Vegas
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1259 | Las Vegas
8 | 13 | Reno | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1994 WING PLOW,PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 894 | Reno
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Pilot | 1297 | Reno
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Pilot | 1298 | Reno
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Pilot | 1299 | Reno
5 | 24 | Carson City | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER DSL | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 1300 | Carson City
5 | 24 | Reno | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1308 | Reno
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Pilot | 1313 | Reno
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1320 | Reno
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  | 2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1328 | Reno
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1330 | Reno
5 | 24 | Reno | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1339 | Reno
8 | 13 | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 977 | Tonopah
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,2020 HENKE PLOW,2020 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 984 | Wells
5 | 24 | Fallon | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 1378 | Fallon
5 | 24 | Elko | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 3 | POC | 4.5 | 4.5 | 1 | 3.5 | 385 | 495 | [5 empty] | Phase 4 | 1381 | Elko
5 | 24 | Las Vegas | 2018 | ELGIN | EAGLE | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1395 | Las Vegas
5 | 24 | Fallon | 2018 | ELGIN | EAGLE | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 1399 | Fallon
5 | 24 | Las Vegas | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1407 | Las Vegas
5 | 24 | Las Vegas | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1418 | Las Vegas
8 | 13 | Ely | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | MODEL #12-99 TENCO 12' REVERSIBLE,8 YARD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1076 | Ely
8 | 13 | Carson City | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 SANDER,HEAVY DUTY PATROL WING,FRINK 12' PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1189 | Carson City
5 | 24 | Reno | 2011 | FREIGHTLNR | M2 | 2011 FREIGHTLINER M2 | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1486 | Reno
5 | 24 | Reno | 2011 | FREIGHTLNR | M2 | ELGIN EAGLE SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1491 | Reno
5 | 24 | Carson City | 2014 | TYMCO | DST6 | INTL TYMCO SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 1612 | Carson City
5 | 24 | Wells | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 1630 | Wells
5 | 24 | Wells | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 1631 | Wells
5 | 24 | Ely | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 1638 | Ely
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW WING,SANDER 8 CUBIC YARDS,REVERSIBLE | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 1331 | Wells
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1335 | Ely
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1343 | Ely
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,SPRATRONICS DE ICER,PLOW REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 | POC | 6.25 | 6.25 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1368 | Elko
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 | POC | 6.25 | 6.25 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1372 | Elko
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 11' LAWTON STR DBL SWING,FLINK 10' LMC5H 5CU YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 1427 | Las Vegas
5 | 24 | Elko | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 | POC | 4 | 4 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 1832 | Elko
5 | 24 | Winnemucca | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 1847 | Winnemucca
8 | 12 | Las Vegas | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 11' SWING PLOW,SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 1569 | Las Vegas
8 | 13 | Reno | 1996 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENDERSON CHIEF 5 YARD,1996 PLOW,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 1570 | Reno
8 | 13 | Winnemucca | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2016 WING PLOW,1991 PLOW,FLINK 8 YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1642 | Winnemucca
8 | 13 | Carson City | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | VARITECH 1750 GAL BRINE TANK,MONROE 11' REVERSIBLE PLOW 540-58-11,PLOW REVERSIBLE ALASKA EXPRESSWAY,2014 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 2 | 1651 | Carson City
5 | 24 | Las Vegas | 2015 | ELGIN | EAGLE | SELF PROPELLED DUSTLESS SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 1920 | Las Vegas
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 | POC | 6.25 | 6.25 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 1690 | Elko
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 2046 | Las Vegas
5 | 24 | Las Vegas | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 2052 | Las Vegas
8 | 13 | Tonopah | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2058 | Tonopah
8 | 13 | Reno | 2020 | WESTERN ST | 4900SF | 2020 TANDEM DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 2062 | Reno
6 | 15 | Reno | 1988 | INTL | F5070 | AWD 6X6 DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW WING,1988 SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 2164 | Reno
5 | 24 | Elko | 2020 | ELGIN | EAGLE | 2020 SELF PROPELLED TENNANT BR | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 | POC | 4 | 4 | 1 | 3 | 330 | 440 | [5 empty] | Phase 4 | 2491 | Elko
5 | 24 | Fallon | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 2685 | Fallon
5 | 24 | Reno | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 2795 | Reno
5 | 24 | Las Vegas | 1998 | MOBILE | M-8A | SP PICKUP BROOM HIGH DUMP | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 2801 | Las Vegas
8 | 13 | Reno | 1992 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE WING PLOW,SANDER,2001 HENKE REV WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 1 | 2487 | Reno
8 | 13 | Winnemucca | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW TENCO WING,8 CU YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2774 | Winnemucca
8 | 13 | Winnemucca | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE TRK MTED WING PLOW,SANDER 8 CU YD,PLOW REVERSIBLE,PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 2776 | Winnemucca
8 | 13 | Wells | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YD,HENKE REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 3 | 2783 | Wells
5 | 24 | Las Vegas | 2008 | TYMCO | D3T6 | SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3035 | Las Vegas
5 | 24 | Las Vegas | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3039 | Las Vegas
5 | 24 | Las Vegas | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3040 | Las Vegas
5 | 24 | Wells | 2000 | MOBILE | M-8A | STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 3 | 3041 | Wells
5 | 24 | Las Vegas | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3132 | Las Vegas
5 | 24 | Las Vegas | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3133 | Las Vegas
5 | 24 | Las Vegas | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3134 | Las Vegas
5 | 24 | Las Vegas | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3135 | Las Vegas
5 | 24 | Las Vegas | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3136 | Las Vegas
5 | 24 | Las Vegas | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3137 | Las Vegas
5 | 24 | Carson City | 2003 | GMC | T7500 | GMC T7500 W/WAYNE SWEEPER | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 3169 | Carson City
5 | 24 | Carson City | 2002 | GMC | T7500 | WAYNE WARRIOR SWEEPER | OBDII |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 2 | 3172 | Carson City
8 | 13 | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,2012 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 3 |  | 6.25 | 0 | 1 | 5.25 | 577.5 | 687.5 | [5 empty] | Phase 4 | 3187 | Tonopah
5 | 24 | Reno | 2006 | FREIGHTLNR | SC-8000 | SELF PROPELLED P/U BROOM | J1939 |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 3 |  | 4 | 0 | 1 | 3 | 330 | 440 | [5 empty] | Phase 1 | 3294 | Reno
8 | 13 | Tonopah | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | EPOKE | SANDER EPOKE,HEAVY DUTY PATROL WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 |  | Install Hours no RW/GO | 3155 | 347050 |  | Phase 4 | 32 | Tonopah
6 | 13 | Reno | 2007 | PETERBILT | 357 | AWD TRUCK W/EPOKE SANDER | J1939 | Roadwatch Sensor | EPOKE | PLOW SLOTTED TRIP,PLOW ONE WAY,JENSEN 12 FT ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 54 | Reno
6 | 13 | Reno | 2016 | PETERBILT | 367 | AWD TANDEM AXLE PLOW TRUCK | J1939 | Roadwatch Sensor | EPOKE | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 62 | Reno
6 | 15 | Reno | 2016 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | J1939 | Roadwatch Sensor | EPOKE |  | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 66 | Reno
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | WATER TANK SWAPLOADER,PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,FLAT RACK, SWAPLOADER,2014 LITE READER 1230F-4,TRUCK MOUNTED ATTENUATOR | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 955 | Carson City
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 1897 | Reno
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 1899 | Carson City
8 | 15 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 2306 | Reno
8 | 15 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 2910 | Reno
8 | 13S | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1347 | Elko
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/ HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | 15 FOOT SWAPLOADER DUMP BODY,2006 HENKE PLOW REVERSIBLE,2006 FLINK SANDER 8 YARD,SWAPLOADER WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 323 | Reno
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2018 REVERSIBLE PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 327 | Carson City
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD,SLIDE IN PRAYER,PLOW,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 167 | Elko
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 172 | Elko
OFF ROAD / NA | 42 | Carson City | 2020 | KODIAK | 1200 | 2020 KODIAK ROTARY BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 2 | 191 | Carson City
8 | 13 | Winnemucca | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW UNDERBODY,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 342 | Winnemucca
8 | 13 | Carson City | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 877 | Carson City
8 | 13 | Tonopah | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | SWAPLOADER WATER TANK,ONE WAY PLOW,SANDER 8 YARD,DUMP BODY SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 884 | Tonopah
8 | 13 | Ely | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 963 | Ely
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SPRATRONICS DE ICER,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 966 | Reno
8 | 13 | Carson City | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER,HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 986 | Carson City
8 | 13 | Reno | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 1327 | Reno
OFF ROAD / NA | 42 | Reno | 2020 | KODIAK | 1200 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Pilot | 234 | Reno
8 | 13 | Fallon | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2000 PLOW PLOWS,REBUILD 2006 SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 3 | 1329 | Fallon
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK WORKMAN SWAPLOADER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1338 | Las Vegas
6 | 11B | Las Vegas | 2007 | FREIGHTLNR | FDL120 | CRANE TRUCK W/FLATBED | J1939 |  |  | ATTENUATOR W/VERTICAL LIFT ARROW BOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 241 | Las Vegas
8 | 13S | Tonopah | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE 12FT RGHT HAND DISCHARGE,REVERSIBLE,REBUILD 2008 HENDERSON SANDER/HOPPER TYP | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1346 | Tonopah
8 | 13 | Elko | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REBUILD 2000 SANDER,REBUILD 2000 PLOWS,REBUILD 1999 PLOWS | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1351 | Elko
8 | 13 | Elko | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1387 | Elko
8 | 13 | Reno | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 1474 | Reno
8 | 13 | Fallon | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,8 YD STAINLESS STEEL SANDER,PLOW ONE WAY,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 3 | 1632 | Fallon
8 | 13 | Ely | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 1705 | Ely
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1706 | Elko
8 | 13 | Ely | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 1728 | Ely
8 | 13 | Winnemucca | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1865 | Winnemucca
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | HENKE 11FT REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1895 | Elko
8 | 13 | Elko | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1896 | Elko
8 | 13S | Tonopah | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW,SANDER W/PREWET SYSTEM | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 1898 | Tonopah
8 | 13 | Fallon | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | REVERSIBLE PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 3 | 1904 | Fallon
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1929 | Las Vegas
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1932 | Las Vegas
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1935 | Las Vegas
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 3 | 1965 | Wells
8 | 13 | Reno | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | VARITECH BRINE DISTRIBUTION TANK,PLOW REVERSIBLE,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 2038 | Reno
8 | 13 | Tonopah | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 2041 | Tonopah
6 | 13 | Ely | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2011 HENKE 10 ONE-WAY SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 2219 | Ely
6 | 13 | Ely | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW TRUCK PATROL | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 2220 | Ely
8 | 13 | Carson City | 2016 | PETERBILT | 367 | TANDEM AXLE SWAP LOADER | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY PLOW,SANDER,DUMP BODY | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 2275 | Carson City
8 | 13 | Reno | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SNOW PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 2276 | Reno
8 | 13S | Las Vegas | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | DUMP BODY SWAP-LOADER,WATER TANK WRKMAN SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 2277 | Las Vegas
6 | 20 | Reno | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Pilot | 370 | Reno
8 | 13 | Fallon | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 3 | 2278 | Fallon
6 | 20 | Las Vegas | 2016 | PETERBILT | 567 | VACTOR 2100 CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 409 | Las Vegas
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 CU YD FLINK LMC1H SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 4 | 2292 | Elko
8 | 15 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2000 SANDER,SPRATRONICS DE ICER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 2682 | Reno
8 | 15 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | TENCO PLOW,FLINK SANDER 8 CU YRD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 2684 | Reno
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 2778 | Reno
6 | 20 | Tonopah | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 452 | Tonopah
6 | 20 | Elko | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 490 | Elko
8 | 13 | Ely | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | ONE WAY HENKE,2000 SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 3018 | Ely
8 | 13 | Reno | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 1 | 3019 | Reno
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 8 CU YD FLINK LMC1H SANDER,REVERSIBLE PLOW, TENCO TC-132,DE-ICING SPRAYER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Pilot | 3021 | Reno
8 | 13 | Carson City | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | SANDER 8 CU YD HOPPER TYPE F,PLOW REVERSIBLE, TENCO TC-132 | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 3022 | Carson City
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | 5.5 | 0 | 0 | 5.5 | 495 | 605 | [5 empty] | Phase 2 | 3023 | Ely
6 | 11B | Tonopah | 1992 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | 2014 LITEREADER 1230F-4 SIGN BOARD,2007 SCORPION TL-3TRUCK MNTD. ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 4 | 537 | Tonopah
8 | 13 | Las Vegas | 2007 | WESTERN ST | 4900FA | DUMP TRUCK W/SIDE DUMP BODY | J1939 | Roadwatch Sensor | Parker Iqan | 2020 REBUILD -ATTENUATOR VEH MNT,2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 1 | 3269 | Las Vegas
8 | 12 | Elko | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE 11 FT REVERSABLE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 194 | Elko
8 | 12 | Elko | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE,2001 SANDER 5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 6.5 | 6.5 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 4 | 196 | Elko
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Pilot | 218 | Reno
8 | 13 | Elko | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 231 | Elko
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1988 SANDER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 244 | Reno
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 250 | Reno
8 | 13 | Las Vegas | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 251 | Las Vegas
8 | 13 | Fallon | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK 8 YD SANDER,JENSEN SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 254 | Fallon
OFF ROAD / NA | 42 | Reno | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Pilot | 726 | Reno
OFF ROAD / NA | 42 | Carson City | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 2 | 730 | Carson City
8 | 13 | Reno | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 263 | Reno
8 | 13S | Las Vegas | 2002 | INTL | 2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor |  | SANDER SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 266 | Las Vegas
6 | 15 | Reno | 2001 | INTL | F5000 | AWD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 267 | Reno
8 | 13S | Las Vegas | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 319 | Las Vegas
8 | 12 | Winnemucca | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,1993 SANDER 5 YD 10',ATTENUATOR, V/M | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 4 | 503 | Winnemucca
8 | 12 | Ely | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 510 | Ely
8 | 12 | Reno | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK SANDER,CLEDHILL PLOW MDL 20931 | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 514 | Reno
8 | 12 | Winnemucca | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 516 | Winnemucca
6 | 11B | Elko | 2003 | INTL | 7600 | FLATRACK TRUCK W/CRANE | J1939 |  |  | 2018 ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 6 | 6 | 1 | 5 | 550 | 660 | [5 empty] | Phase 4 | 909 | Elko
8 | 12 | Ely | 2002 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,5 CU YD SANDER W/PRE WET & GUARD,FRONT BROOM ATTACHMENT | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 580 | Ely
8 | 12 | Reno | 2002 | INTL | 5500 | SINGLE AXLE DUMP TRUCK AWD | J1939 | Roadwatch Sensor |  | HENKE PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Pilot | 582 | Reno
8 | 13 | Wells | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 583 | Wells
8 | 13 | Reno | 2003 | MACK | RD6885 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Pilot | 588 | Reno
8 | 13 | Tonopah | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REV PLOW REBUILD,1850 GALLON SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 590 | Tonopah
8 | 13 | Fallon | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE PLOW,8 YRD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 594 | Fallon
8 | 13 | Reno | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' ONE WAY HENKE,FLINK Model #LMC5H15-NVS4E01 | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 600 | Reno
8 | 13 | Reno | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENKE,SANDER FLINK W PREWET | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 612 | Reno
8 | 13S | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor |  | HENKE REVERSIBLE,SANDER,DUMP BED | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 618 | Las Vegas
8 | 13 | Fallon | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' ONE WAY PLOW,8 YRD FLINK SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 629 | Fallon
8 | 13 | Winnemucca | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 8 CU YD,HENKE REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 634 | Winnemucca
8 | 12 | Elko | 2009 | PETERBILT | 367 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | BONNELL SANDER 5 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.5 | 3.5 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 4 | 671 | Elko
8 | 12 | Tonopah | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SCHMIDT 12' PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 677 | Tonopah
8 | 12 | Tonopah | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SWENSON SANDER,11' ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 678 | Tonopah
8 | 12 | Reno | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YRD SANDER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 680 | Reno
8 | 13S | Winnemucca | 2009 | PETERBILT | 367 | TANDEM AXLE HYDRAULICS W/HOOK LIFT | J1939 | Roadwatch Sensor |  | LARSON 5 CU YD,SANDER,REVERSIBLE PLOW,FLATRACK SWAPLOADER,2006 WORKMAN WATER TANK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 685 | Winnemucca
8 | 12 | Tonopah | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1986 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 692 | Tonopah
8 | 12 | Tonopah | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENDERSON SANDER,1986 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 4 | 693 | Tonopah
8 | 12 | Reno | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,HIGHSPEED 11' PLOW,SANDER 5 YD | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 696 | Reno
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 717 | Fallon
8 | 13 | Fallon | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 739 | Fallon
8 | 13S | Las Vegas | 2009 | PETERBILT | 367 | TANDEM AXLE DUMB TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 742 | Las Vegas
8 | 13S | Tonopah | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | SWAPLOADER SANDER,ONE WAY PLOW,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 4 | 743 | Tonopah
8 | 13 | Wells | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 752 | Wells
8 | 12 | Fallon | 1994 | INTL | F2574 | REBUILD SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' RIGHT HAND PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 757 | Fallon
8 | 12 | Fallon | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,TENCO,5 YRD HENDERSON SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 764 | Fallon
6 | 11G | Las Vegas | 1984 | INTL | F2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 1201 | Las Vegas
8 | 12 | Reno | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Pilot | 784 | Reno
8 | 12 | Reno | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,5 YRD FLINK MOD 10 LMC .5H | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 805 | Reno
8 | 12 | Tonopah | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1986 SANDER,1985 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 819 | Tonopah
8 | 12 | Tonopah | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 SANDER,1995 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 823 | Tonopah
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CU YARD | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 827 | Las Vegas
8 | 13 | Reno | 1995 | GMC | ACL64 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE 11' PLOW,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 829 | Reno
6 | 20 | Las Vegas | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1240 | Las Vegas
8 | 12 | Reno | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 CU. YD SANDER,TYNCO REVERSIBLE | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 842 | Reno
6 | 20 | Elko | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 1244 | Elko
6 | 20 | Reno | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Pilot | 1249 | Reno
8 | 12 | Reno | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1996 SANDER,1996 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 903 | Reno
6 | 11B | Ely | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  | LITEREADER ARROW BOARD V/M,2020 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 2 | 1284 | Ely
8 | 13H | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 1302 | Las Vegas
8 | 12 | Tonopah | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK REBUILD | J1939 | Roadwatch Sensor |  | 10FT PLOW REVERSIBLE,MESSAGE BOARD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 910 | Tonopah
6 | 11G | Las Vegas | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 2021 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 1325 | Las Vegas
6 | 11G | Las Vegas | 1990 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 1345 | Las Vegas
8 | 13 | Las Vegas | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2007 HENKE PLOW REVERSIBLE,FLINK SANDER 8 YARD | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 950 | Las Vegas
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 958 | Ely
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 961 | Ely
8 | 12 | Ely | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD,1996 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 967 | Ely
8 | 12 | Elko | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.5 | 3.5 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 4 | 978 | Elko
8 | 12 | Elko | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1995 PLOW,1995 SANDER,2021 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 6.5 | 6.5 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 4 | 1031 | Elko
8 | 12 | Tonopah | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1996 SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 1034 | Tonopah
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SWENSON 1996 SANDER,ONE WAY | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1062 | Las Vegas
8 | 12 | Reno | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,8 Yard Sander | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1063 | Reno
8 | 13 | Carson City | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK SANDER MODEL 15LMC5H | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 1079 | Carson City
8 | 13 | Carson City | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | ATTENUATOR TRUCK MOUNTED,FLINK 8CU YD-15 LMC 5H | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 2 | 1119 | Carson City
8 | 13 | Reno | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 12' ONE WAY,11 FT REVERSIBLE SNOW PLOW,SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1204 | Reno
8 | 12 | Las Vegas | 1989 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 PLOW,SWENSON | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1217 | Las Vegas
6 | 11G | Ely | 1986 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 1986 SANDER | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 2 | 1633 | Ely
6 | 15 | Reno | 2020 | PETERBILT | 567 | 2020 TANDEM AXLE 4X4 SANDER/PLOW TRUCK | J1939 | Roadwatch Sensor |  | 2018 HENKE 40-65-12NV ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1279 | Reno
8 | 13S | Las Vegas | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1363 | Las Vegas
6 | 15 | Ely | 1995 | INTL | D3057 | AWD DUMP TRUCK | J1939 | Roadwatch Sensor |  | STAINLESS 7 YD SANDER,1995 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 1386 | Ely
8 | 12 | Las Vegas | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1969 BOUMAN SANDER,1996 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1419 | Las Vegas
OFF ROAD / NA | 42 | Reno | 1996 | KODIAK | 6060- | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 1773 | Reno
8 | 12 | Wells | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE,1996 SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 1434 | Wells
8 | 12 | Reno | 1992 | FORD | L9000 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | JENSEN 3/38/60 PLOW,5 YRD SANDER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1440 | Reno
8 | 12 | Reno | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YRD HENDERSON CHIEF,2000 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 1483 | Reno
8 | 12 | Reno | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1988 SANDER,1988 REV PLOW,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1484 | Reno
8 | 12 | Winnemucca | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SNOW PLOW,ATTENUATOR, V/M,2000 SNOW PLOW | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 4 | 1489 | Winnemucca
8 | 12 | Reno | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1512 | Reno
6 | 15 | Carson City | 1989 | INTL | 5070 | AWD DUMP TRUCK | J1939 | Roadwatch Sensor |  | 11' REVERSIBLE PLOW,MONROE A39-52-10 ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 1521 | Carson City
8 | 12 | Reno | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | MODEL #12-99 TENCO,1999 SANDER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 1565 | Reno
8 | 12 | Elko | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 1622 | Elko
6 | 11G | Las Vegas | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 2001 ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 1914 | Las Vegas
8 | 13 | Fallon | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YRD FLINK,REVERSIBLE JENSEN MDL 34058 | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 1650 | Fallon
8 | 12 | Carson City | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | HENDERSEN 5 CU YD SANDER,11' SNOW PLOW, REVERSIBLE, LAWTON EQUIPM | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 1670 | Carson City
8 | 13 | Reno | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,BRINE DISTRIBUTOR | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 1671 | Reno
6 | 11G | Las Vegas | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 1928 | Las Vegas
8 | 13 | Fallon | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YRD FLINK SANDER,12' PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 1684 | Fallon
8 | 13 | Wells | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YD SANDER,SPRATRONICS DE ICER,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 1691 | Wells
8 | 13 | Elko | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 1702 | Elko
8 | 13 | Fallon | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE JENSEN PLOW,8 YRD FLIMK SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 1722 | Fallon
6 | 11B | Elko | 2019 | WESTERN ST | 4900SF | 2019 WESTERN STAR FLAT RACK | J1939 |  |  | 2021 SCORPION ATTENUATOR,2021 LITEREADER ARROWBOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 6 | 6 | 1 | 5 | 550 | 660 | [5 empty] | Phase 4 | 2056 | Elko
OFF ROAD / NA | 42 | Reno | 1999 | KODIAK | CR65 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 2545 | Reno
OFF ROAD / NA | 42 | Elko | 1997 | KODIAK | CR400 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 4.25 | 4.25 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 4 | 2700 | Elko
6 | 11B | Elko | 1998 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | ARROW SIGNBOARD, T/M,SCORPION ATTENUATOR TRK MNT | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | POC | 6 | 6 | 1 | 5 | 550 | 660 | [5 empty] | Phase 4 | 2741 | Elko
8 | 12 | Las Vegas | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 2257 | Las Vegas
8 | 12 | Reno | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SKID MOUNTED STAINLESS WATER TANK 1200,SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 2262 | Reno
8 | 12 | Fallon | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 2263 | Fallon
8 | 12 | Carson City | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2268 | Carson City
8 | 13 | Wells | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW REVERSIBLE,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 2269 | Wells
8 | 13 | Elko | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 SANDER HOPPER-TYPE 8 CU YD,PLOW REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 2271 | Elko
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 8 CUBIC YARDS,PLOW ALASKAN EXPRESSWAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2284 | Ely
8 | 12 | Reno | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER 5 CUBIC YARDS,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 2286 | Reno
8 | 12 | Winnemucca | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW REVERSIBLE,5 CUBIC YARD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 2289 | Winnemucca
8 | 13 | Ely | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW ONE WAY,SANDER 8 CUBIC YARDS | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2290 | Ely
OFF ROAD / NA | 42 | Reno | 1998 | KODIAK | CR65 | ROTARY SNOW BLOWER | None- wired direct |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | x | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 4.25 | 0 | 1 | 3.25 | 357.5 | 467.5 | [5 empty] | Phase 1 | 2826 | Reno
6 | 11B | Winnemucca | 2001 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 4 | 2993 | Winnemucca
8 | 12 | Las Vegas | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 1989 SANDER,HENKE 11' REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 2675 | Las Vegas
8 | 12 | Reno | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE PLOW,5 YRD | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 2676 | Reno
8 | 12 | Las Vegas | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,1997 SANDER | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 2677 | Las Vegas
8 | 12 | Elko | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,5 YD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 2764 | Elko
8 | 12 | Elko | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2000 FLINK SANDER,11 REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 5.5 | 5.5 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 2765 | Elko
8 | 12 | Elko | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,PLOW,SANDER 5 CU YD,2020 SCORPION VEH MNT ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 6.5 | 6.5 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 4 | 2766 | Elko
8 | 12 | Ely | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2767 | Ely
8 | 12 | Wells | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD Flink,11 FT. REVERSIBLE SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 2768 | Wells
8 | 12 | Reno | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSIBLE JENSEN PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 2769 | Reno
8 | 12 | Wells | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | FLINK LCM 10NV-59 SANDER,PLOW,ATTENUATOR, TM,ARROW SIGNBOARD, T/M | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 3 | 2770 | Wells
8 | 12 | Wells | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 6.5 | 0 | 1 | 5.5 | 605 | 715 | [5 empty] | Phase 3 | 2771 | Wells
8 | 12 | Ely | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 CU YD SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2772 | Ely
8 | 13 | Wells | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | PLOW,8 YD FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 3 | 2775 | Wells
8 | 13 | Carson City | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 2011 HENKE ONE-WAY 10 SNOW PLOW,FLINK/MDL 15 LM C5H 8 CU YRD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2777 | Carson City
8 | 13 | Carson City | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD SANDER,PLOW,11FT JENSEN REVERSIBLE SNOW PLOW,8 YRD,SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 2780 | Carson City
6 | 15 | Las Vegas | 1999 | INTL | F5000 | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 2788 | Las Vegas
6 | 15 | Reno | 1999 | INTL | F5000 | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 1 | 2789 | Reno
8 | 12 | Tonopah | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 5 YD FLINK,HENKE 4530 | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 3015 | Tonopah
8 | 12 | Ely | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | SANDER,PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 3017 | Ely
6 | 15 | Carson City | 2001 | INTL | 5600I | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  | HENKE SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 2 | 3038 | Carson City
8 | 13H | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | x | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 6 | 0 | 1 | 5 | 550 | 660 | [5 empty] | Phase 1 | 3128 | Las Vegas
8 | 13 | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | REVERSABLE PLOW,SANDER,WATERTANK | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 3126 | Las Vegas
8 | 13S | Las Vegas | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 1 | 3129 | Las Vegas
6 | 20 | Las Vegas | 2004 | VECTOR | 58055VD | T/M CULVERT CLEANER | J1939 |  |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 3188 | Las Vegas
8 | 13S | Reno | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | SPRAYTRONIC DE-ICER,PLOW REVERSIBLE,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 3319 | Reno
8 | 13S | Reno | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | PLOW REVERSIBLE,2003 SANDERS,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,WATER TANK, SWAPLOADER,PLOW | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Pilot | 3320 | Reno
8 | 13S | Tonopah | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  | HENKE ONEWAY PLOW,SANDER SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 5.5 | 0 | 1 | 4.5 | 495 | 605 | [5 empty] | Phase 4 | 3327 | Tonopah
8 | 25 | Las Vegas | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 39 | Las Vegas
8 | 25 | Elko | 1976 | PETERBILT | MD359 | TRACTOR TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 102 | Elko
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 390 | Fallon
8 | 25 | Reno | 2006 | INTL | 5900I | 2006 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Pilot | 393 | Reno
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 395 | Fallon
8 | 25 | Las Vegas | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 396 | Las Vegas
8 | 25 | Tonopah | 2002 | INTL | F2574 | TANDEM AXLE WATER TRUCK REBUILD | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 617 | Tonopah
8 | 25 | Reno | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Pilot | 690 | Reno
8 | 25 | Las Vegas | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 695 | Las Vegas
8 | 25 | Ely | 1983 | AUTOCAR | KM64F | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 797 | Ely
8 | 25 | Tonopah | 1980 | MACK | RS685 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1142 | Tonopah
8 | 25 | Reno | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Pilot | 1442 | Reno
8 | 25 | Wells | 1989 | MACK | RD688 | 3500 GALLON WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1562 | Wells
8 | 25 | Winnemucca | 1990 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1563 | Winnemucca
8 | 25 | Wells | 1991 | INTL | F2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1682 | Wells
8 | 25 | Las Vegas | 2018 | MACK | GR64F | 2018 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1704 | Las Vegas
8 | 25 | Tonopah | 2018 | MACK | GR64F | 2018 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1707 | Tonopah
8 | 25 | Las Vegas | 2019 | INTL | HX620 | 2019 INT'L HX 620 WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1708 | Las Vegas
8 | 25 | Las Vegas | 1987 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2103 | Las Vegas
8 | 25 | Elko | 1991 | INTL | 2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2291 | Elko
8 | 25 | Ely | 1991 | INTL | F2574 | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2293 | Ely
8 | 25 | Ely | 1990 | INTL | 2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2314 | Ely
8 | 25 | Winnemucca | 1991 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2319 | Winnemucca
8 | 25 | Elko | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2359 | Elko
8 | 25 | Tonopah | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2360 | Tonopah
8 | 25 | Reno | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2374 | Reno
8 | 25 | Las Vegas | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2385 | Las Vegas
8 | 25 | Ely | 1997 | INTL | 2574 | 1997 REBUILT TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  | PLOW,8 YRD SANDER CHIEF | Telematics Device | Plow Up Down Sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.5 | 0 | 1 | 2.5 | 275 | 385 | [5 empty] | Phase 2 | 2679 | Ely
8 | 25 | Las Vegas | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3189 | Las Vegas
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 3203 | Fallon
8 | 25 | Reno | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3204 | Reno
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 3206 | Fallon
8 | 25 | Fallon | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 3235 | Fallon
8 | 25 | Reno | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 2 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3236 | Reno
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 20 | Tonopah
5 | 6 | Tonopah | 2016 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 |  | POC Hrs | 327.25 |  |  | Phase 4 | 22 | Tonopah
8 | 13 | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | EPOKE | SANDER 8 YARD,PLOW ONE WAY,EPOKE SANDER,2021 HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 |  | 4.75 | 0 | 0 | 4.75 | 412.5 | 522.5 |  | Our cost runs $140/hr |  |  |  | Phase 1 | 38 | Las Vegas
2 | 01A | Ely | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 84 | Ely
3 | 5 | Ely | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 137 | Ely
3 | 5 | Carson City | 2007 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 139 | Carson City
3 | 5 | Ely | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 142 | Ely
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 143 | Elko
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 154 | Elko
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 155 | Carson City
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 1 | 311 | Las Vegas
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 1 | 317 | Las Vegas
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 1 | 322 | Las Vegas
5 | 11A | Ely | 2001 | FREIGHTLNR | 25K GVW | AERIAL LIFT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 164 | Ely
8 | 13S | Las Vegas | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward only | x | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 1 | 328 | Las Vegas
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 186 | Carson City
5 | 11F | Carson City | 2001 | FORD | F-350 | 4X4 SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 188 | Carson City
5 | 11J | Carson City | 2001 | FORD | F-350 | 4X4 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 192 | Carson City
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 193 | Reno
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 200 | Reno
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 209 | Carson City
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 214 | Carson City
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 216 | Reno
8 | 13 | Fallon | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | 2014 VARITECH 403 V | Telematics device for Winter Operations |  | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 |  | 4.75 | 0 | 0 | 4.75 | 412.5 | 522.5 | [5 empty] | Phase 3 | 962 | Fallon
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 221 | Carson City
3 | 4 | Carson City | 2018 | CHEVROLET | EXPRESS | 2018 CHEV EXP 1T 15 PASS VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 227 | Carson City
6 | 28 | Tonopah | 2001 | INTL | 2574 | 2001 REBUILD INTL F2574 DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 229 | Tonopah
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 230 | Carson City
5 | 11H | Carson City | 2007 | FREIGHTLNR | FLD120 | FLATRACK TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 232 | Carson City
5 | 11A | Tonopah | 2006 | GMC | SIERRA | SIGNSHOP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 237 | Tonopah
5 | 11A | Reno | 2008 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 239 | Reno
2 | 1 | Reno | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 240 | Reno
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 245 | Carson City
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 257 | Carson City
2 | 1 | Elko | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 258 | Elko
3 | 4 | Carson City | 2018 | CHEVROLET | EXPRESS | 2018 3/4 TON VAN 12 PASSENGER | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 259 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 261 | Las Vegas
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 264 | Carson City
2 | 1 | Las Vegas | 1998 | FORD | ESCORT | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 269 | Las Vegas
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 273 | Carson City
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 274 | Elko
2 | 01A | Carson City | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 276 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 2018 1/2 TON CHEVY SILVERADO 1500 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 277 | Las Vegas
2 | 01A | Carson City | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 278 | Carson City
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 286 | Winnemucca
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 287 | Las Vegas
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 CHEVY 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 289 | Las Vegas
5 | 11F | Ely | 2007 | FORD | F-350 | SERVICE TRUCK 4X4 | OBDII |  |  | 2018 REAR BUMPER CRANE | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 292 | Ely
2 | 01A | Tonopah | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 293 | Tonopah
3 | 5 | Tonopah | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 295 | Tonopah
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 300 | Las Vegas
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 305 | Carson City
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 310 | Tonopah
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 314 | Carson City
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 318 | Winnemucca
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 320 | Winnemucca
8 | 13 | Ely | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | JENSEN REVERSIBLE,8 CU YD | Telematics device for Winter Operations |  | Yes | Yes - Forward only | x | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | POC | 4.75 | 4.75 | 0 | 4.75 | 412.5 | 522.5 | [5 empty] | Phase 2 | 2210 | Ely
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 325 | Las Vegas
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 329 | Carson City
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 330 | Carson City
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 332 | Tonopah
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 335 | Elko
3 | 5 | Elko | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 336 | Elko
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 341 | Las Vegas
3 | 5 | Carson City | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 345 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 347 | Las Vegas
5 | 11J | Carson City | 2016 | FORD | F-550 | UTILITY TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 348 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 350 | Las Vegas
3 | 5 | Ely | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 352 | Ely
9 | 14 | Reno | 1993 | KENW | T800 | KENWORTH T800 REBUILD | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 375 | Reno
5 | 76 | Carson City | 2001 | FORD | E-350 | 1 TON VAN W/FALLING WEIGHT DEFLECT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 377 | Carson City
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 383 | Las Vegas
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 385 | Tonopah
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 386 | Las Vegas
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 387 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 389 | Reno
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 391 | Las Vegas
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 399 | Las Vegas
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 400 | Las Vegas
2 | 1 | Las Vegas | 2002 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 401 | Las Vegas
2 | 01A | Elko | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 404 | Elko
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 406 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 407 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 408 | Reno
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 415 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 417 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 423 | Las Vegas
3 | 4 | Reno | 1999 | GMC | TG3140 | 1 TON CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 425 | Reno
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 426 | Las Vegas
3 | 5 | Winnemucca | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 429 | Winnemucca
3 | 4 | Reno | 1999 | CHEVROLET | CG21406 | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 437 | Reno
6 | 77 | Tonopah | 1988 | MACK | MR688 | MACK STRIPER REBUILD | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 438 | Tonopah
5 | 6 | Ely | 2008 | FORD | F-350 | ONE TON PICKUP TRUCK W/4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 439 | Ely
3 | 4 | Elko | 2002 | GMC | SAVANA | PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 442 | Elko
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 443 | Reno
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 444 | Carson City
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 450 | Reno
8 | 13H | Las Vegas | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR TANDEM AXLE SIDE DUMP | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 458 | Las Vegas
3 | 5 | Reno | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 464 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 466 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 474 | Reno
3 | 5 | Carson City | 2002 | GMC | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 475 | Carson City
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 480 | Reno
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 481 | Elko
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 482 | Reno
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 485 | Elko
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 486 | Elko
OFF ROAD / NA | 55B | Winnemucca | 2006 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 493 | Winnemucca
3 | 5 | Elko | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 500 | Elko
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 502 | Reno
5 | 11H | Reno | 2008 | FORD | F-650 | FLATRACK TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 507 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 519 | Reno
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 532 | Carson City
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 533 | Carson City
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 534 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 535 | Las Vegas
5 | 11H | Reno | 1992 | INTL | 4700 | FLATRACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 538 | Reno
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 539 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 540 | Las Vegas
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 541 | Carson City
3 | 5 | Carson City | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 543 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 548 | Las Vegas
2 | 1 | Reno | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 550 | Reno
2 | 1 | Carson City | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 553 | Carson City
5 | 11F | Reno | 2016 | FORD | F-350 | SHOP SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 556 | Reno
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 557 | Las Vegas
3 | 5 | Elko | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 561 | Elko
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 562 | Tonopah
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 564 | Tonopah
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 568 | Tonopah
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 571 | Reno
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 577 | Las Vegas
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 581 | Tonopah
5 | 11E | Las Vegas | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 29 | Las Vegas
5 | 11H | Reno | 1992 | GMC | TC7H0 | FLATRACK TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 589 | Reno
3 | 3 | Elko | 2006 | FORD | F-250 | 3/4 TON PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 68 | Elko
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 592 | Las Vegas
3 | 3 | Ely | 2017 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 88 | Ely
3 | 5 | Elko | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 596 | Elko
3 | 3 | Wells | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 91 | Wells
3 | 3 | Ely | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 94 | Ely
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 101 | Las Vegas
5 | 11H | Reno | 1992 | INTL | 4700 | FLATRACK TRUCK | J1939 |  |  | 2021 LITEREADER ARROW BOARD | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 601 | Reno
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 603 | Las Vegas
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 604 | Carson City
3 | 5 | Las Vegas | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 606 | Las Vegas
3 | 3 | Ely | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 111 | Ely
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 608 | Las Vegas
6 | 77 | Las Vegas | 2006 | PETERBILT | 320 | LINE STRIPER TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 609 | Las Vegas
2 | 01A | Carson City | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 610 | Carson City
3 | 3 | Elko | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 113 | Elko
3 | 3 | Wells | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 114 | Wells
3 | 3 | Reno | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 115 | Reno
3 | 3 | Wells | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 121 | Wells
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 620 | Las Vegas
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 621 | Las Vegas
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 122 | Las Vegas
3 | 3 | Elko | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 141 | Elko
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 146 | Las Vegas
5 | 11E | Wells | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 156 | Wells
5 | 11H | Las Vegas | 2001 | FORD | F-450 | REBUILD FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 157 | Las Vegas
5 | 11H | Winnemucca | 2001 | FORD | F-450 | FLAT RACK TRUCK | OBDII | Roadwatch Sensor |  | DEICING UNIT,325 GALLON DE-ICING UNIT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 160 | Winnemucca
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 632 | Las Vegas
5 | 11E | Elko | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 162 | Elko
5 | 11H | Las Vegas | 2001 | FORD | F-450 | FLAT RACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 163 | Las Vegas
5 | 11E | Wells | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 166 | Wells
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 637 | Reno
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 174 | Carson City
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 641 | Carson City
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 642 | Reno
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 644 | Reno
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 645 | Reno
3 | 3 | Fallon | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 189 | Fallon
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 648 | Reno
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 198 | Reno
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 205 | Reno
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 656 | Carson City
3 | 5 | Reno | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 659 | Reno
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 660 | Elko
5 | 11E | Winnemucca | 2008 | FORD | F-250 | DUMP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 664 | Winnemucca
3 | 5 | Winnemucca | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 665 | Winnemucca
5 | 11F | Reno | 2009 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DSL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 668 | Reno
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 217 | Reno
3 | 5 | Elko | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 672 | Elko
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 219 | Carson City
5 | 11J | Reno | 2007 | FORD | F-450 | 4X4 UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 224 | Reno
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 228 | Las Vegas
5 | 11F | Ely | 1994 | GMC | TC310 | AWD 1 TON TRUCK W/ WELDING BODY | OBDII |  |  | 2019 TRAILBLAZER 302 WELDER | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 689 | Ely
5 | 11E | Carson City | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 238 | Carson City
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 242 | Reno
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 694 | Carson City
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 698 | Las Vegas
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 699 | Las Vegas
3 | 5 | Elko | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 705 | Elko
3 | 5 | Reno | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 708 | Reno
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 711 | Las Vegas
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 714 | Carson City
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 716 | Las Vegas
2 | 1 | Las Vegas | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 736 | Las Vegas
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  | PROGRAMMABLE MESSAGE SIGN,2014 LITE READER 1030F-4 | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 255 | Reno
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 740 | Reno
3 | 3 | Elko | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 260 | Elko
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 748 | Reno
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 753 | Reno
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 755 | Reno
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 268 | Las Vegas
5 | 11E | Reno | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  | TRAILER OFFICE 60' X 24',2014 SNOW DOGG SNOW PLOW KIT EX-80,2014 SALT DOGG MODEL SHIP 2000X | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 280 | Reno
5 | 11E | Las Vegas | 2007 | FORD | F-450 | 1 TON DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 281 | Las Vegas
3 | 5 | Reno | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 769 | Reno
3 | 4 | Las Vegas | 2017 | CHEVROLET | EXPRESS | 15 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 771 | Las Vegas
6 | 77 | Reno | 2002 | EZ LINER | 320 | FREEWAY LINE STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 772 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 773 | Reno
3 | 4 | Carson City | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 774 | Carson City
5 | 11E | Carson City | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 285 | Carson City
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 778 | Las Vegas
5 | 11E | Las Vegas | 2007 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 288 | Las Vegas
9 | 14 | Ely | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 783 | Ely
3 | 3 | Reno | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 298 | Reno
9 | 14 | Fallon | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 785 | Fallon
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 786 | Carson City
2 | 01A | Ely | 2017 | FORD | EXPLORER | 4X4 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 790 | Ely
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 299 | Las Vegas
9 | 14 | Wells | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 793 | Wells
3 | 3 | Reno | 1987 | CHEVROLET | CR209 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 315 | Reno
9 | 14 | Ely | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 796 | Ely
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 800 | Las Vegas
2 | 1 | Reno | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 802 | Reno
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 321 | Las Vegas
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 809 | Carson City
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2014 PROFILING SYSTEM | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 324 | Carson City
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 811 | Reno
5 | 11J | Carson City | 2016 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 346 | Carson City
3 | 5 | Elko | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 814 | Elko
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 816 | Reno
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 817 | Reno
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 349 | Las Vegas
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 821 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 822 | Reno
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 392 | Las Vegas
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 826 | Reno
5 | 11E | Las Vegas | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 402 | Las Vegas
3 | 3 | Las Vegas | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 403 | Las Vegas
5 | 11E | Tonopah | 2016 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 405 | Tonopah
3 | 4 | Carson City | 2003 | GMC | SAVANA | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 830 | Carson City
3 | 4 | Carson City | 2003 | GMC | SAVANA | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 831 | Carson City
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 832 | Carson City
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 412 | Carson City
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 835 | Reno
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 838 | Carson City
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 840 | Carson City
3 | 3 | Carson City | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 421 | Carson City
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 843 | Carson City
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 846 | Reno
3 | 3 | Carson City | 1998 | CHEVROLET | CC209 | 3/4 TON PICKUP TRUCK W/SVC BODY | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 422 | Carson City
3 | 5 | Carson City | 2003 | GMC | SIERRA | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 854 | Carson City
3 | 3 | Reno | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 431 | Reno
3 | 3 | Winnemucca | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 436 | Winnemucca
5 | 11E | Reno | 2016 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 451 | Reno
3 | 5 | Carson City | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 869 | Carson City
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 870 | Reno
5 | 11E | Elko | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 489 | Elko
5 | 11H | Ely | 2008 | FORD | F-450 | 1 TON FLATRACH TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 497 | Ely
3 | 5 | Tonopah | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 878 | Tonopah
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 504 | Reno
5 | 11J | Las Vegas | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 505 | Las Vegas
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 892 | Reno
8 | 12 | Reno | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 2.75 | 0 | 1 | 1.75 | 192.5 | 302.5 | [5 empty] | Pilot | 512 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 898 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 899 | Reno
5 | 11S | Las Vegas | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | 400 GAL SPRAY TANK/SLIDE-IN | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 531 | Las Vegas
5 | 11H | Las Vegas | 1996 | INTL | 4700 | FLAT RACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 905 | Las Vegas
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 906 | Reno
5 | 11H | Las Vegas | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 542 | Las Vegas
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 913 | Reno
5 | 11A | Elko | 2017 | FORD | F-550 | AERIAL TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 914 | Elko
5 | 11S | Las Vegas | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 545 | Las Vegas
5 | 11A | Reno | 2003 | INTL | 7600 | AERIAL LIFT TRUCK BIO-DSL | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 917 | Reno
5 | 11H | Winnemucca | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 547 | Winnemucca
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 923 | Reno
5 | 11E | Fallon | 2002 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 558 | Fallon
5 | 11E | Carson City | 2002 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | SALTDOGG SHPE2000X SANDER,SNOWDOGG EX-85 PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 565 | Carson City
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  | JENSEN-MODEL 43058 | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 927 | Reno
3 | 5 | Reno | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 928 | Reno
5 | 11S | Las Vegas | 2002 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOKLIFT | OBDII | Roadwatch Sensor |  | ARROW BOARD, T/M,DUMPBED SL95 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 567 | Las Vegas
5 | 11E | Reno | 2002 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 569 | Reno
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 570 | Las Vegas
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 940 | Reno
5 | 6 | Reno | 2008 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 945 | Reno
5 | 11H | Tonopah | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 598 | Tonopah
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 599 | Las Vegas
5 | 11E | Tonopah | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 607 | Tonopah
5 | 11E | Reno | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2014 SNOW DOGG SNOW PLOW EX-80,2014 SNOW DOGG SHPE 2000 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 614 | Reno
5 | 11A | Elko | 2020 | DODGE | 5500 | 2020 DODGE RAM 5500 FLATRACK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 973 | Elko
5 | 11E | Tonopah | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 627 | Tonopah
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 631 | Las Vegas
9 | 14 | Reno | 2003 | KENW | W900B | TRACTOR TRUCK | J1939 |  |  | 1995 SANDER | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 987 | Reno
5 | 11H | Carson City | 1991 | INTL | 4700 | SINGLE AXLE FLATRACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 988 | Carson City
5 | 11E | Fallon | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 635 | Fallon
3 | 4 | Carson City | 2017 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 993 | Carson City
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 995 | Carson City
2 | 1 | Tonopah | 2013 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1002 | Tonopah
2 | 01A | Las Vegas | 2013 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1003 | Las Vegas
5 | 11E | Wells | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 639 | Wells
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1008 | Carson City
5 | 11J | Winnemucca | 2020 | RAM | 5500 | 2020 RAM 5500 4X4 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1009 | Winnemucca
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 646 | Las Vegas
5 | 11E | Fallon | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 647 | Fallon
6 | 11B | Carson City | 1986 | INTL | 2574 | REBUILD CRANE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1021 | Carson City
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 650 | Las Vegas
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | HINKER C-PLOW 8802 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 652 | Las Vegas
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | ARROW BOARD, T/M/LITEREADER | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 653 | Las Vegas
5 | 11J | Las Vegas | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 667 | Las Vegas
3 | 5 | Carson City | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1028 | Carson City
5 | 11F | Carson City | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 669 | Carson City
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1038 | Carson City
3 | 5 | Reno | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1044 | Reno
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1048 | Carson City
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1049 | Carson City
5 | 11F | Tonopah | 1991 | GMC | TC31A | SERVICE TRUCK W/FLATBED | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1054 | Tonopah
3 | 5 | Carson City | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1059 | Carson City
3 | 5 | Tonopah | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1064 | Tonopah
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1067 | Las Vegas
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1070 | Las Vegas
6 | 11B | Winnemucca | 1987 | INTL | F2574 | CRANE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1073 | Winnemucca
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1075 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1078 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1083 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1084 | Las Vegas
3 | 5 | Las Vegas | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1086 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1088 | Las Vegas
6 | 77 | Reno | 2003 | MACK | MR688S | LINE STRIPER 700 GALLON | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Pilot | 1089 | Reno
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1090 | Reno
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1091 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1093 | Las Vegas
6 | 77 | Elko | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 1094 | Elko
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1095 | Reno
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1096 | Elko
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1097 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICK UP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1099 | Las Vegas
7 | 83 | Carson City | 2003 | PETERBILT | 357 | UNDERBRIDGE INSPECTION TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Pilot | 1100 | Carson City
2 | 01A | Elko | 2004 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1102 | Elko
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1106 | Elko
6 | 28 | Ely | 1994 | INTL | 2574 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1107 | Ely
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1108 | Elko
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1109 | Las Vegas
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1112 | Elko
2 | 1 | Las Vegas | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1113 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1115 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1117 | Las Vegas
3 | 5 | Elko | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1118 | Elko
2 | 01A | Carson City | 2004 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1122 | Carson City
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1124 | Las Vegas
3 | 5 | Winnemucca | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1125 | Winnemucca
8 | 12 | Ely | 1994 | FORD | F-700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 2.75 | 0 | 1 | 1.75 | 192.5 | 302.5 | [5 empty] | Phase 2 | 741 | Ely
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1127 | Las Vegas
3 | 5 | Reno | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1128 | Reno
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1129 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1131 | Las Vegas
6 | 28 | Las Vegas | 1995 | INTL | 2574 | TRUCK W/ASPHALT PATCHER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1132 | Las Vegas
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1134 | Las Vegas
6 | 11B | Reno | 1999 | INTL | F257A | CRANE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 1135 | Reno
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1139 | Las Vegas
5 | 11D | Las Vegas | 1999 | GMC | TC31403 | COMPACTOR TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1144 | Las Vegas
3 | 4 | Carson City | 2004 | FORD | ECONO | CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1150 | Carson City
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1151 | Las Vegas
3 | 4 | Ely | 2004 | CHEVROLET | EXPRESS | 12 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1152 | Ely
3 | 5 | Las Vegas | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1157 | Las Vegas
3 | 5 | Carson City | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  | 2014 PROFILING SYSTEM PANASONIC TOUGHBOO | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1159 | Carson City
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1161 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1164 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1165 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1166 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1169 | Elko
2 | 01A | Carson City | 2017 | FORD | EXPLORER | 4X4 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1170 | Carson City
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1171 | Elko
3 | 5 | Reno | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK AFV | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1172 | Reno
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1173 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1174 | Elko
3 | 5 | Las Vegas | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1178 | Las Vegas
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1179 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1180 | Elko
3 | 5 | Las Vegas | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1182 | Las Vegas
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1183 | Elko
3 | 5 | Elko | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1185 | Elko
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1186 | Reno
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1187 | Reno
3 | 5 | Reno | 2004 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1188 | Reno
3 | 5 | Ely | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1191 | Ely
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1193 | Reno
3 | 5 | Ely | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1194 | Ely
3 | 5 | Winnemucca | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1198 | Winnemucca
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1200 | Reno
3 | 3 | Reno | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 792 | Reno
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1206 | Reno
5 | 11J | Las Vegas | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1212 | Las Vegas
5 | 11F | Elko | 1989 | INTL | 2574 | SERVICE TRUCK W/CRANE | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1213 | Elko
3 | 5 | Elko | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1215 | Elko
5 | 6 | Reno | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1216 | Reno
3 | 3 | Reno | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 807 | Reno
5 | 10 | Reno | 2013 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1218 | Reno
6 | 20 | Elko | 1998 | INTL | 4900 | 1998 CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1219 | Elko
3 | 3 | Reno | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 810 | Reno
3 | 5 | Reno | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1223 | Reno
3 | 5 | Wells | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1224 | Wells
3 | 3 | Fallon | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 813 | Fallon
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 828 | Carson City
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 4X2 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 834 | Las Vegas
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 850 | Las Vegas
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 860 | Elko
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 862 | Elko
3 | 5 | Reno | 2013 | FORD | F-150 | 2013 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1248 | Reno
3 | 5 | Reno | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1250 | Reno
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 866 | Elko
3 | 5 | Reno | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1252 | Reno
3 | 3 | Winnemucca | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 872 | Winnemucca
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 895 | Elko
3 | 3 | Elko | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 896 | Elko
5 | 11A | Winnemucca | 2005 | INTL | 7400 | AERIAL TRUCK W/PLATFORM | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1267 | Winnemucca
9 | 14 | Reno | 1991 | GMC | WG42 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1268 | Reno
6 | 11B | Ely | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1269 | Ely
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1270 | Carson City
6 | 11B | Reno | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 1274 | Reno
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1275 | Las Vegas
5 | 11F | Reno | 2003 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 902 | Reno
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1287 | Las Vegas
5 | 11H | Reno | 2003 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 915 | Reno
5 | 11E | Winnemucca | 2017 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 921 | Winnemucca
5 | 11F | Ely | 2017 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2018 WESTERN MULE REAR BUMPER CRANE | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 925 | Ely
6 | 11B | Fallon | 1988 | INTL | 2574 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1324 | Fallon
5 | 11H | Ely | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 926 | Ely
5 | 11J | Reno | 2003 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 931 | Reno
5 | 11J | Reno | 2003 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 933 | Reno
5 | 11J | Las Vegas | 2003 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 936 | Las Vegas
5 | 11J | Elko | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 939 | Elko
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 941 | Reno
5 | 11J | Ely | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 942 | Ely
5 | 11F | Winnemucca | 2004 | FORD | F-450 | UTILITY TRUCK W/CRANE 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 943 | Winnemucca
3 | 3 | Carson City | 2009 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 946 | Carson City
8 | 13H | Las Vegas | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXEL DUMP TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1350 | Las Vegas
7 | 83 | Carson City | 2009 | PETERBILT | 367 | UNDER BRIDGE TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Pilot | 1353 | Carson City
5 | 11F | Reno | 1996 | GMC | SIERRA | SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1359 | Reno
3 | 3 | Carson City | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 968 | Carson City
3 | 3 | Fallon | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 969 | Fallon
OFF ROAD / NA | 55B | Elko | 2009 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1374 | Elko
3 | 3 | Fallon | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 989 | Fallon
3 | 3 | Carson City | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 992 | Carson City
3 | 3 | Tonopah | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1006 | Tonopah
9 | 14 | Reno | 2004 | PETERBILT | 378 | TRUCK TRACTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 1388 | Reno
3 | 3 | Las Vegas | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1011 | Las Vegas
3 | 3 | Las Vegas | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1012 | Las Vegas
5 | 11F | Las Vegas | 1999 | DODGE | 3500 | 1 TON SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1397 | Las Vegas
3 | 3 | Las Vegas | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1023 | Las Vegas
3 | 3 | Reno | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1025 | Reno
3 | 3 | Reno | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1026 | Reno
3 | 3 | Reno | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1027 | Reno
3 | 3 | Fallon | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1029 | Fallon
5 | 11F | Las Vegas | 1999 | DODGE | 3500 | SERVICE TRUCK W/CRANE | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1409 | Las Vegas
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1033 | Elko
5 | 11J | Reno | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1413 | Reno
5 | 11J | Reno | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1414 | Reno
5 | 11J | Reno | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1417 | Reno
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1036 | Elko
3 | 3 | Ely | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1037 | Ely
5 | 11F | Elko | 2018 | DODGE | RAM 5500 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1425 | Elko
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 FORD F150 1/2 TON EXT CAB S/B | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1426 | Las Vegas
3 | 3 | Winnemucca | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1039 | Winnemucca
3 | 3 | Carson City | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1043 | Carson City
3 | 3 | Carson City | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1053 | Carson City
9 | 14 | Ely | 1991 | INTL | 9300 | REBUILD TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1430 | Ely
3 | 3 | Elko | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1061 | Elko
3 | 3 | Winnemucca | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1104 | Winnemucca
3 | 3 | Winnemucca | 2018 | FORD | F-250 | 2018 FORD F-250 LB EXT CAB 4X4 FFUEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1105 | Winnemucca
3 | 3 | Winnemucca | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1120 | Winnemucca
5 | 11F | Winnemucca | 1999 | GMC | TK310 | AWD SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1450 | Winnemucca
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1126 | Carson City
5 | 11E | Las Vegas | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1147 | Las Vegas
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1155 | Carson City
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON VHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1158 | Carson City
3 | 3 | Carson City | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1162 | Carson City
5 | 11H | Las Vegas | 2017 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1184 | Las Vegas
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1470 | Las Vegas
5 | 11E | Las Vegas | 1999 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1196 | Las Vegas
3 | 3 | Reno | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1197 | Reno
5 | 11A | Reno | 2011 | PETERBILT | 367 | PETERBILT 6X6 AERIAL LIFT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1482 | Reno
5 | 11E | Las Vegas | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | OBDII | Roadwatch Sensor |  | SANDER | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1203 | Las Vegas
3 | 3 | Reno | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVRADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1205 | Reno
3 | 5 | Carson City | 1998 | GMC | TK109 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1500 | Carson City
2 | 01A | Las Vegas | 2018 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1505 | Las Vegas
2 | 01A | Carson City | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1508 | Carson City
2 | 01A | Reno | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1511 | Reno
5 | 11E | Reno | 2017 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1207 | Reno
2 | 01A | Elko | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 3.5L V6 4WD | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1516 | Elko
5 | 11H | Elko | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1214 | Elko
2 | 01A | Elko | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 3.25 | 3.25 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1527 | Elko
5 | 11E | Wells | 2013 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1222 | Wells
3 | 5 | Las Vegas | 2012 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1533 | Las Vegas
2 | 01A | Carson City | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1534 | Carson City
2 | 01A | Reno | 2019 | JEEP | CHEROKEE | 2019 JEEP CHEROKEE SUV 4X4 UNLEAD | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1537 | Reno
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1545 | Las Vegas
2 | 01A | Carson City | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1549 | Carson City
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2019 JEEP GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1550 | Carson City
2 | 01A | Reno | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1553 | Reno
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1555 | Las Vegas
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2018 JEEP GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1558 | Carson City
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1560 | Carson City
5 | 11H | Wells | 2013 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1227 | Wells
5 | 11E | Reno | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1228 | Reno
5 | 11E | Elko | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1231 | Elko
2 | 01A | Reno | 2018 | JEEP | CHEROKEE | 2019 JEEP LATITUDE CHEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1583 | Reno
2 | 01A | Reno | 2018 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1589 | Reno
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1591 | Las Vegas
6 | 28 | Elko | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1593 | Elko
2 | 01A | Carson City | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1595 | Carson City
5 | 11E | Reno | 2017 | FORD | F-450 | 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | CULVERT INSPECTION CAMERA,2018 SNOWDOGG EX80II SNOW PLOW,2018 SALTDOGG SANDER SHPE2000 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1234 | Reno
6 | 28 | Wells | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1613 | Wells
5 | 11H | Elko | 2013 | FORD | F-450 | FLATRACK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1235 | Elko
5 | 11J | Elko | 2013 | FORD | F-450 | UTILITY TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1236 | Elko
5 | 11H | Winnemucca | 2013 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2021 ASPHALT HOTBOX | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1239 | Winnemucca
5 | 11E | Ely | 2013 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1241 | Ely
3 | 3 | Winnemucca | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1242 | Winnemucca
6 | 77 | Ely | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1639 | Ely
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1640 | Las Vegas
3 | 3 | Fallon | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1243 | Fallon
2 | 01A | Reno | 2018 | FORD | EXPEDITION | 2018 FORD EXPEDITION SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1643 | Reno
6 | 28 | Ely | 1996 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1649 | Ely
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1246 | Carson City
3 | 3 | Carson City | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1251 | Carson City
3 | 5 | Carson City | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1653 | Carson City
3 | 5 | Las Vegas | 2018 | CHEVROLET | SILVERADO | 18 CHEVY SILVERADO 1/2 T CREW CAB 4X2 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1656 | Las Vegas
3 | 5 | Las Vegas | 2018 | CHEVROLET | 2500 | 2018 CHEVY SILVERADO 1/2T CREW CAB SB V8 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1658 | Las Vegas
5 | 10 | Reno | 2005 | FORD | F-450 | SURVEY UNIT | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1253 | Reno
3 | 5 | Las Vegas | 2018 | CHEVROLET | 2500 | 2018 CHEV SILVERADO 1/2T CREW CAB SB V8 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1664 | Las Vegas
5 | 11A | Las Vegas | 2017 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1665 | Las Vegas
6 | 28 | Wells | 1996 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1668 | Wells
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1669 | Las Vegas
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1255 | Carson City
3 | 3 | Reno | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1257 | Reno
5 | 11J | Reno | 2019 | FORD | F-350 | 2019 FORD F-350 4X4 UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1673 | Reno
5 | 11E | Las Vegas | 2017 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1261 | Las Vegas
5 | 11F | Las Vegas | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1263 | Las Vegas
3 | 5 | Las Vegas | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1678 | Las Vegas
3 | 5 | Las Vegas | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1679 | Las Vegas
3 | 5 | Reno | 2018 | FORD | 150 | 2018 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1680 | Reno
5 | 11H | Las Vegas | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | MESSAGE SIGN, VEHICLE MOUNTED | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1265 | Las Vegas
2 | 01A | Tonopah | 2018 | FORD | EXPLORER | 2018 FORD EXPL SUV 1/2T 5.3 4WD 6 PASS | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 1686 | Tonopah
9 | 14 | Reno | 2020 | KENWORTH | W900L | 2020 KENWORTH W900L TRANSPORT TRACTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 1688 | Reno
3 | 3 | Carson City | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1281 | Carson City
5 | 11D | Las Vegas | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1304 | Las Vegas
5 | 11S | Las Vegas | 2005 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | SWAPLOADER DUMP BODY,SWAPLOADER FLATRACK | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1312 | Las Vegas
6 | 28 | Winnemucca | 1986 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1692 | Winnemucca
3 | 5 | Las Vegas | 2018 | CHEVROLET | 1500 | 2018 1/2 TON PICK UPS | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1693 | Las Vegas
3 | 5 | Reno | 2018 | FORD | F-150 | 2018 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1694 | Reno
5 | 11F | Tonopah | 2005 | FORD | F-450 | SERVICE TRUCK W/CRANE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1316 | Tonopah
5 | 11F | Elko | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1322 | Elko
2 | 01A | Las Vegas | 2005 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1700 | Las Vegas
2 | 01A | Las Vegas | 2005 | GMC | ENVOY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1701 | Las Vegas
5 | 11H | Las Vegas | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  | 2015 ARROW BOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1340 | Las Vegas
3 | 4 | Winnemucca | 2019 | CHEVROLET | EXPRESS | PASSANGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 1711 | Winnemucca
2 | 1 | Las Vegas | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1712 | Las Vegas
5 | 11F | Reno | 1992 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1367 | Reno
8 | 12 | Winnemucca | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 4 | 1370 | Winnemucca
2 | 1 | Carson City | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1724 | Carson City
6 | 28 | Winnemucca | 1993 | INTL | 2574 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1730 | Winnemucca
2 | 01A | Carson City | 2018 | JEEP | CHEROKEE | 2018 GRAND CHAEROKEE SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1737 | Carson City
2 | 1 | Carson City | 2019 | CHEVROLET | MALIBU | 2019 CHEV MALIBU 1.5L TURBO | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1741 | Carson City
2 | 01A | Carson City | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1743 | Carson City
8 | 12 | Winnemucca | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 4 | 1375 | Winnemucca
5 | 11J | Carson City | 2006 | FORD | F-350 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1745 | Carson City
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1390 | Las Vegas
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1391 | Las Vegas
9 | 14 | Carson City | 2000 | INTL | 9900 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1751 | Carson City
6 | 20 | Las Vegas | 2000 | INTL | 2674 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1752 | Las Vegas
6 | 15 | Reno | 1995 | INTL | D3057 | AWD SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 1 | 1400 | Reno
9 | 14 | Tonopah | 1994 | INTL | F9200 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1757 | Tonopah
5 | 11J | Las Vegas | 2018 | FORD | F-450 | 2018 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1403 | Las Vegas
5 | 11E | Las Vegas | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1404 | Las Vegas
5 | 11D | Las Vegas | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1405 | Las Vegas
5 | 11D | Las Vegas | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1406 | Las Vegas
3 | 5 | Reno | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1767 | Reno
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1410 | Las Vegas
5 | 11E | Reno | 2018 | FORD | F-450 | 2018 FORD F-450 DUMP CREW V10 DRW 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1411 | Reno
5 | 11E | Winnemucca | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1421 | Winnemucca
5 | 11E | Winnemucca | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1424 | Winnemucca
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1782 | Reno
5 | 76 | Carson City | 1996 | CYBR | SFT50 | REBUILT 2021 INTERNATIONAL CYBERNETICS SKID TRAILER | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1788 | Carson City
3 | 5 | Fallon | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1791 | Fallon
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1792 | Reno
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1795 | Reno
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1796 | Reno
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1798 | Reno
5 | 11H | Elko | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1428 | Elko
3 | 5 | Elko | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1803 | Elko
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1804 | Reno
5 | 11H | Elko | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1429 | Elko
5 | 11J | Elko | 2018 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1432 | Elko
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1814 | Reno
6 | 11B | Reno | 1991 | INTL | F2574 | TANDEM AXLE CRANE TRUCK REBUILD | J1939 |  |  | SPRATRONICS DE ICER | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 1821 | Reno
3 | 5 | Reno | 2019 | FORD | F-150 | 2019 FORD 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1823 | Reno
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 FORD F450 SNGL AXEL DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1438 | Las Vegas
5 | 11A | Elko | 2005 | FORD | F-550 | FLANNIGAN SHOP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1829 | Elko
3 | 5 | Elko | 2019 | FORD | F-150 | 2019 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1833 | Elko
6 | 11B | Tonopah | 1986 | INTL | F2574 | CRANE TRUCK CONVERTED | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1834 | Tonopah
3 | 3 | Las Vegas | 2018 | FORD | F-250 | 2018 FORD F250 3/4T 4X4 CREW | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1441 | Las Vegas
5 | 11C | Las Vegas | 2005 | PETERBILT | 335 | FUEL LUBE TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1836 | Las Vegas
3 | 3 | Winnemucca | 2018 | FORD | F-250 | 2018 FORD F250 3/4T TRUCK 4X4 CREW CAB | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1444 | Winnemucca
5 | 11A | Ely | 2018 | FORD | F-450 | AERIAL TRUCK F-450 1 TON | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1445 | Ely
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1447 | Las Vegas
2 | 01A | Reno | 2018 | FORD | EXPLORER | 2018 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 1844 | Reno
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1849 | Reno
3 | 5 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1850 | Reno
3 | 5 | Carson City | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1851 | Carson City
9 | 14 | Elko | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1853 | Elko
9 | 14 | Carson City | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1854 | Carson City
3 | 3 | Carson City | 2011 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1448 | Carson City
5 | 11F | Las Vegas | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1857 | Las Vegas
5 | 11F | Las Vegas | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1858 | Las Vegas
8 | 12 | Ely | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 2.75 | 0 | 1 | 1.75 | 192.5 | 302.5 | [5 empty] | Phase 2 | 1451 | Ely
5 | 11E | Reno | 2018 | FORD | F-450 | 2018 FORD F-450 1 TON DUMP 4X4 | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' STRAIGHT PLOW,2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1452 | Reno
8 | 12 | Winnemucca | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  | Yes | Yes - Forward only | X | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 4 | 1454 | Winnemucca
5 | 11E | Fallon | 2018 | FORD | F-450 | 2018 1 - 2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1456 | Fallon
5 | 11E | Reno | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1457 | Reno
5 | 11F | Elko | 2008 | FORD | F-650 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1868 | Elko
5 | 11F | Reno | 2005 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1869 | Reno
8 | 13 | Ely | 1990 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  | 8 YD | Telematics Device |  | Yes | Yes - Forward only | X | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 4.75 | 0 | 1 | 3.75 | 412.5 | 522.5 | [5 empty] | Phase 2 | 1469 | Ely
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 FORD F-450 1T V10 DUMP EXT CAB 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1476 | Las Vegas
3 | 5 | Reno | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1876 | Reno
5 | 11E | Las Vegas | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1480 | Las Vegas
3 | 5 | Carson City | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1883 | Carson City
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1886 | Las Vegas
9 | 14 | Tonopah | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1887 | Tonopah
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1888 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | 1500 | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1889 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1890 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1891 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1892 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1893 | Las Vegas
3 | 3 | Las Vegas | 2012 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1529 | Las Vegas
5 | 11A | Las Vegas | 2016 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1900 | Las Vegas
9 | 14 | Winnemucca | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1901 | Winnemucca
5 | 11A | Las Vegas | 2015 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1903 | Las Vegas
3 | 3 | Fallon | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1605 | Fallon
5 | 11S | Las Vegas | 2014 | FORD | F-450 | DUMP TRUCK W/SWAPLOADER BIODSL | OBDII | Roadwatch Sensor |  | 2014 WILLIAMSEN SWAPLOADER BED | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1614 | Las Vegas
3 | 3 | Elko | 2018 | CHEVROLET | SILVERADO | 2018 CHEVEROLET SIVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1615 | Elko
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1908 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  | SKIDSTER PICKUP BROOM | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1909 | Las Vegas
6 | 11B | Las Vegas | 2015 | WESTERN ST | 4900SF | FLATRACK W/CRANE | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1912 | Las Vegas
5 | 11D | Las Vegas | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1659 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1921 | Las Vegas
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1922 | Las Vegas
5 | 11F | Reno | 2015 | FORD | F-350 | 1 TON SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 1924 | Reno
3 | 3 | Winnemucca | 2019 | FORD | 250 | 2019 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1675 | Winnemucca
5 | 11A | Reno | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1926 | Reno
3 | 3 | Carson City | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1676 | Carson City
3 | 5 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1930 | Las Vegas
5 | 11A | Fallon | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1934 | Fallon
5 | 11H | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1687 | Las Vegas
3 | 3 | Tonopah | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1689 | Tonopah
3 | 3 | Reno | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1695 | Reno
3 | 3 | Fallon | 2019 | FORD | 250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1697 | Fallon
6 | 20 | Elko | 2005 | INTL | 7600 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1942 | Elko
5 | 11J | Ely | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' TE STRAIGHT PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1699 | Ely
3 | 3 | Elko | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1710 | Elko
3 | 3 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1714 | Reno
5 | 11E | Fallon | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1715 | Fallon
5 | 11F | Fallon | 2016 | FORD | F-550 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1954 | Fallon
5 | 11H | Reno | 2016 | PETERBILT | 337 | SINGLE AXLE FLATRACK TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 1955 | Reno
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1744 | Las Vegas
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1959 | Elko
3 | 3 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1748 | Reno
3 | 3 | Reno | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1749 | Reno
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1750 | Las Vegas
3 | 3 | Reno | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1753 | Reno
3 | 3 | Las Vegas | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1759 | Las Vegas
3 | 3 | Ely | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1761 | Ely
3 | 3 | Ely | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1763 | Ely
3 | 3 | Carson City | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICKUP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1766 | Carson City
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1768 | Las Vegas
2 | 01A | Carson City | 2015 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1969 | Carson City
3 | 3 | Las Vegas | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1769 | Las Vegas
3 | 3 | Elko | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1771 | Elko
3 | 3 | Elko | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1778 | Elko
3 | 3 | Elko | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1780 | Elko
3 | 3 | Las Vegas | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1789 | Las Vegas
3 | 3 | Las Vegas | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1801 | Las Vegas
3 | 4 | Carson City | 2015 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 1977 | Carson City
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1978 | Carson City
3 | 3 | Reno | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1805 | Reno
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1807 | Las Vegas
3 | 5 | Winnemucca | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 1982 | Winnemucca
5 | 11H | Elko | 2007 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1826 | Elko
OFF ROAD / NA | 55B | Ely | 2005 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  | 6 WAY STRAIGHT BLADE | Telematics Device |  |  |  | X | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 1997 | Ely
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2001 | Elko
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2003 | Carson City
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2005 | Carson City
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2006 | Carson City
5 | 11E | Las Vegas | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1827 | Las Vegas
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2015 | Elko
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2016 | Carson City
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2017 | Elko
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2018 | Elko
3 | 5 | Las Vegas | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2019 | Las Vegas
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2020 | Elko
3 | 5 | Elko | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2021 | Elko
3 | 5 | Reno | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2023 | Reno
3 | 5 | Carson City | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2024 | Carson City
3 | 5 | Reno | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2025 | Reno
5 | 11J | Carson City | 2006 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1830 | Carson City
2 | 01A | Reno | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2039 | Reno
5 | 11H | Tonopah | 2005 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1835 | Tonopah
2 | 01A | Reno | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2054 | Reno
5 | 11D | Las Vegas | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1837 | Las Vegas
5 | 11D | Las Vegas | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1838 | Las Vegas
2 | 01A | Las Vegas | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2063 | Las Vegas
2 | 01A | Carson City | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2069 | Carson City
2 | 01A | Carson City | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2070 | Carson City
5 | 11 | Reno | 2019 | KENWORTH | T440 | 2021 KENWORTH T400 | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2074 | Reno
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2077 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2078 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2079 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2080 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2081 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2082 | Las Vegas
2 | 1 | Reno | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2083 | Reno
5 | 11E | Carson City | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1840 | Carson City
5 | 11 | Carson City | 2016 | FREIGHTLNR | M2 112 | HERBICIDE SPRAY TRUCK | J1939 |  |  | INJECTION SPRAYER | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2087 | Carson City
5 | 11E | Reno | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1856 | Reno
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2090 | Las Vegas
5 | 11C | Reno | 2016 | FORD | F-550 | LUBE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2091 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2093 | Reno
5 | 11D | Las Vegas | 2019 | FORD | F-450 | 2019 FORD COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1860 | Las Vegas
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 FORD 1/2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1862 | Las Vegas
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2099 | Reno
2 | 01A | Ely | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2102 | Ely
5 | 11S | Las Vegas | 2007 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | FLATRACK BODY SWAPLOADER,DUMP BODY SWAPLOADER,ARROWBOARD VEHICLE MOUNTED | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1863 | Las Vegas
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2106 | Reno
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2107 | Reno
3 | 5 | Ely | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2110 | Ely
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2115 | Reno
5 | 11E | Reno | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1866 | Reno
3 | 5 | Winnemucca | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2117 | Winnemucca
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2118 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2119 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2120 | Las Vegas
2 | 1 | Las Vegas | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2121 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2122 | Las Vegas
5 | 11J | Elko | 2006 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1872 | Elko
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2124 | Las Vegas
5 | 11E | Carson City | 2019 | FORD | F-450 | 2019 FORD F-450 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1874 | Carson City
5 | 11E | Reno | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1877 | Reno
2 | 1 | Reno | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2132 | Reno
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2135 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2136 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2137 | Las Vegas
5 | 11E | Ely | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1879 | Ely
5 | 11E | Ely | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1881 | Ely
5 | 11E | Ely | 2019 | FORD | F-450 | 2019 1/2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITEREADER ARROWBOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1882 | Ely
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2141 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2142 | Las Vegas
5 | 11F | Las Vegas | 2006 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1884 | Las Vegas
5 | 11H | Tonopah | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | ARROW BOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1905 | Tonopah
5 | 11H | Tonopah | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | ARROW BOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1906 | Tonopah
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2154 | Las Vegas
5 | 11H | Tonopah | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1911 | Tonopah
5 | 11E | Tonopah | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 1916 | Tonopah
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2157 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2158 | Las Vegas
5 | 11E | Las Vegas | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1917 | Las Vegas
5 | 11F | Reno | 2015 | FORD | F-350 | SERVICE TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 2160 | Reno
5 | 11E | Las Vegas | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1919 | Las Vegas
5 | 11H | Reno | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1923 | Reno
5 | 11D | Reno | 2015 | FORD | F-450 | TRASH COMPACTOR 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1936 | Reno
5 | 11D | Reno | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1937 | Reno
5 | 11D | Carson City | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1938 | Carson City
5 | 11E | Fallon | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1939 | Fallon
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1940 | Reno
5 | 11E | Fallon | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1943 | Fallon
6 | 28 | Las Vegas | 1988 | FORD | 9000 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2172 | Las Vegas
3 | 5 | Ely | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2173 | Ely
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2175 | Las Vegas
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | SNOWPLOW 8' | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1947 | Reno
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | SNOW PLOW,ARROW BOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1948 | Reno
5 | 11E | Carson City | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2014 SNOW PLOW SNOW DOGG,2014 SALT DOGG SPREADER | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1949 | Carson City
3 | 5 | Carson City | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2183 | Carson City
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2189 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2193 | Las Vegas
5 | 11E | Reno | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 1952 | Reno
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2198 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2201 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2203 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2204 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2205 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2206 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2207 | Las Vegas
5 | 11C | Fallon | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 2209 | Fallon
5 | 11E | Fallon | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | ROCK PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1953 | Fallon
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2215 | Las Vegas
5 | 11H | Elko | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  | HENKE 11 FT REV SNOW PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1960 | Elko
5 | 11H | Wells | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1961 | Wells
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2221 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2222 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2228 | Las Vegas
5 | 11H | Wells | 2015 | FORD | F-450 | FLATRACK TRUCK W/LIFT GATE | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 1962 | Wells
5 | 11E | Elko | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1963 | Elko
2 | 1 | Las Vegas | 2015 | FORD | FOCUS | ELECTRIC SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2234 | Las Vegas
5 | 11E | Elko | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1964 | Elko
2 | 1 | Las Vegas | 2015 | FORD | FOCUS | ELECTRIC SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2237 | Las Vegas
5 | 11H | Elko | 2019 | FORD | F-450 | 2019 FLATRACK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1967 | Elko
5 | 11J | Las Vegas | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1970 | Las Vegas
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/ CAMPERSHELL 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1971 | Carson City
2 | 01A | Carson City | 2015 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2241 | Carson City
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2242 | Las Vegas
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1972 | Carson City
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1973 | Carson City
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1974 | Carson City
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1976 | Carson City
5 | 11H | Elko | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 1979 | Elko
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2248 | Las Vegas
5 | 11F | Carson City | 2008 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2249 | Carson City
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2251 | Elko
5 | 11F | Carson City | 2019 | FORD | F-450 | 2019 1 TON SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 1981 | Carson City
5 | 11F | Las Vegas | 2019 | FORD | F-450 | 2019 SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 1984 | Las Vegas
5 | 11J | Winnemucca | 2008 | FORD | F-350 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2254 | Winnemucca
3 | 3 | Las Vegas | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2085 | Las Vegas
5 | 11H | Reno | 2016 | FORD | F-550 | 1 1/2 TON FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2088 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2259 | Reno
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK W/CAMPERSHELL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2260 | Carson City
5 | 11C | Ely | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2261 | Ely
3 | 3 | Reno | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2094 | Reno
3 | 3 | Carson City | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2097 | Carson City
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  | 2013 LIGHT READER 1230 F-4 | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2264 | Reno
5 | 11 | Las Vegas | 1990 | INTL | 4700 | T/M WEED SPRAYER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2265 | Las Vegas
5 | 11 | Reno | 1990 | INTL | 4700 | INTL TRUCK W/WEED SPRAYER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2266 | Reno
5 | 11C | Las Vegas | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2267 | Las Vegas
3 | 3 | Reno | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2104 | Reno
3 | 3 | Tonopah | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2116 | Tonopah
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2123 | Las Vegas
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2128 | Las Vegas
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2131 | Las Vegas
3 | 5 | Reno | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2273 | Reno
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2138 | Las Vegas
3 | 3 | Tonopah | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2139 | Tonopah
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2140 | Las Vegas
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2151 | Las Vegas
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2152 | Las Vegas
3 | 3 | Fallon | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 2153 | Fallon
5 | 11E | Carson City | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2155 | Carson City
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2281 | Reno
5 | 11E | Fallon | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 2156 | Fallon
3 | 5 | Winnemucca | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2283 | Winnemucca
3 | 3 | Carson City | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2159 | Carson City
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2285 | Elko
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2287 | Las Vegas
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2288 | Reno
3 | 3 | Carson City | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2165 | Carson City
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2166 | Reno
3 | 3 | Elko | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2167 | Elko
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2294 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2295 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2297 | Reno
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2298 | Las Vegas
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2299 | Reno
3 | 5 | Winnemucca | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2300 | Winnemucca
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2301 | Reno
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2168 | Reno
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2170 | Las Vegas
9 | 14 | Las Vegas | 2007 | PETERBILT | 378 | TRACTOR TRUCK W/MANUAL TRANS | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2304 | Las Vegas
9 | 14 | Las Vegas | 2007 | PETERBILT | 378 | TRUCK TRACTOR W/MANUAL TRANS | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2305 | Las Vegas
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2179 | Reno
3 | 5 | Reno | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2307 | Reno
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2180 | Las Vegas
2 | 01A | Reno | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2310 | Reno
6 | 28 | Elko | 1990 | MACK | MR690 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2315 | Elko
6 | 28 | Ely | 1990 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2316 | Ely
2 | 01A | Reno | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2317 | Reno
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2318 | Las Vegas
6 | 28 | Fallon | 1991 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 2331 | Fallon
9 | 14 | Elko | 2019 | WESTERN | 4900SF | TRANSPORT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2334 | Elko
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  | PROFILING SYSTEM | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2335 | Carson City
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2336 | Carson City
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2362 | Carson City
2 | 01A | Carson City | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2365 | Carson City
3 | 5 | Carson City | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2366 | Carson City
3 | 5 | Carson City | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2368 | Carson City
2 | 01A | Carson City | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2373 | Carson City
3 | 5 | Carson City | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2375 | Carson City
2 | 01A | Las Vegas | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2377 | Las Vegas
5 | 11F | Elko | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 UTILITY TRUCK WITH CRANE ASSEMBLY | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2379 | Elko
2 | 01A | Carson City | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 2380 | Carson City
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2382 | Las Vegas
3 | 5 | Winnemucca | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2386 | Winnemucca
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2387 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2390 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2391 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2392 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2393 | Las Vegas
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2395 | Las Vegas
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2396 | Las Vegas
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2397 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2398 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2399 | Reno
3 | 5 | Carson City | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2400 | Carson City
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2401 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2402 | Reno
3 | 5 | Elko | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2403 | Elko
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2404 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2405 | Reno
3 | 5 | Reno | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2406 | Reno
3 | 5 | Las Vegas | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2407 | Las Vegas
3 | 5 | Elko | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2408 | Elko
3 | 5 | Winnemucca | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2409 | Winnemucca
3 | 5 | Elko | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2410 | Elko
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2421 | Las Vegas
3 | 5 | Las Vegas | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2423 | Las Vegas
5 | 11E | Ely | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2181 | Ely
5 | 10 | Carson City | 2016 | FORD | F-350 | 1 TON TRUCK W/UTILITY BODY | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2448 | Carson City
6 | 28 | Ely | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2463 | Ely
6 | 28 | Fallon | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 2464 | Fallon
6 | 77 | Winnemucca | 1991 | MACK | MR688 | LINE STRIPER | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 2474 | Winnemucca
6 | 28 | Winnemucca | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2479 | Winnemucca
5 | 11E | Ely | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2196 | Ely
2 | 1 | Elko | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2525 | Elko
2 | 1 | Elko | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2528 | Elko
2 | 1 | Winnemucca | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2535 | Winnemucca
3 | 4 | Las Vegas | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS 15 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 2544 | Las Vegas
OFF ROAD / NA | 55B | Reno | 2007 | PSTN BULLY | SCOUT | SNOW CAT | None- wired direct |  |  | BLADE 6-WAY | Telematics Device |  |  |  | X | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 2583 | Reno
5 | 76 | Carson City | 1992 | DYNA | TEST | FALLING WEIGHT DEFLECTOMETER | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2619 | Carson City
5 | 11J | Fallon | 2008 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 2231 | Fallon
5 | 76 | Carson City | 2018 | DYNA | 8000 | 2018 SKID TESTER | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2666 | Carson City
5 | 11A | Las Vegas | 1997 | GMC | 3500H | AERIAL TRUCK W/MAN LIFT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2670 | Las Vegas
5 | 11H | Winnemucca | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2232 | Winnemucca
5 | 11H | Reno | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2235 | Reno
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2238 | Las Vegas
9 | 14 | Las Vegas | 1996 | FORD | 9501 | TRACTOR TRUCK | J1939 |  |  | BREAKER ATTACHMENT | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2680 | Las Vegas
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2239 | Las Vegas
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2240 | Las Vegas
6 | 28 | Reno | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Pilot | 2691 | Reno
6 | 28 | Tonopah | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2692 | Tonopah
5 | 10 | Las Vegas | 1998 | GMC | K3094 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2733 | Las Vegas
5 | 11J | Reno | 1998 | GMC | TK314 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2742 | Reno
5 | 11E | Reno | 1998 | GMC | TC31003 | DUMP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2747 | Reno
5 | 11E | Reno | 1998 | GMC | TC31003 | DUMP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2753 | Reno
5 | 11J | Las Vegas | 1998 | GMC | W5R04 | UTILITY TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2754 | Las Vegas
5 | 11E | Las Vegas | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | HINKER C- PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2243 | Las Vegas
5 | 11H | Tonopah | 2008 | FORD | F-450 | 1 TON FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  | MESSAGE BOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2244 | Tonopah
3 | 3 | Reno | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2245 | Reno
3 | 3 | Carson City | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2246 | Carson City
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2247 | Las Vegas
3 | 3 | Las Vegas | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2252 | Las Vegas
5 | 11J | Tonopah | 2008 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2253 | Tonopah
5 | 11F | Carson City | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2255 | Carson City
5 | 11F | Tonopah | 2008 | FORD | F-450 | 1 TON SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 | 2256 | Tonopah
3 | 3 | Las Vegas | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2258 | Las Vegas
9 | 14 | Winnemucca | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2785 | Winnemucca
9 | 14 | Carson City | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2786 | Carson City
9 | 14 | Reno | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2787 | Reno
3 | 3 | Reno | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2302 | Reno
6 | 28 | Carson City | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2803 | Carson City
6 | 28 | Tonopah | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2804 | Tonopah
OFF ROAD / NA | 55B | Tonopah | 1981 | TUCKER | SNOWCAT | SNOW CAT | None- wired direct |  |  |  | Telematics Device |  |  |  | X | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2810 | Tonopah
5 | 11A | Las Vegas | 2019 | FREIGHTLNR | M2 | 2019 AERIAL LIFT TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2904 | Las Vegas
3 | 5 | Reno | 1999 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2906 | Reno
5 | 11A | Elko | 2018 | DODGE | 5500 | 2018 AERIAL LIFT TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2907 | Elko
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2303 | Reno
5 | 11E | Las Vegas | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2308 | Las Vegas
5 | 11A | Carson City | 2019 | FORD | F-550 | 2019 ARIEL LIFT TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 2911 | Carson City
2 | 1 | Las Vegas | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2912 | Las Vegas
2 | 01A | Las Vegas | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2915 | Las Vegas
3 | 4 | Las Vegas | 2021 | FORD | T-350 | 2021 FORD T-350 12 PASSENGER TRANSIT VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2916 | Las Vegas
2 | 1 | Reno | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2917 | Reno
5 | 11F | Carson City | 2016 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 2429 | Carson City
2 | 01A | Las Vegas | 2000 | GMC | JIMMY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2927 | Las Vegas
3 | 4 | Tonopah | 2000 | GMC | TG31405 | AWD CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 4 | 2932 | Tonopah
3 | 5 | Winnemucca | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2941 | Winnemucca
3 | 5 | Winnemucca | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2943 | Winnemucca
3 | 5 | Elko | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2951 | Elko
3 | 5 | Reno | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2952 | Reno
3 | 5 | Reno | 2000 | GMC | SIERRA | 1/2 TON PICKUP AWD | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2975 | Reno
5 | 10 | Las Vegas | 2000 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2984 | Las Vegas
5 | 10 | Las Vegas | 2000 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2987 | Las Vegas
5 | 11H | Reno | 2001 | INTL | 4700 | FLAT RACK TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 2989 | Reno
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2647 | Las Vegas
5 | 11F | Elko | 2001 | INTL | 4700 | FLAT RACK W/CRANE | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 | 2991 | Elko
3 | 3 | Elko | 1998 | GMC | SIERRA | 3/4 TON PICKUP TRUCK W/SVC BODY AWD | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | POC | 3.75 | 3.75 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 2761 | Elko
8 | 12 | Las Vegas | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 2.75 | 0 | 1 | 1.75 | 192.5 | 302.5 | [5 empty] | Phase 1 | 2773 | Las Vegas
5 | 11J | Reno | 2000 | FORD | F-450 | AWD SIGN SHOP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2990 | Reno
5 | 11E | Las Vegas | 2000 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 2995 | Las Vegas
5 | 11S | Las Vegas | 2000 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  | SWAPLOADER DUMP BODY | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 2996 | Las Vegas
3 | 5 | Las Vegas | 2000 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3066 | Las Vegas
5 | 11 | Reno | 2000 | FORD | F-450 | REBUILD MISC TRUCK - BOX TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3001 | Reno
6 | 11B | Las Vegas | 2001 | FREIGHTLNR | FL70 | CRANE TRUCK | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3069 | Las Vegas
5 | 11J | Las Vegas | 2008 | FORD | F-350 | UTILITY TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3071 | Las Vegas
5 | 11E | Las Vegas | 2000 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  | ARROW BOARD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3005 | Las Vegas
3 | 5 | Reno | 2000 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3089 | Reno
3 | 4 | Carson City | 2000 | DODGE | GRAND CARAVA | 7 PASSENGER VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 2 | 3093 | Carson City
2 | 1 | Las Vegas | 2001 | TOYOTA | PRIUS | 4 DOOR SEDAN/HYBRID ELECTRIC | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3096 | Las Vegas
5 | 11J | Reno | 2001 | GMC | SIERRA | UTILITY TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3112 | Reno
2 | 1 | Carson City | 2002 | TOYOTA | PRIUS | HYBRID ELECTRIC SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 3113 | Carson City
2 | 1 | Las Vegas | 2002 | TOYOTA | PRIUS | HYBRID SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3114 | Las Vegas
5 | 6 | Las Vegas | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3121 | Las Vegas
5 | 11F | Las Vegas | 2002 | FORD | F-550 | SHOP SERVICE TRUCK W/CRANE | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3122 | Las Vegas
8 | 13H | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3125 | Las Vegas
8 | 13H | Las Vegas | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3127 | Las Vegas
5 | 11H | Las Vegas | 2000 | FORD | F-450 | 1 TON FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3068 | Las Vegas
5 | 11A | Elko | 2002 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 3138 | Elko
5 | 11 | Las Vegas | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3149 | Las Vegas
5 | 11 | Las Vegas | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3150 | Las Vegas
2 | 01A | Las Vegas | 2002 | GMC | ENVOY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3151 | Las Vegas
5 | 6 | Reno | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3158 | Reno
8 | 13 | Las Vegas | 2001 | PETERBILT | 320 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 2.75 | 0 | 1 | 1.75 | 192.5 | 302.5 | [5 empty] | Phase 1 | 3072 | Las Vegas
3 | 3 | Las Vegas | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3119 | Las Vegas
5 | 11E | Las Vegas | 2002 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3124 | Las Vegas
5 | 11A | Las Vegas | 2005 | FORD | F-550 | AERIAL TRUCK W/ARTICULATING DEVICE | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3185 | Las Vegas
3 | 3 | Las Vegas | 2004 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3180 | Las Vegas
5 | 11F | Las Vegas | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3181 | Las Vegas
5 | 11F | Las Vegas | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3182 | Las Vegas
5 | 11H | Las Vegas | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3183 | Las Vegas
3 | 5 | Carson City | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 3194 | Carson City
5 | 11E | Las Vegas | 2005 | FORD | F-450 | DUMP TRUCK W/ARROWBOARD BIO-DSL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3184 | Las Vegas
5 | 11D | Las Vegas | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3186 | Las Vegas
5 | 11E | Reno | 2005 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2019 SNOWDOG SNOW PLOW 9',2019 SALTDOG SAND SPREADER 2.0 CU YD | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3192 | Reno
5 | 11H | Reno | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3193 | Reno
9 | 14 | Fallon | 2004 | PETERBILT | 378 | TRUCK TRACTOR | J1939 |  |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 3201 | Fallon
6 | 20 | Carson City | 2004 | INTL | 7600 6X4 | CULVERT CLEANER | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 3202 | Carson City
5 | 11H | Carson City | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 2 | 3227 | Carson City
5 | 11H | Fallon | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 3228 | Fallon
5 | 11H | Reno | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3229 | Reno
5 | 11H | Fallon | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 3230 | Fallon
5 | 11H | Reno | 2005 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3196 | Reno
5 | 11H | Carson City | 2005 | FORD | F-450 | 1 TON FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 3197 | Carson City
5 | 11E | Reno | 2006 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  | 2 YARD SANDER,SNOW PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3231 | Reno
5 | 11E | Reno | 2006 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3232 | Reno
5 | 11F | Carson City | 2005 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 2 | 3233 | Carson City
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3248 | Las Vegas
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3249 | Las Vegas
5 | 6 | Las Vegas | 2006 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3256 | Las Vegas
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3252 | Las Vegas
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3254 | Las Vegas
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3259 | Las Vegas
3 | 3 | Reno | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3260 | Reno
3 | 3 | Las Vegas | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3262 | Las Vegas
5 | 11 | Las Vegas | 2007 | INTL | 7400 | WEED SPRAYER TRUCK | J1939 |  |  |  | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3266 | Las Vegas
3 | 3 | Reno | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3264 | Reno
5 | 11 | Las Vegas | 2006 | INTL | 4200 | BUTTON TRUCK W/UTILITY BODY | J1939 |  |  | ARROW BOARD | Telematics Device | No |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 1 | 3270 | Las Vegas
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | POC | 2.25 | 2.25 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 4 - (Pre-Pilot) | 3274 | Elko
5 | 11H | Las Vegas | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3265 | Las Vegas
2 | 01A | Las Vegas | 2007 | FORD | EXPLORER | SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3298 | Las Vegas
2 | 01A | Reno | 2007 | FORD | EXPLORER | SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 | 3299 | Reno
2 | 01A | Las Vegas | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 3.25 | 0 | 1 | 2.25 | 247.5 | 357.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3301 | Las Vegas
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3297 | Las Vegas
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3302 | Reno
3 | 3 | Reno | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3303 | Reno
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3304 | Las Vegas
3 | 3 | Las Vegas | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3305 | Las Vegas
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3310 | Reno
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3311 | Reno
3 | 3 | Reno | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3312 | Reno
5 | 11J | Reno | 2008 | FORD | F-450 | UTILITY TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3313 | Reno
5 | 11E | Las Vegas | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  | 2012 HINKER C-PLOW | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 - (Pre-Pilot) | 3314 | Las Vegas
5 | 11S | Las Vegas | 2008 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 1 | 3315 | Las Vegas
8 | 13 | Las Vegas | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | Telematics Device |  |  |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 2.75 | 0 | 1 | 1.75 | 192.5 | 302.5 | [5 empty] | Phase 1 | 3318 | Las Vegas
8 | 25 | Carson City | 2007 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3 | 0 | 1 | 2 | 220 | 330 | [5 empty] | Phase 2 | 394 | Carson City
8 | 25 | Carson City | 2006 | INTL | 5900I | TRUCK , W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3 | 0 | 1 | 2 | 220 | 330 | [5 empty] | Phase 2 | 3205 | Carson City
8 | 25 | Carson City | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  | Telematics Device | Pump on/off sensor |  |  | x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3 | 0 | 1 | 2 | 220 | 330 | [5 empty] | Phase 2 | 3234 | Carson City
5 | 11F | Fallon | 2019 | FORD | F-550 | F-550 SERVICE TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | 2.25 | 0 | 1 | 1.25 | 137.5 | 247.5 | [5 empty] | Phase 3 | 1859 | Fallon
3 | 3 | Fallon | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 |  | 3.75 | 0 | 1 | 2.75 | 302.5 | 412.5 | [5 empty] | Phase 3 | 2092 | Fallon
2 | 01A | Carson City | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 1 | 1 | 0 | Geotab only install $0 under NASPO | Phase 2 | 1 | Carson City
2 | 01A | Las Vegas | 2016 | FORD | EXPLORER | SUV 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 2 | 2 | 264 |  | Phase 1 - (Pre-Pilot) | 2 | Las Vegas
2 | 1 | Las Vegas | 2019 | CHEVROLET | MALIBU HYB | 2019 SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 3 | 4 | 484 |  | Phase 1 - (Pre-Pilot) | 3 | Las Vegas
2 | 01A | Reno | 2007 | GMC | ENVOY | GMC ENVOY SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 4 | 6 | 660 |  | Phase 1 | 10 | Reno
2 | 01A | Las Vegas | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 5 | 9 | 990 |  | Phase 1 - (Pre-Pilot) | 11 | Las Vegas
3 | 5 | Las Vegas | 2016 | FORD | F-150 | 1/2 TON PICKUP 4X4 E-85 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 6 | 12 | 1320 |  | Phase 1 - (Pre-Pilot) | 12 | Las Vegas
3 | 5 | Tonopah | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier 7 | 15 | 1650 |  | Phase 4 | 13 | Tonopah
2 | 01A | Las Vegas | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Special Req. |  |  |  | Phase 1 - (Pre-Pilot) | 17 | Las Vegas
2 | 01A | Carson City | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 2 | 18 | Carson City
2 | 1 | Las Vegas | 2001 | TOYOTA | PRIUS | HYBRID SEDAN 4 DOOR | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 |  | Full Imp. Hrs | 83.5 |  |  | Phase 1 - (Pre-Pilot) | 26 | Las Vegas
2 | 1 | Las Vegas | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Install Hours | 86.5 | 9515 |  | Phase 1 - (Pre-Pilot) | 31 | Las Vegas
3 | 5 | Carson City | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 2 | 37 | Carson City
2 | 1 | Las Vegas | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 - (Pre-Pilot) | 43 | Las Vegas
2 | 1 | Carson City | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Notes |  |  |  | Phase 2 | 50 | Carson City
2 | 1 | Carson City | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | GO installs at $0 |  |  |  | Phase 2 | 52 | Carson City
3 | 5 | Reno | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | IOX-WRKS as Naspo rate |  |  |  | Phase 1 | 53 | Reno
2 | 1 | Carson City | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 |  | Tier package based on Cost Minus 1hr Go Install Cost |  |  |  | Phase 2 | 55 | Carson City
2 | 1 | Ely | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 2 | 56 | Ely
2 | 1 | Las Vegas | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 - (Pre-Pilot) | 57 | Las Vegas
2 | 1 | Reno | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 | 58 | Reno
2 | 1 | Winnemucca | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 4 | 59 | Winnemucca
3 | 5 | Reno | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 | 72 | Reno
3 | 5 | Reno | 2001 | GMC | TC15903 | 1/2 TON PICKUP | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 | 89 | Reno
3 | 5 | Reno | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 | 96 | Reno
2 | 01A | Reno | 1998 | GMC | JIMMY | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 | 99 | Reno
3 | 5 | Winnemucca | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 4 | 104 | Winnemucca
2 | 01A | Las Vegas | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 - (Pre-Pilot) | 106 | Las Vegas
2 | 01A | Reno | 2005 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 | 116 | Reno
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | POC | 1 | 1 | 1 | 0 | 0 | 110 | [5 empty] | Phase 4 - (Pre-Pilot) | 120 | Elko
5 | 10 | Reno | 2001 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 | 136 | Reno
3 | 5 | Elko | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | POC | 1 | 1 | 1 | 0 | 0 | 110 | [5 empty] | Phase 4 - (Pre-Pilot) | 140 | Elko
2 | 1 | Reno | 2008 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 | 148 | Reno
3 | 5 | Las Vegas | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 | 151 | Las Vegas
3 | 5 | Reno | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 | 152 | Reno
2 | 01A | Las Vegas | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 | 153 | Las Vegas
2 | 1 | Las Vegas | 1998 | FORD | ESCORT | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 - (Pre-Pilot) | 185 | Las Vegas
2 | 1 | Las Vegas | 2018 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 1 - (Pre-Pilot) | 210 | Las Vegas
5 | 11F | Las Vegas | 2007 | FORD | F-550 | SERVICE TRUCK BIO-DIESEL | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 1 - (Pre-Pilot) | 233 | Las Vegas
3 | 5 | Carson City | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 2 | 3250 | Carson City
3 | 3 | Carson City | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  | SPREADER BED MOUNT,SNOW V PLOW 4 WAY, | Telematics Device | No | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2.5 | 0 | 1 | 1.5 | 165 | 275 | [5 empty] | Phase 2 | 3257 | Carson City
3 | 3 | Carson City | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2.5 | 0 | 1 | 1.5 | 165 | 275 | [5 empty] | Phase 2 | 3275 | Carson City
3 | 3 | Carson City | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2.5 | 0 | 1 | 1.5 | 165 | 275 | [5 empty] | Phase 2 | 3295 | Carson City
2 | 1 | Carson City | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  | Telematics Device |  |  |  | X | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 0 | 0 | 110 | [5 empty] | Phase 2 | 3306 | Carson City
3 | 4 | Carson City | 2008 | GMC | SAVANA | CARGO VAN | OBDII |  |  |  | Telematics Device |  | Yes |  | X | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Phase 2 | 3308 | Carson City
7 | 83 | Carson City | 2020 | WESTERN ST | 4900 | UNDERBRIDGE INSPECTION TRUCK | J1939 |  |  |  | Telematics Device |  | Yes |  | X | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 1 | 1 | 110 | 220 | [5 empty] | Pilot | 2350 | Carson City

## Unit Master 11-14-2022
VIN # | Unit No | MCC | Owning Dept | Using Dept | Maint Loc | Year | Make | Model | Description | LTD Meter | Fuel Type | County | Acqtn Date | Arvl Date | In-Srvc Date | HYD PUMP MAKE | HYD VALVE BANK MAKE | Unit Status @ RFP | Unit Status - 11/14/2022 | Deleted/New | Crew Description | Location | District | New Description | Winter Operations | Federal MCC | Existing OBDII/J1939 | Existing Roadwatch SS | Existing Parker/CIRUS/FORCE AMERICA/EPOKE | Existing GO9/GO9+ | GO9 Device Serial Number | Existing Verizon hardware | Existing Associations/Hardware | Need Telematics device (no Wi-Fi required) or Wi-Fi capable telematics device or Winter operations and Wi-Fi capable telematic device or Telematics device for Winter Operations (All telematic devices to come with the required harness) | Need Wi-Fi HotSpot | Harness Needed | Need Up/down sensors | Need a single facing (road facing) Weatherproof Wide-Angle Camera with built-in Infrared and Wi-Fi | Need Harnesses | Lightbar Needed | Comments | Implementation Phase | Implementation Actual Phase | NDOT Validation | Satellite | Dual Share Services | Installation Date (George) | Installation Date (Mustafa) | Installation Date (Gov5 Geotab) | Internal Notes
1FM5K8B88GGB81346 | 1 | 01A | C727 | A002 | C727 | 2016 | FORD | EXPLORER | SUV 4X4 | 10959 | UNLEADED | CARSON CITY | 2015-10-29 | 2016-01-19 | 2016-02-08 |  |  | A | A |  | Office of the Director | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B8XGGC93212 | 2 | 01A | C721 | C101 | C721 | 2016 | FORD | EXPLORER | SUV 4X4 E-85 | 41160 | E-85 | CLARK | 2016-02-18 | 2016-05-10 | 2016-05-18 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FM5K8B8XGGC93212 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1G1ZF5SU7KF217265 | 3 | 1 | C721 | C721 | C721 | 2019 | CHEVROLET | MALIBU HYB | 2019 SEDAN | 1418 | UNLEADED | CARSON CITY | 2019-10-09 | 2019-10-17 | 2019-11-05 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZF5SU7KF217265 |  | Yes |  |  | 11.22.2022
1GKDT13S872202163 | 10 | 01A | C767 | C204 | C767 | 2007 | GMC | ENVOY | GMC ENVOY SUV | 67774 | UNLEADED | CARSON CITY | 2007-07-17 | 2007-08-14 | 2007-09-07 |  |  | A | A |  | Permits | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B80GGB75976 | 11 | 01A | C721 | C101 | C721 | 2016 | FORD | EXPLORER | SUV 4X4 | 13321 | E-85 | CLARK | 2015-10-29 | 2016-01-19 | 2016-03-09 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FM5K8B80GGB75976 |  |  |  |  | 11.22.2022 | 11/28/2022: The installation date has two entries for this vehicle on gov5 server for some reason.
1FTEX1E85GFB30160 | 12 | 5 | C721 | C101 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP 4X4 E-85 | 64580 | E-85 | CLARK | 2015-11-09 | 2016-04-13 | 2016-06-08 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1E85GFB30160 |  |  |  |  | 11.23.2022
1FTEX1EF1GKD82767 | 13 | 5 | C725 | C170 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 98402 | UNLEADED | NYE | 2015-11-09 | 2016-03-03 | 2016-04-21 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GKDT13S762246783 | 17 | 01A | C721 | C101 | C721 | 2006 | GMC | ENVOY | SUV 4X4 | 107479 | UNLEADED | CLARK | 2005-07-01 | 2006-01-26 | 2006-02-23 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GKDT13S762246783 |  |  |  |  | 11.22.2022
1GKDT13S962247594 | 18 | 01A | C727 | C802 | C727 | 2006 | GMC | ENVOY | SUV 4X4 | 105159 | UNLEADED | CARSON CITY | 2005-07-01 | 2006-01-26 | 2006-03-02 |  |  | A | A |  | Transportation / Multimodal Planning (Landmark) | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E89GFB30162 | 20 | 5 | C725 | C104 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 92976 | UNLEADED | NYE | 2015-11-09 | 2016-04-14 | 2016-07-22 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT8W3B67GEB79297 | 22 | 6 | C725 | C171 | C725 | 2016 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | 160700 | UNLEADED | NYE | 2015-11-03 | 2016-01-25 | 2016-04-21 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
JT2BK12U510007495 | 26 | 1 | C721 | C721 | C721 | 2001 | TOYOTA | PRIUS | HYBRID SEDAN 4 DOOR | 65126 | UNLEADED | CLARK | 2000-08-18 | 2000-08-18 | 2000-08-18 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot |  | #N/A
1FD0X4GT2GEC57849 | 29 | 11E | C720 | C159 | C721 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 59588 | BIO DIESEL | CLARK | 2016-02-08 | 2016-07-19 | 2016-08-22 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | NA |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1G1ZS52F34F162202 | 31 | 1 | C721 | A061 | C721 | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 77869 | UNLEADED | CLARK | 2004-06-01 | 2004-06-09 | 2004-06-22 |  |  | A | A |  | Traffic Management Center (TMC) | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZS52F34F162202 |  |  |  |  | 11.22.2022
1NPTL70X0HD414984 | 32 | 13 | C725 | C175 | C725 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 31096 | DIESEL | NYE | 2016-02-08 | 2016-05-23 | 2017-08-18 | PARKER | CERTIFIED POWER | A | A |  | Goldfield Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,ONE WAY PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X2HD414985 | 34 | 13 | C725 | C172 | C725 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 44818 | DIESEL | NYE | 2016-02-08 | 2016-05-23 | 2017-08-08 | PARKER | CERTIFIED POWER | A | A |  | Big Smokey Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | ONE-WAY PLOW,2017 HENKE SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTPW14596FA39605 | 37 | 5 | C727 | C056 | C727 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 134748 | UNLEADED | CARSON CITY | 2006-02-21 | 2006-02-24 | 2006-03-24 |  |  | A | A |  | Architectural | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X4HD414986 | 38 | 13 | C721 | C178 | C721 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 37646 | DIESEL | CLARK | 2016-02-08 | 2016-05-23 | 2017-09-05 | PARKER | CERTIFIED POWER | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,ONE WAY PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPCL70X3HD440107 | 39 | 25 | C721 | C124 | C721 | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | 25547 | DIESEL | CLARK | 2016-06-27 | 2017-10-25 | 2018-01-25 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZT51F76F208311 | 43 | 1 | C720 | C720 | C767 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 115139 | RFG | WASHOE | 2005-07-07 | 2006-02-22 | 2006-03-28 |  |  | A | A |  | South Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZT51F76F208311 |  |  |  |  | 11.22.2022
1G1ZC5ST9MF035134 | 50 | 1 | C727 | C727 | C727 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | 5098 | UNLEADED | WASHOE | 2020-09-27 | 2020-11-24 | 2020-12-28 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G1ZC5ST8MF035139 | 52 | 1 | C727 | C727 | C727 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | 2575 | UNLEADED | WASHOE | 2020-09-27 | 2020-11-24 | 2020-12-29 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1FTEX1EF8GKD82765 | 53 | 5 | C767 | C201 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 74169 | RFG | WASHOE | 2015-11-09 | 2016-04-14 | 2016-08-25 |  |  | A | A |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X6HD414987 | 54 | 13 | C767 | C234 | C767 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 50079 | DIESEL | STOREY | 2016-02-08 | 2016-05-23 | 2017-08-02 | PARKER | CERTIFIED POWER | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1G1ZC5ST7MF035052 | 55 | 1 | C727 | C727 | C727 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | 3529 | UNLEADED | WASHOE | 2020-09-27 | 2020-11-24 | 2020-12-29 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G1ZC5ST2MF035055 | 56 | 1 | C724 | C724 | C724 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | 939 | UNLEADED | WHITE PINE | 2020-09-27 | 2020-11-24 | 2020-12-15 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G1ZT51F36F208127 | 57 | 1 | C720 | C720 | C720 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 52954 | RFG | WASHOE | 2005-07-07 | 2006-02-22 | 2006-03-23 |  |  | A | A |  | South Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZT51F36F208127 |  |  |  |  | 11.22.2022
1G1ZT51F46F207794 | 58 | 1 | C767 | C767 | C767 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 115936 | RFG | WASHOE | 2005-07-07 | 2006-02-22 | 2006-03-23 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G1ZC5ST1MF034947 | 59 | 1 | C726 | C726 | C726 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | 5250 | FLEX FUEL | CLARK | 2020-09-27 | 2020-11-24 | 2020-12-16 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1NPTL70X8HD414988 | 62 | 13 | C767 | C231 | C767 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 33570 | DIESEL | WASHOE | 2016-02-08 | 2016-05-23 | 2017-08-02 | PARKER | CERTIFIED POWER | A | A |  | Nixon Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1NPTM70X8HD418004 | 66 | 15 | C767 | C250 | C767 | 2017 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | 37128 | DIESEL | WASHOE | 2016-03-10 | 2016-05-23 | 2017-09-28 | PARKER | CERTIFIED POWER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | ONE WAY PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FTSX21596ED02294 | 68 | 3 | C723 | C723 | C723 | 2006 | FORD | F-250 | 3/4 TON PICKUP 4X4 | 183811 | UNLEADED | ELKO | 2005-07-01 | 2006-04-13 | 2006-05-08 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSX21596ED02294 |  |  |  |  | 11.30.2022
1GTEC14T51E265850 | 72 | 5 | C767 | C904 | C767 | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | 80275 | RFG | WASHOE | 2000-11-06 | 2001-03-14 | 2001-04-19 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT0HHHT9494 | 82 | 24 | C767 | C225 | C767 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 11967 | DIESEL | LYON | 2015-10-08 | 2016-10-11 | 2016-10-28 |  | PARKER | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B82GGB75977 | 84 | 01A | C724 | C307 | C724 | 2016 | FORD | EXPLORER | SUV 4X4 | 54531 | UNLEADED | WHITE PINE | 2015-10-29 | 2016-01-19 | 2016-03-15 |  |  | A | A |  | Ely District Administration | Ely | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTBF2B60HEB30282 | 88 | 3 | C724 | C380 | C724 | 2017 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 91772 | FLEX FUEL | WHITE PINE | 2015-11-03 | 2016-09-27 | 2016-11-09 |  |  | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14T91E265964 | 89 | 5 | C722 | C911 | C722 | 2001 | GMC | TC15903 | 1/2 TON PICKUP | 156002 | UNLEADED | CARSON CITY | 2000-11-07 | 2001-03-14 | 2001-04-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTBF2B66GEB79291 | 91 | 3 | C723 | C336 | C723 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 172962 | UNLEADED | ELKO | 2015-11-03 | 2016-01-25 | 2016-03-25 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTBF2B63GEB79295 | 94 | 3 | C724 | C381 | C724 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 135420 | FLEX FUEL | WHITE PINE | 2015-11-03 | 2016-01-25 | 2016-06-13 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14T41E263510 | 96 | 5 | C767 | C767 | C767 | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | 162905 | UNLEADED | CARSON CITY | 2000-11-06 | 2001-03-13 | 2001-04-02 |  |  | D | D |  | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GKDT13W5WK513812 | 99 | 01A | C767 | C767 | C767 | 1998 | GMC | JIMMY | AWD SUV | 87979 | UNLEADED | CARSON CITY | 1998-03-26 | 1998-09-24 | 1998-09-24 |  |  | D | A |  | Equipment Shop | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BB7MGB35341 | 100 | 01A | C721 | C101 | C721 | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | 4786 | E-85 | CLARK | 2021-01-13 | 2021-04-16 | 2021-09-08 |  |  |  | A | New - Nov 2022 | Las Vegas District Administration | Las Vegas | District 1 |  |  | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1FMSK8BB7MGB35341 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FTSF20PX6EC83518 | 101 | 3 | C720 | C720 | C720 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 214771 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-08 |  |  | A | A |  | South Las Vegas District Repair Shop | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSF20PX6EC83518 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
863535P | 102 | 25 | C723 | C351 | C723 | 1976 | PETERBILT | MD359 | TRACTOR TRUCK | 764354 | DIESEL | ELKO | 1984-02-02 | 1984-02-02 | 1984-02-02 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTRX14W56KC29939 | 104 | 5 | C726 | C304 | C726 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 117337 | UNLEADED | HUMBOLDT | 2005-07-01 | 2006-01-31 | 2006-03-02 |  |  | A | A |  | Winnemucca District Administration | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BB9MGB35342 | 105 | 01A | C721 | C101 | C721 | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | 4140 | E-85 | CLARK | 2021-01-13 | 2021-04-16 | 2021-09-08 |  |  |  | A | New - Nov 2022 | Las Vegas District Administration | Las Vegas | District 1 |  |  | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1FMSK8BB9MGB35342 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FMSK8BB0MGB35343 | 106 | 01A | C721 | C721 | C721 | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | 47 | E-85 | CLARK | 2021-01-13 | 2021-04-16 | 2021-08-09 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMSK8BB0MGB35343 |  | Yes |  |  | 11.23.2022
1FMSK8BB2MGB35344 | 107 | 01A | C721 | C101 | C721 | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | 4402 | E-85 | CLARK | 2021-01-13 | 2021-04-27 | 2021-09-13 |  |  |  | A | New - Nov 2022 | Las Vegas District Administration | Las Vegas | District 1 |  |  | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot | 1FMSK8BB2MGB35344 |  |  |  | 11.21.2022 | 11.21.2022
1FMSK8BB1MGC30915 | 108 | 01A | C728 | C201 | C728 | 2022 | FORD | EXPLORER | 2022 FORD EXPLORER SUV 4X4 | 7963 | FLEX FUEL | WASHOE | 2021-04-15 | 2021-12-02 | 2022-06-08 |  |  |  | A | New - Nov 2022 | Reno District Administration | Reno | District 2 |  |  | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1C4RJFAG8MC615273 | 109 | 01A | C723 | C723 | C723 | 2021 | JEEP | CHEROKEE | 2021 JEEP GRAND CHEROKEE | 6824 | UNLEADED | ELKO | 2021-05-07 | 2021-05-13 | 2022-01-27 |  |  |  | A | New - Nov 2022 | Elko District Repair Shop | Elko | District 3 |  |  | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot | 1C4RJFAG8MC615273 |  |  |  |  | 11.29.2022
1FTBF2B61GEB79294 | 111 | 3 | C724 | C384 | C724 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 113184 | UNLEADED | WHITE PINE | 2015-11-03 | 2016-02-08 | 2016-06-15 |  |  | A | A |  | Eureka Maintenance Crew | Ely | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTBF2A62GEB79290 | 113 | 3 | C723 | C301 | C723 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 25779 | UNLEADED | ELKO | 2015-11-04 | 2016-03-18 | 2016-07-05 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTBF2A62GEB79290 |  |  |  |  | 11.28.2022
1FTBF2B6XGEB79293 | 114 | 3 | C723 | C332 | C723 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 113967 | UNLEADED | ELKO | 2015-11-04 | 2016-01-27 | 2016-06-15 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P86EC83517 | 115 | 3 | C767 | C767 | C767 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 147554 | BIO DIESEL | CLARK | 2005-07-01 | 2006-03-07 | 2006-05-08 |  |  | A | A |  | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMDU73WX5ZA62387 | 116 | 01A | C767 | C201 | C767 | 2005 | FORD | EXPLORER | AWD SUV | 92908 | RFG | WASHOE | 2005-07-01 | 2006-02-16 | 2006-03-23 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12206NB18524 | 120 | 5 | C723 | C918 | C723 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 150446 | UNLEADED | ELKO | 2005-07-01 | 2006-04-04 | 2006-05-25 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTRF12206NB18524 |  |  |  |  | 11.28.2022
1FTBF2B68GEB79292 | 121 | 3 | C723 | C322 | C723 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 203847 | UNLEADED | ELKO | 2015-11-04 | 2016-01-25 | 2016-03-29 |  |  | A | A |  | Contact Maintenance Crew | Wells | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P86EC83520 | 122 | 3 | C721 | C926 | C721 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 154814 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDWW36F31EA92520 | 136 | 10 | C767 | C910 | C767 | 2001 | FORD | F-350 | SURVEY UNIT | 157995 | DIESEL | WASHOE | 2000-11-17 | 2000-12-01 | 2001-01-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12296NB18523 | 137 | 5 | C724 | C319 | C724 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 172463 | UNLEADED | WHITE PINE | 2005-07-01 | 2006-04-13 | 2006-05-25 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
2GCEK13C771520741 | 139 | 5 | C727 | C056 | C727 | 2007 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 150794 | UNLEADED | CARSON CITY | 2007-08-09 | 2007-08-20 | 2007-09-07 |  |  | A | A |  | Architectural | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF14W26NB18525 | 140 | 5 | C723 | C301 | C723 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 185630 | UNLEADED | ELKO | 2005-07-01 | 2006-04-04 | 2006-05-05 |  |  | A | A |  | Elko District Administration | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTRF14W26NB18525 |  |  |  |  | 11.28.2022
1FT7W2B68GEB79296 | 141 | 3 | C723 | C912 | C723 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 103336 | UNLEADED | ELKO | 2015-11-04 | 2016-01-27 | 2016-05-13 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7W2B68GEB79296 |  |  |  |  | 11.28.2022
1FTEW1EFXGKD82754 | 142 | 5 | C724 | C382 | C724 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 61118 | UNLEADED | WHITE PINE | 2015-11-10 | 2016-03-18 | 2016-06-13 |  |  | A | A |  | Lund Maintenance Crew | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C80GKE99453 | 143 | 5 | C723 | C918 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 31275 | UNLEADED | ELKO | 2015-11-09 | 2016-08-08 | 2016-10-05 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1C80GKE99453 |  |  |  |  | 11.28.2022
#N/A | 146 | 3 | C721 | C101 | #N/A | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 248946 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Las Vegas District Administration | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Deleted |  | #N/A
1G1ZG57B08F188821 | 148 | 1 | C767 | C767 | C767 | 2008 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 118944 | UNLEADED | CARSON CITY | 2007-07-25 | 2008-02-11 | 2008-03-05 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1FTMF1C50KKE52308 | 151 | 5 | C721 | C906 | C721 | 2019 | FORD | F-150 | 1/2 TON PICK UP | 20372 | E-85 | CLARK | 2019-04-17 | 2019-08-14 | 2020-06-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRW14W56FA97549 | 152 | 5 | C767 | C767 | C767 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 191212 | UNLEADED | HUMBOLDT | 2005-07-01 | 2006-04-13 | 2006-04-28 |  |  | A | A |  | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BH9LGA94116 | 153 | 01A | C721 | C914 | C721 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | 7944 | E-85 | CLARK | 2019-06-11 | 2019-10-22 | 2020-01-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C81GKD46807 | 154 | 5 | C723 | C301 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 38431 | UNLEADED | ELKO | 2015-11-09 | 2016-02-08 | 2016-06-15 |  |  | A | A |  | Elko District Administration | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1C81GKD46807 |  |  |  |  | 11.29.2022
1C4RJFAG3JC309724 | 155 | 01A | C727 | C030 | C727 | 2018 | JEEP | CHEROKEE | SUV 4X4 | 21960 | UNLEADED | CARSON CITY | 2017-12-06 | 2018-03-08 | 2018-04-24 |  |  | A | A |  | Right of Way Administration | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4GT5GEC57848 | 156 | 11E | C723 | C332 | C723 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 78233 | DIESEL | ELKO | 2016-02-08 | 2016-07-07 | 2016-08-16 | BUNCHER | BUNCHER | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot |  | #N/A | [5 empty] | 11/16/2022: In an internal meeting with Billie, chose this vehicle for pre-pilot to replace 1872. This vehicle can be brought to Elko during installations.
1FDXW46F41EA92519 | 157 | 11H | C721 | C122 | C721 | 2001 | FORD | F-450 | REBUILD FLATRACK TRUCK | 333033 | DIESEL | LINCOLN | 2000-09-07 | 2000-11-22 | 2014-05-01 |  |  | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF47F51EA80121 | 160 | 11H | C726 | C341 | C726 | 2001 | FORD | F-450 | FLAT RACK TRUCK | 210782 | DIESEL | HUMBOLDT | 2000-10-12 | 2000-12-18 | 2001-02-01 |  |  | A | A |  | Winnemucca Striping Crew | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | DEICING UNIT,325 GALLON DE-ICING UNIT | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDUF4GT3GEC57847 | 162 | 11E | C723 | C351 | C723 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 59369 | DIESEL | ELKO | 2016-02-09 | 2016-12-02 | 2017-03-16 | BUNCHER | BUNCHER | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDUF4GT3GEC57847 |  | Yes |  |  | 11.28.2022
1FDXF46F51EA81724 | 163 | 11H | C721 | C113 | C721 | 2001 | FORD | F-450 | FLAT RACK TRUCK | 205198 | DIESEL | CLARK | 2000-08-28 | 2001-04-25 | 2001-06-29 | TOMMY |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FVABPAK01HJ04289 | 164 | 11A | C724 | C724 | C724 | 2001 | FREIGHTLNR | 25K GVW | AERIAL LIFT TRUCK | 36861 | DIESEL | HUMBOLDT | 2000-08-30 | 2001-06-27 | 2001-08-08 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4GT1GEC57846 | 166 | 11E | C723 | C336 | C723 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 148255 | DIESEL | ELKO | 2016-02-09 | 2016-07-07 | 2016-08-29 | BUNCHER | BUNCHER | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPTL70XXHD414989 | 167 | 13 | C723 | C327 | C723 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 62885 | DIESEL | ELKO | 2016-02-08 | 2016-05-23 | 2017-08-16 | PARKER | CERTIFIED POWER | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot |  |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1NPTL70X6HD414990 | 170 | 13 | C723 | C331 | C723 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 64356 | DIESEL | ELKO | 2016-02-08 | 2016-05-23 | 2017-08-03 | PARKER | CERTIFIED POWER | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,REVERSIBLE PLOW,2018 HENKE NOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes | Yes
1NPTL70X8HD414991 | 172 | 13 | C723 | C324 | C723 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 54222 | DIESEL | ELKO | 2016-02-08 | 2016-05-23 | 2017-09-07 | PARKER | CERTIFIED POWER | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | REVERSIBLE PLOW,8 CU YD HENDERSON,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTSF20R38ED08361 | 174 | 3 | C721 | C813 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 179750 | BIO DIESEL | CLARK | 2007-09-19 | 2008-02-21 | 2008-05-05 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FAFP13P9WW280839 | 185 | 1 | C721 | C721 | C721 | 1998 | FORD | ESCORT | 4 DOOR SEDAN | 98121 | UNLEADED | CLARK | 1998-08-18 | 1998-10-13 | 1998-10-13 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1FAFP13P9WW280839 |  |  |  |  | 11.22.2022
1G11A5SA4GU128015 | 186 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 39503 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-15 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1FDWF37F71EB64141 | 188 | 11F | C722 | C722 | C722 | 2001 | FORD | F-350 | 4X4 SERVICE TRUCK | 292363 | DIESEL | CARSON CITY | 2000-11-15 | 2001-03-27 | 2001-05-09 |  |  | A | A |  | Carson City District Repair Shop | Carson City | District 2 |  | No | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSX21R08ED08359 | 189 | 3 | C728 | C728 | C767 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | 278322 | DIESEL | LYON | 2007-09-19 | 2008-02-20 | 2008-04-02 |  |  | A | D |  | Fallon District Repair Shop | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
2742-420 | 191 | 42 | C722 | C271 | C722 | 2020 | KODIAK | 1200 | 2020 KODIAK ROTARY BLOWER | 3 | DIESEL | WASHOE | 2019-10-30 | 2021-01-28 | 2021-01-28 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Full Project |  | #N/A
1FDWF37F91EB64142 | 192 | 11J | C722 | C050 | C722 | 2001 | FORD | F-350 | 4X4 UTILITY TRUCK | 226323 | DIESEL | WASHOE | 2000-11-15 | 2001-04-03 | 2001-05-17 |  |  | A | A |  | Maintenance and Asset Mgmt | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G11A5SA2GU127641 | 193 | 1 | C767 | C767 | C767 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 39170 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-10 | 2016-01-06 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A |  | Yes
1HTGEAER41H388868 | 194 | 12 | C723 | C331 | C723 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 299655 | DIESEL | ELKO | 2000-09-19 | 2001-04-25 | 2001-05-23 |  |  | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE 11 FT REVERSABLE,FLINK | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
1HTGEAER21H388867 | 196 | 12 | C723 | C350 | C723 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 153364 | DIESEL | ELKO | 2000-09-19 | 2001-04-24 | 2001-06-29 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE,2001 SANDER 5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
#N/A | 198 | 3 | C767 | C767 | #N/A | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 233574 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
1G11A5SA3GU128233 | 200 | 1 | C767 | C767 | C767 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 43900 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-15 | 2016-01-06 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A |  | Yes
1FTSX21R98ED08358 | 205 | 3 | C728 | C201 | C728 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | 292009 | DIESEL | CHURCHILL | 2007-09-19 | 2008-02-13 | 2008-03-20 |  |  | D | D |  | Reno District Administration | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET61H388845 | 206 | 13 | C722 | C270 | C722 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | 228008 | DIESEL | CARSON CITY | 2000-09-25 | 2001-08-10 | 2001-08-24 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,HEAVY DUTY PATROL WING,WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1G11A5SA3GU128698 | 209 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 36024 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-16 | 2016-03-15 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G1ZC5ST2JF187087 | 210 | 1 | C721 | C721 | C721 | 2018 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 8142 | E-85 | CLARK | 2017-12-07 | 2018-03-20 | 2018-04-04 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZC5ST2JF187087 |  | Yes |  |  | 11.22.2022
1G11A5SA6GU128825 | 214 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 39529 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-10 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G11A5SA8GU127515 | 216 | 1 | C767 | C767 | C767 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 40538 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-15 | 2016-03-15 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1FTSX21R78ED08360 | 217 | 3 | C767 | C204 | C767 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 BIO-DIESEL | 231158 | BIO DIESEL | WASHOE | 2007-09-19 | 2008-02-21 | 2008-03-21 |  |  | A | A |  | Permits | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET11H388848 | 218 | 13 | C767 | C253 | C767 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | 189738 | DIESEL | WASHOE | 2000-09-25 | 2001-08-10 | 2001-08-24 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1FTSW21R78ED08362 | 219 | 3 | C722 | C271 | C722 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 215499 | DIESEL | CARSON CITY | 2007-09-19 | 2008-02-13 | 2008-04-02 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G11A5SAXGU128293 | 221 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 38885 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-10 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAETX1H388850 | 223 | 13 | C726 | C371 | C723 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 242473 | DIESEL | LANDER | 2000-09-25 | 2001-05-02 | 2001-06-13 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | WING PLOW,8 YD,REVERSIBLE PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXX47P87EA85778 | 224 | 11J | C767 | C250 | C767 | 2007 | FORD | F-450 | 4X4 UTILITY TRUCK BIO-DIESEL | 256337 | BIO DIESEL | WASHOE | 2005-07-01 | 2007-03-01 | 2007-03-30 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAET11H388851 | 226 | 13 | C725 | C171 | C725 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 221781 | DIESEL | NYE | 2000-09-25 | 2001-05-30 | 2001-07-27 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,SANDER 8 YD,WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GAZGNFGXJ1338336 | 227 | 4 | C767 | C026 | C767 | 2018 | CHEVROLET | EXPRESS | 2018 CHEV EXP 1T 15 PASS VAN | 1268 | UNLEADED | CARSON CITY | 2018-03-23 | 2018-10-08 | 2019-05-09 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R48ED09213 | 228 | 3 | C721 | C711 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 144882 | BIO DIESEL | CLARK | 2007-09-19 | 2008-01-31 | 2008-03-28 |  |  | A | A |  | Las Vegas District Stockroom | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET51H388853 | 229 | 28 | C725 | C104 | C725 | 2001 | INTL | 2574 | 2001 REBUILD INTL F2574 DISTRIBUTOR TRUCK | 1005 | DIESEL | NYE | 2001-05-17 | 2001-09-17 | 2001-10-01 |  |  | D | A |  | Tonopah Administration | Tonopah | District 1 |  | Yes | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1G11A5SA4GU127639 | 230 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 37524 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-10 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAET91H388855 | 231 | 13 | C723 | C351 | C723 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 325712 | DIESEL | ELKO | 2001-09-14 | 2001-09-25 | 2001-10-15 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVHALDE27DX75737 | 232 | 11H | C722 | C028 | C722 | 2007 | FREIGHTLNR | FLD120 | FLATRACK TRUCK | 56054 | DIESEL | CARSON CITY | 2005-07-01 | 2006-11-16 | 2008-04-23 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDAF56P87EA71475 | 233 | 11F | C721 | C721 | C721 | 2007 | FORD | F-550 | SERVICE TRUCK BIO-DIESEL | 137659 | BIO DIESEL | CLARK | 2005-07-01 | 2007-02-07 | 2007-02-14 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FDAF56P87EA71475 |  |  | 11.21.2022 | 11.21.2022 | 11.22.2022 | 11/18/2022: Moving this vehicle back to Pre-Pilot based on the request received from George Poirier of District 1 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
2743-0720 | 234 | 42 | C767 | C250 | C767 | 2020 | KODIAK | 1200 | ROTARY SNOW BLOWER | 19 | DIESEL | WASHOE | 2019-05-29 | 2020-04-28 | 2021-01-28 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
2744-0920 | 235 | 42 | C767 | C250 | C767 | 2019 | KODIAK | CR1200S | ROTARY PLOW | 91 | DIESEL | WASHOE | 2019-05-29 | 2020-11-05 | 2021-11-17 | LINDE | SUN SOURCE |  | A | New - Nov 2022 | Reno Maintenance Crew 1 | Reno | District 2 |  |  | OFF ROAD / NA | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAET01H388856 | 236 | 13 | C725 | C172 | C725 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 334892 | DIESEL | NYE | 2001-05-17 | 2001-08-15 | 2001-09-10 |  |  | A | A |  | Big Smokey Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK 7532,WING PLOW,HENKE 12' RIGHTHAND,2014 VARITECH AI-1850 BRINE TANK | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GDE4E3256F422920 | 237 | 11A | C725 | C143 | C725 | 2006 | GMC | SIERRA | SIGNSHOP TRUCK | 284164 | DIESEL | NYE | 2005-07-01 | 2006-05-02 | 2006-08-21 |  |  | A | A |  | Tonopah Striping Crew 1 | Tonopah | District 1 |  | Yes | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX47P27EA85775 | 238 | 11E | C722 | C270 | C722 | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | 260856 | DIESEL | CARSON CITY | 2005-07-01 | 2007-03-06 | 2007-03-30 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDAW57R58EB35232 | 239 | 11A | C767 | C240 | C767 | 2008 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | 147473 | DIESEL | WASHOE | 2005-07-01 | 2007-08-09 | 2007-09-07 |  |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G11A5SA2GU125596 | 240 | 1 | C767 | C767 | C767 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 39142 | UNLEADED | CARSON CITY | 2015-10-02 | 2015-12-04 | 2016-03-07 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1FVHALDE37DX59157 | 241 | 11B | C721 | C113 | C721 | 2007 | FREIGHTLNR | FDL120 | CRANE TRUCK W/FLATBED | 81367 | DIESEL | CLARK | 2005-07-01 | 2007-02-07 | 2007-04-12 | SUNFAB | PARKER | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 6 | J1939 | [5 empty] | ATTENUATOR W/VERTICAL LIFT ARROW BOARD | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A |  | Yes
#N/A | 242 | 3 | C767 | C250 | #N/A | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL W/4X4 | 176365 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Reno Maintenance Crew 1 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
2745-1220 | 243 | 42 | C722 | C271 | C722 | 2019 | KODIAK | CR1200S | 2019 KODIAK ROTARY PLOW | 25 | DIESEL | CARSON CITY | 2019-05-29 | 2021-01-13 | 2022-10-11 | LINDE | SUN SOURCE |  | A | New - Nov 2022 | Carson City Maintenance Crew 2 | Carson City | District 2 |  |  | OFF ROAD / NA | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
#N/A | 244 | 13 | C767 | C767 | #N/A | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 251632 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1988 SANDER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Blank - 1/24/2023 |  | #N/A
1G11A5SA9GU128432 | 245 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 36925 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-15 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAETX1H388864 | 246 | 13 | C724 | C385 | C724 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 338425 | DIESEL | LANDER | 2000-09-25 | 2001-03-29 | 2001-05-09 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | ONE WAY PLOW,SANDER,DE-ICING SPRAYER,HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET21H388860 | 248 | 13 | C723 | C327 | C723 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 323078 | DIESEL | ELKO | 2000-09-25 | 2001-05-02 | 2001-06-13 |  |  | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,FLINK 8 YD SANDER,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot |  |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
#N/A | 250 | 13 | C767 | C767 | #N/A | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 297192 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Blank - 1/24/2023 |  | #N/A
1HTGGAET61H388862 | 251 | 13 | C721 | C124 | C721 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 207083 | DIESEL | CLARK | 2000-09-25 | 2001-08-15 | 2001-09-12 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,SANDER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET81H388863 | 254 | 13 | C728 | C280 | C728 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 156424 | DIESEL | CHURCHILL | 2000-09-25 | 2001-06-15 | 2001-08-06 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK 8 YD SANDER,JENSEN SNOW PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 255 | 3 | C767 | C241 | #N/A | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | 265968 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Reno Striping Crew 2 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  |  | PROGRAMMABLE MESSAGE SIGN,2014 LITE READER 1030F-4 | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
1HTGGAET31H388849 | 256 | 13 | C725 | C170 | C725 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 246575 | DIESEL | NYE | 2000-09-25 | 2001-04-12 | 2001-05-14 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE 4422,FLINK 7511,WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1G11A5SA6GU127819 | 257 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 35648 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-10 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G11A5SA8GU128485 | 258 | 1 | C723 | C723 | C723 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 31820 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-15 | 2016-01-06 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G11A5SA8GU128485 |  |  |  |  | 11.28.2022
1GAWGEFG3J1340514 | 259 | 4 | C767 | C026 | C767 | 2018 | CHEVROLET | EXPRESS | 2018 3/4 TON VAN 12 PASSENGER | 41825 | UNLEADED | CARSON CITY | 2018-03-13 | 2018-10-08 | 2019-03-28 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTNF21528ED09221 | 260 | 3 | C723 | C340 | C723 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | 123622 | UNLEADED | ELKO | 2007-09-19 | 2008-02-21 | 2008-04-28 |  |  | A | A |  | Elko Striping Crew | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTNF21528ED09221 |  |  |  |  | 11.29.2022
1GCRCNEH7JZ256806 | 261 | 5 | C721 | C101 | C721 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 85322 | E-85 | CLARK | 2017-12-13 | 2018-03-19 | 2018-04-04 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCRCNEH7JZ256806 |  |  | 11.21.2022 | 11.21.2022 | 11.22.2022
2747-0521 | 262 | 42 | C767 | C250 | C767 | 2019 | KODIAK | CR1200S | 2019 KODIAK 1200 SNOW BLOWER | 13 |  | 0 | 2019-05-29 | 2021-05-13 | 2021-11-17 | LINDE | SUN SOURCE |  | A | New - Nov 2022 | Reno Maintenance Crew 1 | Reno | District 2 |  |  | OFF ROAD / NA | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAETX1H388847 | 263 | 13 | C767 | C234 | C767 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 174546 | DIESEL | STOREY | 2000-09-25 | 2001-03-26 | 2001-07-11 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE,FLINK | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1G11A5SA5GU128315 | 264 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 32984 | UNLEADED | CARSON CITY | 2015-10-06 | 2015-12-15 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAET71H388854 | 265 | 13 | C724 | C382 | C724 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 399964 | DIESEL | WHITE PINE | 2000-09-25 | 2001-04-24 | 2001-06-11 |  |  | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW WING,ONE WAY,8 YD | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET42H404798 | 266 | 13S | C721 | C129 | C721 | 2002 | INTL | 2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 160392 | DIESEL | CLARK | 2001-09-14 | 2001-12-20 | 2002-02-08 |  |  | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER SWAPLOADER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXGAETX1J017034 | 267 | 15 | C767 | C250 | C767 | 2001 | INTL | F5000 | AWD TANDEM AXLE DUMP TRUCK | 162014 | DIESEL | WASHOE | 2000-07-10 | 2001-11-07 | 2002-02-08 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 6 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE ONE WAY PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R68ED09214 | 268 | 3 | C721 | C721 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 66248 | BIO DIESEL | CLARK | 2007-09-19 | 2008-02-25 | 2008-03-28 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
#N/A | 269 | 1 | C721 | C721 | #N/A | 1998 | FORD | ESCORT | 4 DOOR SEDAN | 110713 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Deleted |  | #N/A
1FVAB3BV61HH63563 | 271 | 24 | C726 | C370 | C726 | 2001 | WITTKE | WIZARD FC-70 | SELF PROPELLED ROAD BROOM | 76989 | DIESEL | LANDER | 2000-08-31 | 2000-12-08 | 2001-02-13 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 5 | J1939 | [5 empty] | BUCKET, 71 DITCH CLEANING | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1G11A5SAXGU124891 | 273 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 32558 | UNLEADED | CARSON CITY | 2015-10-02 | 2015-12-07 | 2016-01-06 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
IFTRF12288KD44556 | 274 | 5 | C723 | C908 | C723 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 194472 | UNLEADED | ELKO | 2007-06-28 | 2008-03-18 | 2008-04-28 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | #N/A |  |  |  |  | 11.28.2022
1FM5K8B89GGB75975 | 276 | 01A | C727 | C040 | C727 | 2016 | FORD | EXPLORER | SUV 4X4 | 31356 | UNLEADED | CARSON CITY | 2015-10-29 | 2016-01-07 | 2016-02-05 |  |  | A | A |  | Construction Administration | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEC4JZ255117 | 277 | 5 | C721 | C141 | C721 | 2018 | CHEVROLET | SILVERADO | 2018 1/2 TON CHEVY SILVERADO 1500 4X4 | 77324 | E-85 | CLARK | 2017-12-13 | 2018-03-29 | 2018-04-24 |  |  | A | A |  | Las Vegas Striping Crew 2 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCVKNEC4JZ255117 |  |  |  |  | 11.22.2022
1FM5K8B8XGGB81347 | 278 | 01A | C727 | C016 | C767 | 2016 | FORD | EXPLORER | SUV 4X4 | 53377 | UNLEADED | CARSON CITY | 2015-10-29 | 2016-01-19 | 2016-03-02 |  |  | A | A |  | Traffic Operations | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX47P27EB12182 | 280 | 11E | C767 | C243 | C767 | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | 183159 | BIO DIESEL | WASHOE | 2005-07-01 | 2007-02-15 | 2007-04-19 |  |  | A | A |  | #N/A | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | TRAILER OFFICE 60' X 24',2014 SNOW DOGG SNOW PLOW KIT EX-80,2014 SALT DOGG MODEL SHIP 2000X | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46P97EA71473 | 281 | 11E | C721 | C145 | C721 | 2007 | FORD | F-450 | 1 TON DUMP TRUCK BIO-DIESEL | 133108 | BIO DIESEL | CLARK | 2005-07-01 | 2007-03-01 | 2007-04-18 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1FDXX47P67EA85777 | 285 | 11E | C722 | C270 | C722 | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | 284453 | DIESEL | CARSON CITY | 2006-07-01 | 2007-01-29 | 2007-03-09 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTRX14WX8FA84795 | 286 | 5 | C726 | C304 | C726 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | 127201 | UNLEADED | HUMBOLDT | 2007-09-19 | 2008-01-14 | 2008-02-05 |  |  | A | A |  | Winnemucca District Administration | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRCNEC6JZ253531 | 287 | 5 | C721 | C140 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 27049 | E-85 | CLARK | 2017-12-13 | 2018-04-19 | 2018-08-15 |  |  | A | A |  | Las Vegas Sign Crew 1 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII |  |  | GO9 |  |  |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1GCRCNEC6JZ253531
1FDXF46P77EA71472 | 288 | 11E | C721 | C178 | C721 | 2007 | FORD | F-450 | 1 TON DUMP TRUCK | 238773 | DIESEL | LINCOLN | 2005-07-01 | 2006-10-23 | 2006-11-28 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCVKNEC9JZ256182 | 289 | 5 | C721 | C151 | C721 | 2018 | CHEVROLET | 1500 | 2018 CHEVY 1/2 TON PICKUP TRUCK 4X4 | 70321 | E-85 | CLARK | 2017-12-13 | 2018-03-01 | 2018-09-11 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCVKNEC9JZ256182
1FDSF35P67EA42017 | 292 | 11F | C724 | C724 | C724 | 2007 | FORD | F-350 | SERVICE TRUCK 4X4 | 138104 | DIESEL | WHITE PINE | 2005-07-01 | 2006-12-11 | 2007-02-06 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 5 | OBDII | [5 empty] | 2018 REAR BUMPER CRANE | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BH7LGA94115 | 293 | 01A | C725 | C104 | C725 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | 12547 | FLEX FUEL | NYE | 2019-06-04 | 2019-10-22 | 2020-01-16 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | AWD Passenger Vehicles | Yes | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF14508KC42952 | 295 | 5 | C725 | C715 | C725 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | 60066 | UNLEADED | NYE | 2007-09-19 | 2007-12-24 | 2008-01-15 |  |  | A | A |  | Tonopah District Stockroom | Tonopah | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X17D654450 | 297 | 13S | C725 | C171 | C725 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 148009 | DIESEL | NYE | 2005-07-01 | 2007-01-18 | 2007-01-25 | PARKER | PARKER | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | WATER TANK SWAPLOADER,PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,FLAT RACK, SWAPLOADER,2014 LITE READER 1230F-4,TRUCK MOUNTED ATTENUATOR | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FT7X2A63GED29393 | 298 | 3 | C767 | C767 | C727 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 50719 | RFG | WASHOE | 2016-02-23 | 2016-08-17 | 2016-09-14 |  |  | A | A |  | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R88ED09215 | 299 | 3 | C721 | C916 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 77995 | BIO DIESEL | CLARK | 2007-09-19 | 2008-03-06 | 2008-03-25 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRCNEC6JZ253786 | 300 | 5 | C721 | C101 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 51558 | E-85 | CLARK | 2017-12-13 | 2018-04-11 | 2018-08-28 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCRCNEC6JZ253786 |  |  |  |  | 11.22.2022
5KKHAEDE16PW97776 | 301 | 13 | C726 | C371 | C726 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 213836 | DIESEL | LANDER | 2005-07-01 | 2006-06-30 | 2006-08-01 | PARKER | PARKER | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X37D654451 | 304 | 13S | C725 | C177 | C725 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 148300 | DIESEL | MINERAL | 2005-07-01 | 2007-01-31 | 2007-02-14 | PARKER | PARKER | A | A |  | Montgomery Pass Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E87GFB30161 | 305 | 5 | C727 | C017 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 68282 | UNLEADED | CARSON CITY | 2015-11-09 | 2016-04-13 | 2016-08-16 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X87D654445 | 309 | 13 | C728 | C283 | C728 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 212595 | DIESEL | PERSHING | 2005-07-01 | 2006-12-06 | 2006-12-12 | PARKER | PARKER | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EFXGKD82766 | 310 | 5 | C725 | C173 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 117486 | UNLEADED | NYE | 2015-11-09 | 2016-04-13 | 2016-06-03 |  |  | A | A |  | Blue Jay Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE16PW45953 | 311 | 13S | C721 | C153 | C721 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 144202 | DIESEL | CLARK | 2005-07-01 | 2006-04-28 | 2006-06-06 | PARKER | PARKER | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | DUMP BODY SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E80GFB30163 | 314 | 5 | C722 | C017 | C722 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 56486 | UNLEADED | CARSON CITY | 2015-11-17 | 2016-04-22 | 2016-08-30 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 315 | 3 | C767 | C767 | #N/A | 1987 | CHEVROLET | CR209 | 3/4 TON PICKUP TRUCK | 86137 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
5KKHAEDE86PW97774 | 317 | 13S | C721 | C124 | C721 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 212593 | DIESEL | CLARK | 2005-07-01 | 2006-07-13 | 2006-08-01 | PARKER | PARKER | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTRF12W18KC46892 | 318 | 5 | C726 | C920 | C726 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 152701 | UNLEADED | HUMBOLDT | 2007-09-19 | 2008-01-15 | 2008-02-05 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X17D655761 | 319 | 13S | C720 | C150 | C720 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 126361 | DIESEL | CLARK | 2005-07-01 | 2007-02-06 | 2007-03-25 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | DUMP BODY SWAPLOADER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTRX14W88FA84794 | 320 | 5 | C726 | C036 | C726 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | 122568 | UNLEADED | HUMBOLDT | 2007-09-19 | 2008-01-14 | 2008-02-05 |  |  | A | A |  | Right of Way Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R38ED09218 | 321 | 3 | C721 | C721 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 97816 | BIO DIESEL | CLARK | 2007-09-19 | 2008-02-20 | 2008-03-06 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSF20R38ED09218 |  |  |  |  | 11.22.2022
5KKHAEDE66PW97773 | 322 | 13S | C721 | C124 | C721 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 164250 | DIESEL | CLARK | 2005-07-01 | 2006-07-10 | 2006-07-31 | PARKER | PARKER | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09XX7D654446 | 323 | 13 | C767 | C225 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 123334 | DIESEL | STOREY | 2005-07-01 | 2006-10-31 | 2006-11-29 | PARKER | PARKER | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1FTSF20R18ED09217 | 324 | 3 | C721 | C040 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 80728 | BIO DIESEL | CLARK | 2007-09-19 | 2008-02-13 | 2008-03-25 |  |  | A | A |  | Construction Administration | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  |  | 2014 PROFILING SYSTEM | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRCNEC9JZ255435 | 325 | 5 | C721 | C150 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 25103 | E-85 | CLARK | 2017-12-13 | 2018-03-29 | 2018-10-09 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII |  |  | GO9 |  |  |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1GCRCNEC9JZ255435
1NPAL09X17D654447 | 327 | 13 | C722 | C235 | C722 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 193362 | DIESEL | LYON | 2005-07-01 | 2006-12-06 | 2006-12-12 | PARKER | PARKER | A | A |  | Wellington Maintenance Crew | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDEX6PW97775 | 328 | 13S | C720 | C152 | C720 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 115735 | DIESEL | CLARK | 2005-07-01 | 2006-07-10 | 2006-08-01 | PARKER | PARKER | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | DUMP BODY SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEW1EF3GKD82756 | 329 | 5 | C722 | C013 | C722 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 57589 | UNLEADED | CARSON CITY | 2015-11-10 | 2016-03-29 | 2016-05-12 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1EF1GKD82755 | 330 | 5 | C727 | C016 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | 10743 | E-85 | CARSON CITY | 2015-11-10 | 2016-03-29 | 2016-05-05 |  |  | A | A |  | Traffic Operations | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF2GKD82762 | 332 | 5 | C725 | C123 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 171937 | UNLEADED | NYE | 2015-11-09 | 2016-03-23 | 2016-05-25 |  |  | A | A |  | Beatty Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X37D654448 | 333 | 13 | C767 | C225 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 200602 | DIESEL | LYON | 2005-07-01 | 2006-11-01 | 2006-11-29 | PARKER | PARKER | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1FTRF12W48KC42951 | 335 | 5 | C723 | C918 | C723 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 134070 | UNLEADED | ELKO | 2007-09-16 | 2007-12-24 | 2008-02-12 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTRF12W48KC42951 |  |  |  |  | 11.28.2022
1FTRF12WX8KC46891 | 336 | 5 | C723 | C908 | C723 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 158639 | UNLEADED | ELKO | 2007-09-19 | 2008-01-16 | 2008-02-12 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTRF12WX8KC46891 |  |  |  |  | 11.28.2022
1NPAL09X57D654449 | 339 | 13 | C767 | C225 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 183497 | DIESEL | LYON | 2005-07-01 | 2006-11-09 | 2007-02-08 | PARKER | PARKER | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
5KKHAEDE06PW97770 | 340 | 13 | C724 | C380 | C724 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 236160 | DIESEL | WHITE PINE | 2005-07-01 | 2006-04-19 | 2006-05-05 | PARKER | PARKER | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,PLOW WING,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEF7LZ137147 | 341 | 5 | C721 | C914 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 3069 | E-85 | CLARK | 2019-06-06 | 2019-10-16 | 2020-04-09 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE26PW97768 | 342 | 13 | C726 | C374 | C726 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 115005 | DIESEL | HUMBOLDT | 2005-07-01 | 2006-06-27 | 2006-07-08 | PARKER | PARKER | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 8 YD SANDER,PLOW,2006 HENKE PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E85HFA27807 | 345 | 5 | C727 | C017 | C727 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 46051 | FLEX FUEL | CARSON CITY | 2015-11-09 | 2016-11-28 | 2017-02-10 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HT3GEC74187 | 346 | 11J | C722 | C028 | C722 | 2016 | FORD | F-450 | UTILITY TRUCK 4X4 | 88174 | DIESEL | CARSON CITY | 2016-02-23 | 2016-06-16 | 2016-09-21 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCRCNEHXJZ256721 | 347 | 5 | C720 | C901 | C720 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | 16622 | E-85 | CLARK | 2017-12-05 | 2018-04-24 | 2018-04-24 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X5HY4GEA60021 | 348 | 11J | C722 | C028 | C722 | 2016 | FORD | F-550 | UTILITY TRUCK 4X4 | 77959 | UNLEADED | CARSON CITY | 2016-02-22 | 2016-03-08 | 2016-07-13 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20RX8ED09216 | 349 | 3 | C721 | C903 | C721 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 100015 | BIO DIESEL | CLARK | 2007-09-19 | 2008-02-05 | 2008-03-04 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH2JZ263595 | 350 | 5 | C721 | C902 | C721 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 14901 | E-85 | CLARK | 2017-12-05 | 2018-04-11 | 2018-05-10 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12W28KC42950 | 352 | 5 | C724 | C714 | C724 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 38896 | UNLEADED | WHITE PINE | 2007-09-19 | 2007-12-24 | 2008-01-17 |  |  | A | A |  | Ely District Stockroom | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT2HHHT9495 | 366 | 24 | C720 | C154 | C720 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 31377 | DIESEL | CLARK | 2015-10-08 | 2016-11-14 | 2016-11-28 |  | PARKER | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT2HHHT9495
1FVACXDT4HHHT9496 | 367 | 24 | C720 | C154 | C720 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 35391 | DIESEL | CLARK | 2015-10-08 | 2016-11-17 | 2016-12-13 |  | PARKER | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT4HHHT9496
1FVACXDT6HHHT9497 | 368 | 24 | C725 | C170 | C725 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 5225 | DIESEL | NYE | 2015-10-08 | 2017-01-06 | 2017-01-17 |  | PARKER | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1NPCLJ0X2HD411534 | 370 | 20 | C767 | C279 | C767 | 2016 | PETERBILT | 567 | CULVERT CLEANER | 29399 | DIESEL | WASHOE | 2015-11-12 | 2016-07-07 | 2016-07-11 | DANFOSS | #3: 35VQH30A-1A3R | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
#N/A | 375 | 14 | C767 | C767 | #N/A | 1993 | KENW | T800 | KENWORTH T800 REBUILD | 49110 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1FMNE31FX1HA97198 | 377 | 76 | C767 | C026 | C767 | 2001 | FORD | E-350 | 1 TON VAN W/FALLING WEIGHT DEFLECT | 59975 | DIESEL | CARSON CITY | 2000-12-13 | 2001-06-15 | 2001-11-26 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTEX1EF0GKD82758 | 383 | 5 | C721 | C179 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 130638 | E-85 | CLARK | 2015-11-09 | 2016-03-23 | 2016-05-08 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTEX1EF0GKD82758 |  |  |  |  | 11.22.2022 | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FTEX1EF6GKD82764 | 385 | 5 | C725 | C169 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 95567 | UNLEADED | NYE | 2015-11-09 | 2016-04-13 | 2016-05-18 |  |  | A | A |  | Tonopah Storm Water Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF2GKD82759 | 386 | 5 | C721 | C179 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | 27742 | E-85 | CLARK | 2015-11-09 | 2016-04-13 | 2016-05-25 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCEH2JZ263905 | 387 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | 40774 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-03-29 | 2018-09-06 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH5JZ260819 | 389 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | 43254 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-03-19 | 2018-04-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT76J335415 | 390 | 25 | C728 | C236 | C728 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | 70321 | DIESEL | CARSON CITY | 2005-07-01 | 2006-06-26 | 2006-06-27 |  |  | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF7GKD82773 | 391 | 5 | C721 | C179 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | 17176 | E-85 | CLARK | 2015-11-09 | 2016-04-13 | 2016-06-08 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R08ED09225 | 392 | 3 | C720 | C127 | C720 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 212386 | BIO DIESEL | CLARK | 2007-09-19 | 2008-02-26 | 2008-04-02 |  |  | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New |  | #N/A | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1HTXRSBT96J335416 | 393 | 25 | C767 | C253 | C767 | 2006 | INTL | 5900I | 2006 WATER TRUCK | 38851 | DIESEL | WASHOE | 2005-07-01 | 2006-06-30 | 2006-07-20 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Pilot |  | #N/A
1HTXRSBT76J309025 | 394 | 25 | C722 | C272 | C722 | 2007 | INTL | 5900I | TRUCK W/WATER TANK | 76643 | DIESEL | CARSON CITY | 2005-07-01 | 2006-10-19 | 2006-10-19 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT46J335419 | 395 | 25 | C728 | C281 | C728 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | 77137 | DIESEL | CHURCHILL | 2005-07-01 | 2006-04-16 | 2006-06-12 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT06J335417 | 396 | 25 | C720 | C150 | C720 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | 97930 | DIESEL | CLARK | 2005-10-18 | 2006-05-05 | 2006-06-28 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTFW1EF2GKD82753 | 399 | 5 | C721 | C179 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | 79178 | E-85 | CLARK | 2015-11-10 | 2016-04-14 | 2016-06-08 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTFW1EF2GKD82753 | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FTFW1EF7GKD82750 | 400 | 5 | C721 | C179 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | 26924 | E-85 | CLARK | 2015-11-10 | 2016-04-14 | 2016-05-09 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ND52JX2M594775 | 401 | 1 | C721 | C031 | C721 | 2002 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 68619 | UNLEADED | CLARK | 2001-10-25 | 2001-12-21 | 2002-01-14 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ND52JX2M594775 |  |  |  |  | 11.23.2022
1FD0W4GT6GEC74026 | 402 | 11E | C721 | C179 | C721 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 104698 | BIO DIESEL | CLARK | 2016-02-25 | 2016-08-17 | 2016-09-09 | BUNCHER | BUNCHER | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 403 | 3 | C721 | C906 | #N/A | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 174565 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Deleted |  | #N/A
1C4RJFAG6JC310026 | 404 | 01A | C723 | C301 | C723 | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | 21921 | UNLEADED | ELKO | 2017-12-07 | 2018-03-08 | 2018-04-20 |  |  | A | A |  | Elko District Administration | Elko | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1C4RJFAG6JC310026 |  |  |  |  | 11.28.2022
1FDOW4GT2GEC74184 | 405 | 11E | C725 | C169 | C725 | 2016 | FORD | F-450 | DUMP TRUCK | 97594 | DIESEL | NYE | 2016-02-25 | 2016-08-03 | 2016-10-05 | BUNCHER | BUNCHER | A | A |  | Tonopah Storm Water Maintenance Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCNCNEH8JZ276772 | 406 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 27754 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-06-20 | 2018-11-14 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH4JZ259645 | 407 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | 22898 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-04-19 | 2018-11-09 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH9JZ253405 | 408 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 15111 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-04-19 | 2018-11-20 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPCLJ0X4HD411535 | 409 | 20 | C721 | C179 | C721 | 2016 | PETERBILT | 567 | VACTOR 2100 CULVERT CLEANER | 35824 | DIESEL | CLARK | 2015-11-12 | 2016-06-02 | 2016-06-03 | DANFOSS | #3: 35VQH30A-1A3R | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTSF20R78ED09223 | 412 | 3 | C727 | C040 | C727 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 87223 | BIO DIESEL | CARSON CITY | 2007-09-19 | 2008-02-25 | 2008-03-06 |  |  | A | A |  | Construction Administration | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4PJMCXXKD168350 | 415 | 01A | C721 | C052 | C721 | 2018 | JEEP | CHEROKEE | SUV 4X4 | 7909 | UNLEADED | CARSON CITY | 2017-12-07 | 2018-04-16 | 2018-06-21 |  |  | A | A |  | External Civil Rights | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH2JZ253505 | 417 | 5 | C721 | C906 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 32678 | E-85 | CLARK | 2017-12-08 | 2018-04-11 | 2018-07-17 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT1GHHT9485 | 420 | 24 | C723 | C351 | C723 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 6428 | DIESEL | ELKO | 2015-10-08 | 2016-06-27 | 2016-07-08 |  | PARKER | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 421 | 3 | C727 | C040 | #N/A | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 151693 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Construction Administration | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
1GCFC24MXWE217383 | 422 | 3 | C727 | A073 | C727 | 1998 | CHEVROLET | CC209 | 3/4 TON PICKUP TRUCK W/SVC BODY | 98736 | UNLEADED | CARSON CITY | 1998-04-28 | 1998-11-20 | 1998-11-20 |  |  | A | A |  | Building & Grounds | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEF2LZ138982 | 423 | 5 | C721 | C915 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 11818 | E-85 | CLARK | 2019-06-06 | 2019-10-16 | 2020-04-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTHG35R1X1161677 | 425 | 4 | C767 | C242 | C767 | 1999 | GMC | TG3140 | 1 TON CARGO VAN | 144989 | RFG | WASHOE | 1999-07-26 | 1999-07-26 | 1999-07-26 |  |  | A | A |  | Reno Pavement Markings | Reno | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GCRYAEF8LZ137366 | 426 | 5 | C721 | C902 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 18167 | E-85 | CLARK | 2019-06-06 | 2019-10-18 | 2020-04-22 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT5GHHT9487 | 428 | 24 | C723 | C350 | C723 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 11227 | DIESEL | ELKO | 2015-10-08 | 2016-07-19 | 2016-07-22 |  | PARKER | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12W38KC46893 | 429 | 5 | C726 | C920 | C726 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 147843 | UNLEADED | HUMBOLDT | 2007-09-19 | 2008-01-16 | 2008-09-08 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT3GHHT9486 | 430 | 24 | C723 | C332 | C723 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 7943 | DIESEL | ELKO | 2015-10-08 | 2016-07-19 | 2016-07-19 |  | PARKER | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B69KEG52776 | 431 | 3 | C767 | C251 | C767 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | 24832 | FLEX FUEL | WASHOE | 2019-06-05 | 2019-10-22 | 2020-01-29 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTNF21F42EB83928 | 436 | 3 | C726 | C341 | C726 | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | 187227 | DIESEL | HUMBOLDT | 2001-10-17 | 2002-01-30 | 2002-01-30 |  |  | A | A |  | Winnemucca Striping Crew | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GAGG25R2X1048254 | 437 | 4 | C767 | C767 | C767 | 1999 | CHEVROLET | CG21406 | 12 PASSENGER VAN | 55257 | RFG | WASHOE | 1998-11-16 | 1998-11-16 | 1998-11-16 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Vans | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1M2K163C6JM001450 | 438 | 77 | C725 | C143 | C725 | 1988 | MACK | MR688 | MACK STRIPER REBUILD | 98624 | DIESEL | NYE | 1988-07-22 | 1988-07-22 | 2012-05-30 |  |  | A | A |  | Tonopah Striping Crew 1 | Tonopah | District 1 |  | Yes | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTWX31Y68ED08364 | 439 | 6 | C724 | C724 | C724 | 2008 | FORD | F-350 | ONE TON PICKUP TRUCK W/4X4 | 113622 | UNLEADED | WHITE PINE | 2007-09-17 | 2008-02-20 | 2008-07-29 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GJGG25R621178286 | 442 | 4 | C723 | C723 | C723 | 2002 | GMC | SAVANA | PASSENGER VAN | 97723 | UNLEADED | ELKO | 2001-10-17 | 2002-03-07 | 2002-03-07 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GJGG25R621178286 |  | Yes |  |  | 11.28.2022
1FTEX1EF5GKD82772 | 443 | 5 | C767 | C279 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 143495 | RFG | WASHOE | 2015-11-09 | 2016-04-13 | 2016-05-25 |  |  | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF4GKD82763 | 444 | 5 | C767 | C018 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 38740 | UNLEADED | WASHOE | 2015-11-09 | 2016-03-23 | 2016-06-23 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF0GKD82761 | 450 | 5 | C767 | C218 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 20843 | RFG | WASHOE | 2015-11-17 | 2016-04-19 | 2016-05-25 |  |  | A | A |  | Reno Storm Water Inspection Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT0GEC74183 | 451 | 11E | C767 | C279 | C767 | 2016 | FORD | F-450 | DUMP TRUCK | 76961 | DIESEL | WASHOE | 2016-02-25 | 2016-07-25 | 2017-01-24 | BUNCHER | BUNCHER | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPCLJ0X6HD411536 | 452 | 20 | C725 | C169 | C725 | 2016 | PETERBILT | 567 | CULVERT CLEANER | 28290 | DIESEL | CLARK | 2015-11-12 | 2016-06-17 | 2016-07-11 | DANFOSS | #3: 35VQH30A-1A3R | A | A |  | Tonopah Storm Water Maintenance Crew | Tonopah | District 1 |  | Yes | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT5HHHT9488 | 453 | 24 | C728 | C281 | C728 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 8459 | DIESEL | CHURCHILL | 2015-10-08 | 2016-08-08 | 2016-08-29 |  | PARKER | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT5HHHT9488
1FVACXDT7HHHT9489 | 456 | 24 | C767 | C279 | C767 | 2017 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 11604 | DIESEL | WASHOE | 2015-10-08 | 2016-07-25 | 2016-08-11 |  | PARKER | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT7HHHT9489 |  | Yes
5KKHAEDV9MPMG9646 | 458 | 13H | C721 | C124 | C767 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR TANDEM AXLE SIDE DUMP | 7823 | DIESEL | CLARK | 2019-10-04 | 2020-07-14 | 2020-09-23 | METARIS | PRINCE | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 8 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KKHAEDV2MPMJ3827 | 461 | 13 | C725 | C170 | C725 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 7578 | DIESEL | NYE | 2019-06-01 | 2021-01-05 | 2021-08-09 |  |  |  | A | New - Nov 2022 | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  |  | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations |  |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT3HHHT9490 | 462 | 24 | C721 | C179 | C721 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 33878 | DIESEL | CLARK | 2015-10-08 | 2016-08-08 | 2016-08-29 |  | PARKER | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
2FTPF17Z02CA35107 | 464 | 5 | C767 | C904 | C767 | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 115357 | RFG | WASHOE | 2001-11-13 | 2002-03-21 | 2002-03-21 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH8JZ262306 | 466 | 5 | C722 | C907 | C722 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 46640 | FLEX FUEL | CARSON CITY | 2017-12-08 | 2018-04-19 | 2018-07-24 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNKNEH1JZ253742 | 474 | 5 | C722 | C907 | C722 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 25839 | FLEX FUEL | CARSON CITY | 2017-12-12 | 2018-03-29 | 2018-11-29 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14T92E216636 | 475 | 5 | C727 | C040 | C727 | 2002 | GMC | 1500 | 1/2 TON PICKUP TRUCK | 120742 | UNLEADED | CARSON CITY | 2001-10-23 | 2002-03-07 | 2002-03-07 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH3JZ251813 | 480 | 5 | C722 | C907 | C722 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 17596 | FLEX FUEL | CARSON CITY | 2017-12-08 | 2018-03-01 | 2018-12-31 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF5GKD82769 | 481 | 5 | C723 | C318 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 92685 | UNLEADED | ELKO | 2015-11-17 | 2016-04-13 | 2016-05-09 |  |  | A | A |  | Elko Storm Water Inspection Crew | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1EF5GKD82769 |  |  |  |  | 11.28.2022
1GCNCNEH5JZ257483 | 482 | 5 | C767 | C910 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 12098 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-04-19 | 2018-08-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFW1EF0GKD82752 | 485 | 5 | C723 | C379 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 72821 | UNLEADED | ELKO | 2015-11-10 | 2016-04-19 | 2016-06-03 |  |  | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFW1EF0GKD82752 |  |  |  |  | 11.28.2022
1FTFW1EF9GKD82751 | 486 | 5 | C723 | C318 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 99633 | UNLEADED | ELKO | 2015-11-10 | 2016-03-29 | 2016-05-09 |  |  | A | A |  | Elko Storm Water Inspection Crew | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFW1EF9GKD82751 |  |  |  |  | 11.28.2022
1FDOW4GT4GEC74025 | 489 | 11E | C723 | C379 | C723 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 55571 | DIESEL | ELKO | 2016-02-25 | 2016-08-03 | 2016-09-15 |  |  | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | #N/A |  | Yes |  |  | 11.28.2022
1NPCLJ0X0HD411533 | 490 | 20 | C723 | C379 | C723 | 2016 | PETERBILT | 567 | CULVERT CLEANER | 10625 | DIESEL | ELKO | 2015-11-12 | 2016-06-02 | 2016-06-13 | DANFOSS | #3: 35VQH30A-1A3R | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
2006R916 | 493 | 55B | C726 | C726 | C726 | 2006 | TUCKER | 2000BXL265 | SNOW CAT | 641 | DIESEL | HUMBOLDT | 2005-07-01 | 2005-12-19 | 2006-01-26 | VICKERS | GRESEN | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A | Yes |  |  |  |  | 8/17/2022: In the internal discussion between Billie, Yesh and Priyanka it was decided that all the SnowCats should have Satellite
1FVACXDT5HHHT9491 | 494 | 24 | C721 | C179 | C721 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 28059 | DIESEL | CLARK | 2015-10-08 | 2016-08-31 | 2016-09-27 |  | PARKER | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT7HHHT9492 | 495 | 24 | C722 | C272 | C722 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 13183 | DIESEL | CARSON CITY | 2015-10-08 | 2016-09-09 | 2016-12-22 |  | PARKER | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT7HHHT9492
1FDXW47R08ED00012 | 497 | 11H | C724 | C319 | C724 | 2008 | FORD | F-450 | 1 TON FLATRACH TRUCK 4X4 | 164779 | DIESEL | WHITE PINE | 2007-05-14 | 2008-03-18 | 2008-04-08 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FVACXDT9HHHT9493 | 498 | 24 | C721 | C179 | C721 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | 26325 | DIESEL | CLARK | 2015-10-08 | 2016-10-11 | 2016-10-25 |  | PARKER | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 500 | 5 | C723 | C723 | #N/A | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 229078 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Elko District Repair Shop | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1GCNCNEH9JZ264579 | 502 | 5 | C767 | C910 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 22805 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-04-19 | 2018-12-06 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAYR9PH520978 | 503 | 12 | C726 | C371 | C726 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 161970 | DIESEL | LANDER | 1993-07-23 | 1993-07-23 | 1993-07-23 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,1993 SANDER 5 YD 10',ATTENUATOR, V/M | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FTSW21Y58ED08366 | 504 | 3 | C767 | C767 | C767 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | 205000 | UNLEADED | WASHOE | 2007-05-14 | 2008-02-20 | 2008-03-28 |  |  | A | A |  | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46R58EC84066 | 505 | 11J | C721 | C155 | C721 | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | 149406 | BIO DIESEL | CLARK | 2007-05-14 | 2008-02-06 | 2008-02-13 |  |  | A | A |  | Las Vegas Bridge Maintenance | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
3FRNF65XX8V049144 | 507 | 11H | C767 | C252 | C767 | 2008 | FORD | F-650 | FLATRACK TRUCK BIO-DIESEL | 29549 | BIO DIESEL | WASHOE | 2007-08-28 | 2008-09-16 | 2008-11-19 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAYR0PH520979 | 510 | 12 | C724 | C382 | C724 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 209225 | DIESEL | WHITE PINE | 1993-07-23 | 1993-07-23 | 1993-07-23 |  |  | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAYR2PH520983 | 512 | 12 | C728 | C201 | C728 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 213585 | DIESEL | CHURCHILL | 1993-07-23 | 1993-11-29 | 1993-11-29 |  |  | A | A |  | Reno District Administration | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A
1HTGEAYR9PH520981 | 514 | 12 | C767 | C279 | C767 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 127551 | DIESEL | WASHOE | 1993-07-23 | 1993-12-29 | 1993-12-29 |  |  | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK SANDER,CLEDHILL PLOW MDL 20931 | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
5KKHAEDVXMPMJ3834 | 515 | 13 | C725 | C173 | C725 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 3460 | DIESEL | NYE | 2019-06-01 | 2021-03-30 | 2021-08-24 |  |  |  | A | New - Nov 2022 | Blue Jay Maintenance Crew | Tonopah | District 1 |  |  | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations |  |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAYR7PH520980 | 516 | 12 | C726 | C371 | C726 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 187982 | DIESEL | LANDER | 1993-07-23 | 1993-07-23 | 1993-07-23 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH2JZ250541 | 519 | 5 | C767 | C910 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 22330 | FLEX FUEL | WASHOE | 2017-12-08 | 2018-03-07 | 2018-12-20 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT4MEC41066 | 525 | 11H | C725 | C123 | C725 | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | 11949 | DIESEL | NYE | 2020-09-27 | 2021-03-02 | 2021-11-10 |  |  |  | A | New - Nov 2022 | Beatty Maintenance Crew | Tonopah | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV2MPMJ3830 | 526 | 13 | C767 | C225 | C767 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 588 | DIESEL | WASHOE | 2019-06-01 | 2021-01-05 | 2021-07-13 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2020 HENKE SINGEL AUGER CARTRIDGE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FDXW46F62EB44475 | 531 | 11S | C721 | C142 | C721 | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | 243085 | DIESEL | CLARK | 2001-10-09 | 2002-03-04 | 2002-03-25 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 400 GAL SPRAY TANK/SLIDE-IN | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1G11A5SA9GU125448 | 532 | 1 | C727 | C018 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 7862 | UNLEADED | CARSON CITY | 2015-10-02 | 2015-12-04 | 2016-03-07 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1G11A5SA1GU125346 | 533 | 1 | C727 | C018 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 10619 | UNLEADED | CARSON CITY | 2015-10-02 | 2015-12-04 | 2016-03-07 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
1FTEX1EF9GKD82757 | 534 | 5 | C727 | C018 | C727 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 41194 | UNLEADED | CARSON CITY | 2015-11-17 | 2016-04-28 | 2016-05-18 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRCNEH1JZ253948 | 535 | 5 | C721 | C914 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 19827 | E-85 | CLARK | 2017-12-08 | 2018-04-11 | 2018-07-17 |  |  | A | A |  | Construction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCRCNEH1JZ253948 |  |  |  |  | 11.23.2022 | 11/7/2022: In a call between Yesh, Billie, and Priyanka, a decision was made to move this vehicle to Pre-Pilot phase instead of vehicle with unit number 1088.
1HTGGA6T4NH456595 | 537 | 11B | C725 | C143 | C725 | 1992 | INTL | F2574 | CRANE TRUCK W/FLATRACK | 295735 | DIESEL | NYE | 1992-06-15 | 1992-07-06 | 1992-07-06 |  |  | A | A |  | Tonopah Striping Crew 1 | Tonopah | District 1 |  | Yes | 6 | J1939 | [5 empty] | 2014 LITEREADER 1230F-4 SIGN BOARD,2007 SCORPION TL-3TRUCK MNTD. ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1HTSCPLL3NH441289 | 538 | 11H | C767 | C240 | C767 | 1992 | INTL | 4700 | FLATRACK TRUCK | 204891 | DIESEL | WASHOE | 1992-04-21 | 1992-09-29 | 1992-09-29 |  |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTEX1EF2GKD82776 | 539 | 5 | C727 | C018 | C727 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 31462 | UNLEADED | CARSON CITY | 2015-11-17 | 2016-04-22 | 2016-05-12 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH1JZ252569 | 540 | 5 | C721 | C915 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 18713 | E-85 | CLARK | 2017-12-08 | 2018-06-22 | 2018-06-22 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF9GKD82760 | 541 | 5 | C727 | C018 | C727 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 39339 | UNLEADED | CARSON CITY | 2015-11-12 | 2016-05-10 | 2016-05-18 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46R98EC84068 | 542 | 11H | C720 | C142 | C720 | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | 112830 | BIO DIESEL | CLARK | 2007-09-17 | 2008-02-20 | 2008-03-28 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1FTEX1EF1GKD82770 | 543 | 5 | C723 | C018 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 57451 | UNLEADED | ELKO | 2015-11-17 | 2016-05-12 | 2016-06-01 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 545 | 11S | C721 | C151 | #N/A | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | 257968 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Deleted |  | #N/A
1FDXW47R28EC84069 | 547 | 11H | C726 | C373 | C726 | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | 241655 | DIESEL | HUMBOLDT | 2007-09-17 | 2008-02-20 | 2008-03-27 |  |  | A | A |  | Quinn River Maintenance Crew | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | Yes
1GCNCNEH2JZ256274 | 548 | 5 | C721 | C915 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 24521 | E-85 | CLARK | 2017-12-08 | 2018-03-01 | 2018-06-21 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZS52F35F306493 | 550 | 1 | C767 | C767 | C767 | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 25344 | UNLEADED | CARSON CITY | 2005-03-28 | 2005-06-16 | 2005-07-06 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes |  |  | Full Project |  | #N/A
5KKHAEDV6MPMP4386 | 552 | 13S |  | New | C767 | 2020 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT |  |  | WASHOE | 2020-03-23 | 2021-02-23 | 2022-07-14 | DANFOSS | DANFOSS |  | A |  | #N/A | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | FORCE AMERICA |  |  |  | SANDER, REVERSIBLE PLOW, DUMP BODY | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1G11A5SA1GU124889 | 553 | 1 | C727 | C727 | C727 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 34953 | UNLEADED | CARSON CITY | 2015-10-05 | 2015-12-04 | 2016-04-15 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1FD8X3F69GEC74186 | 556 | 11F | C767 | C767 | C767 | 2016 | FORD | F-350 | SHOP SERVICE TRUCK 4X4 | 12921 | UNLEADED | WASHOE | 2016-02-08 | 2016-06-27 | 2017-04-01 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH5JZ262621 | 557 | 5 | C721 | C916 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 15683 | E-85 | CLARK | 2017-12-07 | 2018-04-19 | 2018-07-05 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX46F22EB44485 | 558 | 11E | C728 | C283 | C728 | 2002 | FORD | F-450 | DUMP TRUCK | 353197 | DIESEL | LYON | 2002-03-15 | 2002-05-10 | 2002-08-21 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEDV4MPMJ3831 | 559 | 13 | C728 | C237 | C728 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 2173 | DIESEL | WASHOE | 2019-06-01 | 2020-12-01 | 2021-07-20 |  |  | A | A |  | Hawthrone Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2020 HENKE AUGER CARTRIDGE SANDER,2020 REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT2MEC41065 | 560 | 11H | C725 | C175 | C725 | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | 10733 | DIESEL | ESMERALDA | 2020-09-27 | 2021-03-05 | 2022-03-10 |  |  |  | A | New - Nov 2022 | Goldfield Maintenance Crew | Tonopah | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEHXJZ261335 | 561 | 5 | C723 | C918 | C723 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 29682 | FLEX FUEL | ELKO | 2017-12-07 | 2018-03-27 | 2018-06-26 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCNEHXJZ261335 |  |  |  |  | 11.28.2022
1FTEX1EF1GKF34112 | 562 | 5 | C725 | C177 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 91541 | UNLEADED | NYE | 2015-12-22 | 2016-08-29 | 2016-12-23 |  |  | A | A |  | Montgomery Pass Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF3GKD82768 | 564 | 5 | C725 | C175 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 139679 | UNLEADED | NYE | 2015-12-22 | 2016-04-13 | 2016-07-05 |  |  | A | A |  | Goldfield Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F12EB44481 | 565 | 11E | C722 | C247 | C722 | 2002 | FORD | F-450 | DUMP TRUCK 4X4 | 199193 | DIESEL | CARSON CITY | 2001-09-24 | 2002-05-09 | 2002-06-03 |  |  | A | A |  | Carson City Landscape Crew 3 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | SALTDOGG SHPE2000X SANDER,SNOWDOGG EX-85 PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46F02EB44472 | 567 | 11S | C721 | C153 | C721 | 2002 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOKLIFT | 114593 | BIO DIESEL | CLARK | 2001-10-12 | 2002-03-12 | 2015-04-21 | MUNCIE |  | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | ARROW BOARD, T/M,DUMPBED SL95 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTEX1EF3GKD82771 | 568 | 5 | C725 | C176 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 80324 | UNLEADED | NYE | 2015-12-22 | 2016-04-14 | 2016-07-05 |  |  | A | A |  | Mina Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46FX2EB44480 | 569 | 11E | C767 | C767 | C767 | 2002 | FORD | F-450 | DUMP TRUCK | 313230 | DIESEL | WASHOE | 2002-03-15 | 2002-05-09 | 2002-05-30 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46R28ED23681 | 570 | 11E | C720 | C127 | C720 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 226135 | BIO DIESEL | CLARK | 2007-09-17 | 2008-03-18 | 2008-05-08 |  |  | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTEX1EF5GKF34114 | 571 | 5 | C767 | C757 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 25126 | UNLEADED | NYE | 2015-12-22 | 2016-08-26 | 2017-02-16 |  |  | A | A |  | Equipment Stockroom | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV4MPMJ3828 | 575 | 13 | C723 | C327 | C723 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 2972 | DIESEL | ELKO | 2019-06-01 | 2020-12-01 | 2021-02-04 |  |  | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | PLOW REVERSIBLE ALASKAN,2020 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot | Yes |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1GCNCNEH5JZ262277 | 577 | 5 | C721 | C926 | C721 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 34469 | E-85 | CLARK | 2017-12-07 | 2018-04-11 | 2018-07-02 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEATR32H545410 | 580 | 12 | C724 | C381 | C724 | 2002 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 60835 | DIESEL | WHITE PINE | 2001-12-04 | 2002-06-10 | 2002-07-01 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,5 CU YD SANDER W/PRE WET & GUARD,FRONT BROOM ATTACHMENT | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF0GKD82775 | 581 | 5 | C725 | C172 | C725 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 122644 | UNLEADED | NYE | 2015-12-22 | 2016-04-26 | 2016-07-05 |  |  | A | A |  | Big Smokey Maintenance Crew | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTXJAXR62J044509 | 582 | 12 | C767 | C234 | C767 | 2002 | INTL | 5500 | SINGLE AXLE DUMP TRUCK AWD | 115255 | DIESEL | STOREY | 2002-08-28 | 2003-01-09 | 2003-04-01 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE PLOW,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1HTGGAXT62H549693 | 583 | 13 | C723 | C335 | C723 | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 130520 | DIESEL | ELKO | 2001-11-15 | 2002-07-10 | 2011-11-02 |  |  | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV6MPMJ3829 | 584 | 13 | C723 | C331 | C723 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 6836 | DIESEL | ELKO | 2019-06-01 | 2020-12-01 | 2021-02-02 |  |  | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,2020 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes | Yes
1HTGGAXT93H549687 | 585 | 13 | C725 | C123 | C725 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 270526 | DIESEL | MINERAL | 2001-11-15 | 2002-07-15 | 2002-08-05 |  |  | A | A |  | Beatty Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE,FLINK SANDER,HENKE WING PLOW | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT33H549698 | 587 | 13 | C726 | C370 | C726 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 204966 | DIESEL | HUMBOLDT | 2002-08-28 | 2002-10-22 | 2002-12-04 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE REVERSIBLE,PLOW WING,FLINK SANDER | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1M2P270C13M065024 | 588 | 13 | C767 | C251 | C767 | 2003 | MACK | RD6885 | TANDEM AXLE DUMP TRUCK | 140739 | DIESEL | WASHOE | 2002-08-28 | 2002-10-08 | 2003-06-02 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1GDM7H1J1NJ521048 | 589 | 11H | C767 | C245 | C767 | 1992 | GMC | TC7H0 | FLATRACK TRUCK | 80776 | DIESEL | WASHOE | 1992-04-29 | 1992-04-29 | 1992-04-29 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT22H549691 | 590 | 13 | C725 | C170 | C725 | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 130567 | DIESEL | NYE | 2001-11-15 | 2002-07-01 | 2011-06-20 |  |  | A | D |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REV PLOW REBUILD,1850 GALLON SPRAYER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH6JG301456 | 592 | 5 | C721 | C156 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | 48618 | E-85 | CLARK | 2017-12-13 | 2018-04-11 | 2018-07-19 |  |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X9HD414983 | 593 | 13 | C723 | C327 | C723 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 51924 | DIESEL | ELKO | 2016-02-08 | 2016-05-23 | 2017-09-07 | PARKER | CERTIFIED POWER | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,REVERSIBLE PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot |  |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1M2P270C63M065021 | 594 | 13 | C728 | C236 | C728 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | 266716 | DIESEL | LYON | 2002-08-28 | 2003-01-23 | 2003-09-10 |  |  | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE PLOW,8 YRD SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GTEC14W4XZ525070 | 596 | 5 | C723 | C723 | C767 | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | 229190 | UNLEADED | ELKO | 1999-05-05 | 1999-05-05 | 1999-05-25 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
1FD0W4HT8MEC41068 | 598 | 11H | C725 | C177 | C725 | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | 692 | DIESEL | MINERAL | 2020-09-27 | 2021-03-05 | 2021-07-21 |  |  | A | A |  | Montgomery Pass Maintenance Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46R78ED58104 | 599 | 11E | C721 | C153 | C721 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 250408 | BIO DIESEL | CLARK | 2007-09-17 | 2008-04-15 | 2008-05-08 |  |  | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1M2P270C83M065022 | 600 | 13 | C767 | C767 | C724 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | 179684 | DIESEL | MINERAL | 2002-08-28 | 2002-12-18 | 2003-03-17 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 12' ONE WAY HENKE,FLINK Model #LMC5H15-NVS4E01 | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
1HTSCPLL1NH441288 | 601 | 11H | C767 | C243 | C767 | 1992 | INTL | 4700 | FLATRACK TRUCK | 223423 | DIESEL | WASHOE | 1992-04-22 | 1992-05-28 | 1992-05-28 |  |  | A | A |  | #N/A | Reno | District 2 |  | No | 5 | J1939 | [5 empty] | 2021 LITEREADER ARROW BOARD | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 603 | 5 | C721 | C915 | #N/A | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 20900 | E-85 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Deleted |  | #N/A
1GCNCNEH6JZ260196 | 604 | 5 | C767 | A070 | C727 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 9419 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-01 | 2018-04-12 |  |  | A | A |  | Administrative Services | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT6MEC41067 | 605 | 11H | C725 | C170 | C725 | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | 11462 | DIESEL | NYE | 2020-09-27 | 2021-03-09 | 2022-03-09 |  |  |  | A | New - Nov 2022 | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C81HFA35470 | 606 | 5 | C721 | C915 | C721 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 36909 | E-85 | CLARK | 2016-04-04 | 2016-12-02 | 2017-01-31 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 607 | 11E | C725 | C123 | #N/A | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | 240018 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Beatty Maintenance Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FTEW1C86GKF13506 | 608 | 5 | C721 | C926 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 52265 | E-85 | CLARK | 2016-04-04 | 2016-07-19 | 2016-08-18 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPZL00X37D717418 | 609 | 77 | C720 | C141 | C720 | 2006 | PETERBILT | 320 | LINE STRIPER TRUCK | 169674 | DIESEL | CLARK | 2005-07-01 | 2006-12-15 | 2007-01-08 | DANFOSS |  | A | A |  | Las Vegas Striping Crew 2 | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GKDT13S562248368 | 610 | 01A | C727 | C727 | C727 | 2006 | GMC | ENVOY | SUV 4X4 | 174733 | UNLEADED | CARSON CITY | 2005-07-01 | 2006-01-26 | 2006-03-02 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1M2P270C43M065020 | 611 | 13 | C767 | C767 | C723 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | 183191 | DIESEL | ELKO | 2002-08-28 | 2003-02-13 | 2003-05-19 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,HENKE,HENKE WING PLOW,WING PLOW | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
1M2P270C33M065025 | 612 | 13 | C767 | C225 | C767 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | 155876 | DIESEL | LYON | 2002-08-28 | 2003-01-23 | 2003-04-29 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE,SANDER FLINK W PREWET | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXX47R88ED58110 | 614 | 11E | C767 | C252 | C767 | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | 184836 | BIO DIESEL | WASHOE | 2007-09-19 | 2008-05-06 | 2008-06-06 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2014 SNOW DOGG SNOW PLOW EX-80,2014 SNOW DOGG SHPE 2000 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEDV6MPMJ3832 | 616 | 13 | C724 | C381 | C724 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 556 | DIESEL | WHITE PINE | 2019-06-01 | 2021-01-05 | 2021-07-14 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2020 HENKE SINGLE SANDER,2020 HENKE ONE WAY PLOW,2020 HENKE WING PLAY | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT02H549690 | 617 | 25 | C725 | C171 | C725 | 2002 | INTL | F2574 | TANDEM AXLE WATER TRUCK REBUILD | 16408 | DIESEL | CLARK | 2001-11-14 | 2002-06-14 | 2018-06-21 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT82H549730 | 618 | 13S | C720 | C126 | C720 | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | 97380 | DIESEL | CLARK | 2002-08-28 | 2002-10-31 | 2002-11-20 |  |  | A | A |  | Mountain Springs Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE REVERSIBLE,SANDER,DUMP BED | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C82GKE99454 | 620 | 5 | C721 | C926 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 39759 | E-85 | CLARK | 2016-04-04 | 2016-08-08 | 2016-09-16 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C88GKF13507 | 621 | 5 | C721 | C916 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 32277 | E-85 | CLARK | 2016-04-04 | 2016-07-19 | 2016-09-02 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 1FTEW1C88GKF13507
#N/A | 622 | 13 | C723 | C335 | #N/A | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 267701 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE WING PLOW,11 ' REV HENKE PLOW,FLINK 8 CU YD SANDER | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  |  |  | #N/A
5KKHAEDV8MPJ3833 | 623 | 13 | C726 | C726 | C726 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | 1346 | DIESEL | HUMBOLDT | 2019-06-01 | 2021-01-05 | 2021-08-18 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2020 HENKE SINGLE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT23H549689 | 625 | 13 | C725 | C176 | C725 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 251594 | DIESEL | MINERAL | 2001-11-15 | 2002-07-15 | 2002-08-05 |  |  | A | A |  | Mina Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | ONE WAY PLOW,FLINK,PLOW WING,BRINE TANK | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT53H549699 | 626 | 13 | C725 | C175 | C725 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 245963 | DIESEL | MINERAL | 2001-11-15 | 2002-08-28 | 2002-10-01 |  |  | A | A |  | Goldfield Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK 8 YD W/PRE WET SYSTEM,PLOW,WING PLOW,VARITECH A1-1750-GAS-1LB | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 627 | 11E | C725 | C175 | #N/A | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | 250079 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Goldfield Maintenance Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1M2P270CX3M065023 | 629 | 13 | C728 | C237 | C767 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | 195483 | DIESEL | WASHOE | 2002-08-28 | 2003-01-23 | 2003-05-22 |  |  | A | A |  | Hawthrone Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 12' ONE WAY PLOW,8 YRD FLINK SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXF46R88ED58113 | 631 | 11E | C721 | C124 | C721 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 205627 | BIO DIESEL | CLARK | 2007-09-17 | 2008-05-02 | 2008-06-16 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTEW1C8XGKF13508 | 632 | 5 | C721 | C903 | C721 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 49095 | E-85 | CLARK | 2016-04-04 | 2016-07-25 | 2016-08-11 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT53H549685 | 633 | 13 | C724 | C385 | C724 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 319713 | DIESEL | LANDER | 2002-08-28 | 2002-10-02 | 2002-10-09 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK 8 CU YD SANDER,WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT73H549686 | 634 | 13 | C726 | C373 | C726 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 198851 | DIESEL | HUMBOLDT | 2002-08-28 | 2002-10-07 | 2002-11-19 |  |  | A | A |  | Quinn River Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 CU YD,HENKE REVERSIBLE | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
#N/A | 635 | 11E | C728 | C237 | #N/A | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | 222014 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Hawthrone Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FD0X4HT6MED06741 | 636 | 11S | C721 | C127 | C721 | 2021 | FORD | F-450 | 2021 FORD 40450 1 TON DUMPBED SWAPLOADER | 761 | BIO DIESEL | CLARK | 2020-11-03 | 2021-07-15 | 2022-03-17 | PARKER | SWAPLOADER |  | A | New - Nov 2022 | Searchlight Maintenance Crew | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FD0X4HT6MED06741
1FTEW1EF6GKE99473 | 637 | 5 | C767 | C910 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 22688 | RFG | WASHOE | 2016-04-04 | 2016-07-25 | 2016-08-11 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 639 | 11E | C723 | C335 | #N/A | 2008 | FORD | F-450 | DUMP TRUCK | 189805 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1GCVKNEH5JZ256935 | 641 | 5 | C727 | A078 | C727 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | 4156 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-30 | 2018-12-12 |  |  | A | A |  | Human Resources - Industrial Safety | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1EF8GKE99474 | 642 | 5 | C767 | C904 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 43634 | FLEX FUEL | WASHOE | 2016-04-04 | 2016-07-18 | 2016-08-11 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1EFXGKE99475 | 644 | 5 | C767 | C911 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 57653 | UNLEADED | CARSON CITY | 2016-04-04 | 2016-07-18 | 2016-08-11 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1EF1GKE99476 | 645 | 5 | C767 | C905 | C767 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 34466 | RFG | WASHOE | 2016-04-04 | 2016-07-25 | 2016-08-30 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46RX8EC60412 | 646 | 11E | C721 | C151 | C721 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 205598 | BIO DIESEL | CLARK | 2007-09-17 | 2008-02-07 | 2008-03-06 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
#N/A | 647 | 11E | C728 | C280 | #N/A | 2008 | FORD | F-450 | DUMP TRUCK 4X4 | 196073 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FTEW1EF3GKE99477 | 648 | 5 | C722 | C907 | C722 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 25253 | UNLEADED | CARSON CITY | 2016-04-04 | 2016-07-18 | 2016-09-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46R08ED58106 | 650 | 11E | C720 | C154 | C720 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 211024 | BIO DIESEL | CLARK | 2007-09-17 | 2008-05-15 | 2008-09-04 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46R28ED58107 | 652 | 11E | C720 | C126 | C720 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 168684 | BIO DIESEL | CLARK | 2007-09-17 | 2008-05-16 | 2008-06-18 |  |  | A | A |  | Mountain Springs Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | HINKER C-PLOW 8802 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46R48ED58108 | 653 | 11E | C721 | C151 | C721 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 233603 | BIO DIESEL | CLARK | 2007-09-17 | 2008-05-09 | 2008-06-16 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | ARROW BOARD, T/M/LITEREADER | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
3C7WRKEL9MG613463 | 654 | 11E | C721 | C153 | C721 | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 1 TON DUMP TRUCK | 8747 | BIO DIESEL | CLARK | 2021-01-14 | 2021-06-24 | 2022-05-03 | BUCHER |  |  | A | New - Nov 2022 | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEC9JZ256490 | 656 | 5 | C767 | C017 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 49419 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-30 | 2018-09-25 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14W9XZ524965 | 659 | 5 | C767 | C245 | C767 | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | 164584 | RFG | WASHOE | 1999-05-05 | 1999-05-05 | 1999-05-21 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1CP1GKE99456 | 660 | 5 | C723 | C912 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 43250 | UNLEADED | ELKO | 2016-04-04 | 2016-07-18 | 2016-08-11 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEW1CP1GKE99456 |  |  |  |  | 11.28.2022
49HAADBVX2DK92803 | 662 | 24 | C720 | C159 | C720 | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | 102975 | DIESEL | CLARK | 2002-07-03 | 2002-08-12 | 2002-09-16 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21528ED13322 | 664 | 11E | C726 | C370 | C726 | 2008 | FORD | F-250 | DUMP TRUCK 4X4 | 205029 | UNLEADED | HUMBOLDT | 2007-09-20 | 2008-04-21 | 2009-02-10 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1CP3GKE99457 | 665 | 5 | C726 | C920 | C726 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 34852 | UNLEADED | ELKO | 2016-04-04 | 2016-07-18 | 2016-08-18 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXW46R48ED51997 | 667 | 11J | C721 | C113 | C721 | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | 191548 | BIO DIESEL | CLARK | 2007-09-24 | 2008-05-15 | 2008-06-18 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDAF57R59EA04657 | 668 | 11F | C767 | C767 | C767 | 2009 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DSL | 72190 | BIO DIESEL | WASHOE | 2007-12-18 | 2009-02-09 | 2009-10-23 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX47R18EE31270 | 669 | 11F | C722 | C028 | C722 | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | 86610 | DIESEL | CARSON CITY | 2007-05-14 | 2008-09-23 | 2008-10-16 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEDV8MPMP2512 | 670 | 25 | C721 | C152 | C767 | 2020 | WESTERN ST | 4900 | 2020 WESTERN STAR 4900FS WATER TRUCK | 3878 | DIESEL | CLARK | 2020-03-06 | 2021-07-13 | 2021-10-27 |  |  |  | A | New - Nov 2022 | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  |  | 8 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTH08X89D790332 | 671 | 12 | C723 | C355 | C723 | 2009 | PETERBILT | 367 | SINGLE AXLE DUMP TRUCK | 72373 | DIESEL | ELKO | 2007-11-28 | 2008-12-19 | 2009-10-06 |  |  | A | A |  | Elko Bridge Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | BONNELL SANDER 5 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTMF1C84GKE99455 | 672 | 5 | C723 | C912 | C723 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 49840 | UNLEADED | ELKO | 2016-04-04 | 2016-07-19 | 2016-08-30 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1C84GKE99455 |  |  |  |  | 11.28.2022
49HAADBV62DK92801 | 673 | 24 | C720 | C159 | C720 | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | 126712 | DIESEL | CLARK | 2002-07-03 | 2002-07-30 | 2002-09-16 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00XX9D782212 | 675 | 13 | C723 | C322 | C723 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 226355 | DIESEL | ELKO | 2007-12-04 | 2008-07-16 | 2009-03-30 |  |  | A | A |  | Contact Maintenance Crew | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 CU YD SANDER,PLOW WING,PLOW REVERSIBLE ALASKAN,5 CU YD FLINK SANDER HOPPER-TYPE W,SANDER 8 YARD | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDVXMPMP2513 | 676 | 25 | C721 | C153 | C767 | 2020 | WESTERN ST | 4900 | 2020 WESTERN STAR 4900SF WATER TRUCK | 4643 | DIESEL | CLARK | 2020-03-06 | 2021-07-08 | 2021-10-11 |  |  |  | A | New - Nov 2022 | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  |  | 8 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR2HHA25730 | 677 | 12 | C725 | C176 | C725 | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 185242 | DIESEL | MINERAL | 1986-12-15 | 1987-06-30 | 1987-06-30 |  |  | A | A |  | Mina Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SCHMIDT 12' PLOW,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR5HHA25754 | 678 | 12 | C725 | C171 | C725 | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 167079 | DIESEL | NYE | 1986-12-15 | 1986-12-15 | 1986-12-15 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SWENSON SANDER,11' ONE WAY PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEBG9HPJE0603 | 679 | 13S | C723 | C379 | C723 | 2017 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | 31734 | DIESEL | ELKO | 2016-06-27 | 2017-04-07 | 2017-09-14 | PARKER S/N:N0531469 | DANFOSS | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER 8 CUBIC YARDS,WATER TANK | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTZMGBR1HHA25444 | 680 | 12 | C767 | C767 | C767 | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 262654 | DIESEL | WASHOE | 1986-12-29 | 1987-05-19 | 1987-05-19 |  |  | D | D |  | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 YRD SANDER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
1NPTL00X99D782203 | 682 | 13 | C723 | C350 | C723 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 168404 | DIESEL | ELKO | 2007-11-28 | 2008-07-31 | 2009-05-13 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW WING,SANDER 8 YARD,2000 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X89D782211 | 684 | 13 | C723 | C350 | C723 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 179536 | DIESEL | ELKO | 2007-12-04 | 2008-07-17 | 2009-05-11 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X69D782210 | 685 | 13S | C726 | C373 | C726 | 2009 | PETERBILT | 367 | TANDEM AXLE HYDRAULICS W/HOOK LIFT | 108649 | DIESEL | HUMBOLDT | 2007-12-04 | 2008-07-16 | 2009-02-10 |  |  | A | A |  | Quinn River Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | LARSON 5 CU YD,SANDER,REVERSIBLE PLOW,FLATRACK SWAPLOADER,2006 WORKMAN WATER TANK | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
#N/A | 689 | 11F | C724 | C724 | #N/A | 1994 | GMC | TC310 | AWD 1 TON TRUCK W/ WELDING BODY | 108619 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Ely District Repair Shop | Ely | District 3 |  | No | 5 | OBDII | [5 empty] | 2019 TRAILBLAZER 302 WELDER | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1NPCL70X5HD440108 | 690 | 25 | C767 | C279 | C767 | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | 18578 | DIESEL | STOREY | 2016-06-24 | 2017-06-06 | 2017-11-09 |  |  | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1HTZMGBR3GHA30580 | 691 | 12 | C725 | C170 | C725 | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 177671 | DIESEL | NYE | 1986-04-11 | 1986-05-23 | 1986-05-23 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE PLOW,SANDER,FLINK 8 CU YD SANDER,SANDER 8 YARD,PLOW WING,SALT BRINE TANK | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 692 | 12 | C725 | C173 | #N/A | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 211226 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Blue Jay Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1986 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  |  |  | #N/A
1HTZMGBR9GHA30941 | 693 | 12 | C725 | C123 | C725 | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 290740 | DIESEL | NYE | 1986-04-11 | 1986-05-23 | 1986-05-23 |  |  | A | A |  | Beatty Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENDERSON SANDER,1986 PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEC2JZ251129 | 694 | 5 | C727 | C017 | C727 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 45005 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-01 | 2019-01-25 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPCL70X7HD440109 | 695 | 25 | C721 | C179 | C721 | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | 24302 | DIESEL | CLARK | 2016-06-27 | 2017-10-13 | 2018-02-13 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR5GHA31200 | 696 | 12 | C767 | C241 | C767 | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 185043 | DIESEL | WASHOE | 1986-04-11 | 1986-04-11 | 1986-04-11 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,HIGHSPEED 11' PLOW,SANDER 5 YD | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
1G1ZC5ST9GF297630 | 698 | 1 | C721 | C721 | C721 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 25979 | SMARTWAY | CLARK | 2016-04-21 | 2016-06-20 | 2016-07-14 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ZC5ST9GF297630
#N/A | 699 | 1 | C721 | C721 | #N/A | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 21621 | SMARTWAY | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Deleted |  | #N/A
1NPTL00X79D782202 | 702 | 13 | C728 | C283 | C728 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 150050 | DIESEL | PERSHING | 2007-11-28 | 2008-07-31 | 2009-07-08 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 705 | 5 | C723 | C723 | #N/A | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | 277210 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Elko District Repair Shop | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1NPTL00X39D782214 | 706 | 13 | C723 | C336 | C723 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 203146 | DIESEL | ELKO | 2007-12-04 | 2008-07-18 | 2009-04-07 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X09D782221 | 707 | 13 | C722 | C227 | C722 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 156321 | DIESEL | DOUGLAS | 2007-11-28 | 2008-07-30 | 2009-06-15 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 708 | 5 | C767 | C201 | #N/A | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | 96370 | RFG | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1G1ZC5ST6GF296290 | 711 | 1 | C721 | C110 | C721 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 22243 | SMARTWAY | CLARK | 2016-04-21 | 2016-06-17 | 2016-07-14 |  |  | A | A |  | Project Management - Las Vegas | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ZC5ST6GF296290
1GCVKNEC2JZ252507 | 714 | 5 | C767 | C017 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 56319 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-07 | 2018-09-25 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZC5ST9GF294999 | 716 | 1 | C721 | C721 | C721 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 22939 | SMARTWAY | CLARK | 2016-04-21 | 2016-06-17 | 2016-07-22 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ZC5ST9GF294999
1NPTL00X09D782204 | 717 | 13 | C728 | C237 | C728 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 133028 | DIESEL | MINERAL | 2007-11-28 | 2008-07-31 | 2009-06-25 |  |  | A | A |  | Hawthrone Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
7022293 | 726 | 42 | C722 | C227 | C722 | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | 768 | DIESEL | DOUGLAS | 2002-07-03 | 2002-08-07 | 2002-11-19 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
0702-2294 | 730 | 42 | C722 | C271 | C722 | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | 2542 | DIESEL | STOREY | 2002-07-03 | 2002-08-07 | 2002-11-18 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZC5ST1GF299615 | 736 | 1 | C721 | C721 | C721 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 25698 | SMARTWAY | CLARK | 2016-04-21 | 2016-06-17 | 2016-07-22 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ZC5ST1GF299615
1NPTL00X59D782215 | 739 | 13 | C728 | C281 | C728 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 86713 | DIESEL | CHURCHILL | 2007-12-04 | 2008-07-17 | 2009-05-06 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C82HKC09425 | 740 | 5 | C767 | C904 | C767 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 39298 | FLEX FUEL | WASHOE | 2016-07-08 | 2016-11-17 | 2017-02-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 741 | 12 | C724 | C382 | #N/A | 1994 | FORD | F-700 | SINGLE AXLE DUMP TRUCK | 164915 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Lund Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1NPTL00X09D782218 | 742 | 13S | C721 | C151 | C721 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMB TRUCK W/HOOK LIFT | 132915 | DIESEL | CLARK | 2007-12-04 | 2008-07-24 | 2009-07-06 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1NPTL00X29D782219 | 743 | 13S | C725 | C123 | C725 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 192975 | DIESEL | NYE | 2007-11-28 | 2008-07-30 | 2009-07-14 |  |  | A | A |  | Beatty Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SWAPLOADER SANDER,ONE WAY PLOW,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C84HKC09426 | 748 | 5 | C767 | C905 | C767 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 30086 | FLEX FUEL | WASHOE | 2016-07-08 | 2016-11-21 | 2017-02-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X99D782217 | 749 | 13 | C728 | C280 | C728 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 108133 | DIESEL | CHURCHILL | 2007-12-04 | 2008-07-21 | 2009-07-31 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X29D782205 | 752 | 13 | C723 | C336 | C723 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 236500 | DIESEL | ELKO | 2007-11-28 | 2008-07-31 | 2009-05-18 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C86HKC09427 | 753 | 5 | C722 | C907 | C722 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 36622 | FLEX FUEL | CARSON CITY | 2016-07-08 | 2016-11-16 | 2017-02-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C86GKF34111 | 755 | 5 | C722 | C911 | C722 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 43299 | UNLEADED | CARSON CITY | 2016-07-08 | 2016-08-17 | 2016-09-16 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAURXRH613842 | 757 | 12 | C728 | C237 | C728 | 1994 | INTL | F2574 | REBUILD SINGLE AXLE DUMP TRUCK | 68970 | DIESEL | MINERAL | 1994-05-18 | 1994-12-21 | 2011-02-28 | COMMERCIAL |  | A | A |  | Hawthrone Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 12' RIGHT HAND PLOW,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X19D782213 | 761 | 13 | C722 | C271 | C722 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 165401 | DIESEL | CARSON CITY | 2007-12-04 | 2008-07-17 | 2009-07-21 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | EPOKE |  |  |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X29D782222 | 763 | 13 | C722 | C272 | C722 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 144780 | DIESEL | CARSON CITY | 2007-11-28 | 2008-07-30 | 2009-07-09 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAUR5RH613845 | 764 | 12 | C728 | C236 | C728 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 158461 | DIESEL | CHURCHILL | 1994-05-18 | 1994-10-13 | 1994-10-13 |  |  | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,TENCO,5 YRD HENDERSON SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C88HKC09428 | 769 | 5 | C767 | C910 | C767 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 22221 | FLEX FUEL | WASHOE | 2016-07-08 | 2016-11-14 | 2017-02-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GAWGEFG3H1192164 | 771 | 4 | C721 | C160 | C721 | 2017 | CHEVROLET | EXPRESS | 15 PASSENGER VAN | 46721 | E-85 | CLARK | 2016-12-13 | 2017-03-07 | 2017-05-09 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPZL00X82D714202 | 772 | 77 | C767 | C241 | C767 | 2002 | EZ LINER | 320 | FREEWAY LINE STRIPER | 175468 | DIESEL | WASHOE | 2002-06-13 | 2002-07-12 | 2002-09-20 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes |  |  |  | 10/13/2022: Unit No 772 and 1089. One of these two vehicles is out of service. The vehicle for pilot will be one of these two vehicles and the new vehicle number with unit number 2381
1GCVKNEH7JZ255091 | 773 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 11507 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-04-19 | 2018-12-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GAWGEFG5L1259677 | 774 | 4 | C727 | A059 | C727 | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS VAN | 252 | FLEX FUEL | WASHOE | 2020-01-13 | 2020-08-19 | 2020-08-27 |  |  | A | A |  | Flight Operations | Carson City | District 2 | Vans | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X79D782216 | 776 | 13 | C728 | C281 | C728 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 82101 | DIESEL | CHURCHILL | 2007-11-28 | 2008-07-30 | 2009-07-10 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCRCNEH7HZ222780 | 778 | 5 | C721 | C101 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 57283 | E-85 | CLARK | 2016-11-30 | 2017-02-28 | 2017-08-22 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCRCNEH7HZ222780 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1NPTL70X1JD487190 | 779 | 13 | C725 | C171 | C725 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 17613 | DIESEL | WASHOE | 2017-06-30 | 2018-11-26 | 2019-02-12 | DANFOSS | DANFOSS | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X49D782206 | 780 | 13 | C724 | C342 | C724 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | 127797 | DIESEL | WHITE PINE | 2007-11-28 | 2008-07-31 | 2009-06-02 |  |  | A | A |  | Ely Striping Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4GT2MED06740 | 781 | 11S | C721 | C151 | C721 | 2021 | FORD | F-450 | 2021 F-450 1 TON SWPLOADER DUMP BODY | 6662 | BIO DIESEL | CLARK | 2020-11-03 | 2021-07-01 | 2022-03-10 | PARKER | SWAPLOADER |  | A | New - Nov 2022 | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FD0X4GT2MED06740 |  |  |  |  | 11.22.2022
1FD0X4GT6MED06739 | 782 | 11S | C721 | C145 | C721 | 2021 | FORD | F-450 | 2021 F-450 1 TON SWPLOADER DUMP BODY | 8760 | BIO DIESEL | CLARK | 2020-10-03 | 2021-10-14 | 2022-03-28 | PARKER | SWAPLOADER |  | A | New - Nov 2022 | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1XPTD49XX8D769343 | 783 | 14 | C724 | C319 | C724 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | 185806 | DIESEL | WHITE PINE | 2007-06-19 | 2008-02-06 | 2008-02-25 | MUNCIE |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAUR1RH613843 | 784 | 12 | C767 | C252 | C767 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 109744 | DIESEL | WASHOE | 1994-06-03 | 1994-12-21 | 1994-12-21 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Pilot |  | #N/A
1XPTD49X48D769340 | 785 | 14 | C728 | C280 | C728 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | 98808 | DIESEL | CHURCHILL | 2007-06-19 | 2008-01-24 | 2008-06-05 | MUNCIE |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH5JZ255204 | 786 | 5 | C727 | C802 | C727 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | 10263 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-20 | 2019-01-04 |  |  | A | A |  | Transportation / Multimodal Planning (Landmark) | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXFC2JHJV4643 | 787 | 24 | C725 | C170 | C725 | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 4603 | DIESEL | NYE | 2017-05-31 | 2018-04-03 | 2018-04-12 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B85HGC14532 | 790 | 01A | C724 | C307 | C724 | 2017 | FORD | EXPLORER | 4X4 SUV | 22834 | RFG | WHITE PINE | 2016-11-30 | 2017-04-24 | 2017-08-01 |  |  | A | A |  | Ely District Administration | Ely | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG3HF142217 | 792 | 3 | C767 | C225 | C767 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 79741 | UNLEADED | WASHOE | 2016-12-12 | 2017-02-24 | 2017-05-23 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1XPTD49X88D769342 | 793 | 14 | C723 | C332 | C723 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | 194171 | DIESEL | ELKO | 2007-06-28 | 2008-01-22 | 2008-02-21 | MUNCIE |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAUR7RH613846 | 794 | 12 | C767 | C250 | C767 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 238770 | DIESEL | WASHOE | 1994-06-03 | 1994-06-24 | 1994-06-24 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | ONE WAY PLOW,5 YARD SLIDE IN SANDER,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1XPTD49X68D769341 | 796 | 14 | C724 | C319 | C724 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | 199449 | DIESEL | WHITE PINE | 2007-06-19 | 2008-01-23 | 2008-02-25 | MUNCIE |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1WBMCCSE7DN059351 | 797 | 25 | C724 | C385 | C724 | 1983 | AUTOCAR | KM64F | TANDEM AXLE WATER TRUCK | 345812 | DIESEL | LANDER | 1983-09-19 | 1983-11-07 | 1983-11-07 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH2JG312633 | 800 | 5 | C721 | C031 | C721 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 15254 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-04-19 | 2018-07-25 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3GCUKNEH2JG312633 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1G1ZS57F97F287802 | 802 | 1 | C723 | C767 | C723 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 119275 | FLEX FUEL | WASHOE | 2007-04-11 | 2007-06-07 | 2007-06-13 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot | 1G1ZS57F97F287802 |  |  |  |  | 11.29.2022
1HTGEAUR8RH613841 | 805 | 12 | C767 | C252 | C767 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 120401 | DIESEL | WASHOE | 1994-05-18 | 1994-12-21 | 1994-12-21 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,5 YRD FLINK MOD 10 LMC .5H | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
1GC1KUEG3HF141438 | 807 | 3 | C767 | C231 | C767 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 148936 | UNLEADED | STOREY | 2016-12-12 | 2017-03-08 | 2017-06-20 |  |  | A | A |  | Nixon Maintenance Crew | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEC0JG308925 | 809 | 5 | C767 | C025 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | 25735 | FLEX FUEL | WASHOE | 2017-12-13 | 2018-04-19 | 2018-08-10 |  |  | A | A |  | Materials Structural/Chemical | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG0HF143468 | 810 | 3 | C722 | C227 | C722 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 64815 | UNLEADED | DOUGLAS | 2016-12-12 | 2017-03-13 | 2017-07-25 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEC8JZ254066 | 811 | 5 | C767 | C092 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | 29869 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-01 | 2018-09-11 |  |  | A | A |  | Communications Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG1HF142569 | 813 | 3 | C728 | C282 | C728 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 88188 | FLEX FUEL | CHURCHILL | 2016-12-12 | 2017-02-24 | 2017-07-27 |  |  | A | A |  | Cold Springs Maintenance Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEC6JZ254311 | 814 | 5 | C723 | C093 | C723 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 45094 | FLEX FUEL | ELKO | 2017-12-05 | 2018-03-30 | 2018-08-30 |  |  | A | A |  | Communications Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCVKNEC6JZ254311 |  |  |  |  | 11.30.2022
3GCUKNEHXHG305407 | 816 | 5 | C767 | C201 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 130046 | FLEX FUEL | LYON | 2016-12-07 | 2017-02-22 | 2017-08-25 |  |  | A | D |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH1HG301973 | 817 | 5 | C728 | C201 | C728 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 95300 | FLEX FUEL | WASHOE | 2016-12-07 | 2017-03-03 | 2017-08-07 |  |  | A | A |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 819 | 12 | C725 | C171 | #N/A | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 237905 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1986 SANDER,1985 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  |  |  | #N/A
3GCUKNEH5HG304701 | 821 | 5 | C767 | C201 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 12486 | FLEX FUEL | WASHOE | 2016-12-06 | 2017-02-22 | 2017-09-26 |  |  | A | A |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNKNEH8JZ260347 | 822 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 52729 | FLEX FUEL | ELKO | 2017-12-05 | 2018-03-20 | 2018-12-21 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHROTH229991 | 823 | 12 | C725 | C171 | C725 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 114734 | DIESEL | NYE | 1995-10-13 | 1996-01-10 | 1996-01-10 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1995 SANDER,1995 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEHXHZ221964 | 826 | 5 | C767 | C204 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 83024 | FLEX FUEL | WASHOE | 2016-12-02 | 2017-02-28 | 2017-07-07 |  |  | A | A |  | Permits | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHR2TH229992 | 827 | 12 | C721 | C122 | C721 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 172597 | DIESEL | LINCOLN | 1995-10-04 | 1996-03-18 | 1996-03-18 |  |  | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 5 CU YARD | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG5JF210538 | 828 | 3 | C727 | C016 | C727 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 17876 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-03-20 | 2018-10-18 |  |  | A | A |  | Traffic Operations | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 829 | 13 | C767 | C767 | #N/A | 1995 | GMC | ACL64 | TANDEM AXLE DUMP TRUCK | 251982 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE 11' PLOW,REVERSIBLE PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  |  |  | #N/A
1GJGG25U731179985 | 830 | 4 | C727 | C727 | C727 | 2003 | GMC | SAVANA | 12 PASSENGER VAN | 133368 | UNLEADED | CARSON CITY | 2002-07-01 | 2003-03-03 | 2003-03-03 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Vans | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GJGG25U931180975 | 831 | 4 | C727 | C727 | C727 | 2003 | GMC | SAVANA | 12 PASSENGER VAN | 122015 | UNLEADED | CARSON CITY | 2002-07-01 | 2003-03-03 | 2003-03-03 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Vans | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH5JG305885 | 832 | 5 | C727 | C050 | C727 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 3692 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-06-12 | 2018-10-15 |  |  | A | A |  | Maintenance and Asset Mgmt | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4GT3LEE33916 | 834 | 11E | C721 | C153 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 4X2 DUMP TRUCK | 385 | BIO DIESEL | CLARK | 2020-02-28 | 2021-01-05 | 2021-07-12 |  |  | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCVKNEH2HZ222221 | 835 | 5 | C767 | C032 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 24511 | FLEX FUEL | WASHOE | 2016-12-02 | 2017-03-03 | 2017-11-13 |  |  | A | A |  | Right of Way Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X3JD487191 | 836 | 13 | C728 | C236 | C728 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 23739 | DIESEL | LYON | 2017-06-29 | 2018-01-24 | 2019-02-19 | DANFOSS | DANFOSS | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | HENKE SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1NPTL70X3JD487191
3GCUKNEC8JG307036 | 838 | 5 | C767 | C050 | C727 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 14014 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-04-09 | 2018-07-17 |  |  | A | A |  | Maintenance and Asset Mgmt | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEC6JZ253840 | 840 | 5 | C727 | C017 | C727 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | 46204 | FLEX FUEL | CARSON CITY | 2017-12-06 | 2018-04-11 | 2018-10-18 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X7JD487193 | 841 | 13 | C722 | C271 | C722 | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | 39418 | DIESEL | CARSON CITY | 2017-06-29 | 2018-02-22 | 2019-02-25 | DANFOSS | DANFOSS | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | SANDER,REVERSIBLE PLOW,2021 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1NPTL70X7JD487193
#N/A | 842 | 12 | C767 | C767 | #N/A | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 169428 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 CU. YD SANDER,TYNCO REVERSIBLE | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Blank - 1/24/2023 |  | #N/A
1GCNKNEH2JZ259002 | 843 | 5 | C721 | C013 | C721 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | 17530 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-30 | 2018-05-30 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNKNEH9JZ260132 | 846 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 31073 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-30 | 2018-08-27 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTM70X3JD483624 | 848 | 15 | C767 | C250 | C767 | 2017 | PETERBILT | 367 | TANDEM AXLE PLOW TRUCK | 26990 | DIESEL | WASHOE | 2017-06-08 | 2018-04-13 | 2018-11-30 | DANFOSS | DANFOSS | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | ONE-WAY PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1NPTM70X3JD483624 | [5 empty] | 12/14/2022: VIN number has been corrected based on the email received from Billie
1FD0X4GT3LED97273 | 850 | 11E | C721 | C155 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | 416 | BIO DIESEL | CLARK | 2020-01-29 | 2020-12-09 | 2021-05-04 |  |  | A | A |  | Las Vegas Bridge Maintenance | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GTEK19V43E256783 | 854 | 5 | C767 | C011 | C767 | 2003 | GMC | SIERRA | 1/2 TON PICKUP TRUCK 4X4 | 156549 | UNLEADED | WASHOE | 2002-07-01 | 2003-03-03 | 2003-03-03 |  |  | A | A |  | Structural Design | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG6HF142731 | 860 | 3 | C723 | C301 | C723 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 56467 | UNLEADED | ELKO | 2016-12-12 | 2017-02-24 | 2017-09-27 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
1GC2KUEG6HZ234070 | 862 | 3 | C723 | C301 | C723 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 130224 | UNLEADED | ELKO | 2016-12-13 | 2017-03-13 | 2017-11-03 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GC2KUEG6HZ234070 |  |  |  |  | 11.29.2022
1FD0X4GT5LEE33917 | 864 | 11H | C721 | C142 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | 1651 | BIO DIESEL | CLARK | 2020-03-10 | 2021-02-23 | 2022-02-04 |  |  |  | A | New - Nov 2022 | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG9HF141511 | 866 | 3 | C723 | C301 | C723 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 78407 | UNLEADED | ELKO | 2016-12-12 | 2017-03-13 | 2017-10-19 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
1GCNKNEH2JZ259632 | 869 | 5 | C727 | A067 | C727 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP | 10106 | FLEX FUEL | CARSON CITY | 2017-12-05 | 2018-03-30 | 2019-02-02 |  |  | A | A |  | Information Services | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH7JZ263267 | 870 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 25106 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-06-06 | 2018-07-24 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRLEL4MG621721 | 871 | 11E | C723 | C335 | C723 | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 4X4 1 TON DUMP TRUCK | 4503 | DIESEL | ELKO | 2021-01-20 | 2021-07-15 | 2022-06-22 | BUCHER |  |  | A | New - Nov 2022 | Wells Maintenance Crew 2 | Wells | District 3 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC2KUEG3HZ229554 | 872 | 3 | C726 | C371 | C726 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 82507 | UNLEADED | HUMBOLDT | 2016-12-12 | 2017-03-17 | 2017-08-29 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAUT2RH613680 | 873 | 13 | C767 | C251 | C767 | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 233876 | DIESEL | WASHOE | 1994-07-11 | 1994-07-11 | 1994-07-11 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE WING PLOW,PLOW,SANDER,8 YARD FLINK SANDER | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAUT4RH613678 | 877 | 13 | C722 | C272 | C722 | 1994 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | 84474 | DIESEL | CARSON CITY | 1994-07-11 | 1994-09-28 | 2011-03-04 | PARKER 13 | PARKER | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HEAVY DUTY PATROL WING PLOW,11' REVERSIBLE LEWTON MDL RO1144NV,FLINK MDL #LMC5H-15NV-39 | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GTEC14W3XZ524931 | 878 | 5 | C725 | C725 | C725 | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | 132013 | UNLEADED | NYE | 1999-05-27 | 1999-05-27 | 1999-06-16 |  |  | A | A |  | Tonopah District Repair Shop | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4GT7LEE33918 | 882 | 11H | C721 | C140 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | 19643 | BIO DIESEL | CLARK | 2020-03-10 | 2021-02-23 | 2022-02-01 |  |  |  | A | New - Nov 2022 | Las Vegas Sign Crew 1 | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAUT9RH613675 | 884 | 13 | C725 | C170 | C725 | 1994 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 69680 | DIESEL | NYE | 1994-06-03 | 1994-12-14 | 2013-04-22 | PARKER 13 | PARKER | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 1994 PLOW,HENKE WING PLOW,8 YD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 890 | 13 | C767 | C767 | #N/A | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 283209 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,1994 SANDER,WING PLOW | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  |  |  | #N/A
1GCNCNEH8JZ259745 | 892 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 27194 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-19 | 2018-10-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAUTORH613676 | 894 | 13 | C767 | C767 | C723 | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 216439 | DIESEL | ELKO | 1994-07-11 | 1994-07-11 | 1994-07-11 |  |  | D | A |  | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1994 WING PLOW,PLOW | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1GC0KUEG2HZ230203 | 895 | 3 | C723 | C350 | C723 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 100198 | UNLEADED | ELKO | 2016-12-12 | 2017-02-24 | 2017-08-21 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GC0KUEG2HZ230203 |  |  |  |  | 11.28.2022
1GC0KUEG8HZ229492 | 896 | 3 | C723 | C351 | C723 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 67428 | FLEX FUEL | ELKO | 2016-12-13 | 2017-02-24 | 2017-07-07 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GC0KUEG8HZ229492 |  |  |  |  | 11.28.2022
1GCNCNEH9JZ260225 | 898 | 5 | C767 | C904 | C767 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | 8544 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-13 | 2019-01-09 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH8JZ261883 | 899 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 5769 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-19 | 2019-01-15 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXW47P13ED60307 | 902 | 11F | C767 | C767 | C767 | 2003 | FORD | F-450 | SERVICE TRUCK | 71601 | DIESEL | CARSON CITY | 2003-02-04 | 2003-08-07 | 2003-08-26 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 903 | 12 | C767 | C767 | #N/A | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 152718 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1996 SANDER,1996 PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  |  |  | #N/A
1HTSLABN9VH442513 | 905 | 11H | C721 | C121 | C721 | 1996 | INTL | 4700 | FLAT RACK TRUCK | 115261 | DIESEL | CLARK | 1996-10-25 | 1997-02-11 | 1997-02-11 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCNCNEHXJZ259570 | 906 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 31800 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-07 | 2018-04-23 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTWXAXRX3J074575 | 909 | 11B | C723 | C340 | C723 | 2003 | INTL | 7600 | FLATRACK TRUCK W/CRANE | 130062 | DIESEL | ELKO | 2003-08-27 | 2003-09-18 | 2003-10-07 |  |  | A | A |  | Elko Striping Crew | Elko | District 3 |  | No | 6 | J1939 | [5 empty] | 2018 ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGEAHRXTH229996 | 910 | 12 | C725 | C170 | C725 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK REBUILD | 37517 | DIESEL | NYE | 1995-09-28 | 1996-01-28 | 2011-02-14 | COMMERCIAL |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 10FT PLOW REVERSIBLE,MESSAGE BOARD | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH7JZ259624 | 913 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 10681 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-19 | 2019-01-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF5HY3HEE28131 | 914 | 11A | C723 | C302 | C723 | 2017 | FORD | F-550 | AERIAL TRUCK 4X4 | 31612 | UNLEADED | ELKO | 2017-05-11 | 2018-05-10 | 2018-06-06 |  |  | A | A |  | Elko Service Crew | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FDUF5HY3HEE28131 |  |  |  |  | 11.28.2022
#N/A | 915 | 11H | C767 | C242 | #N/A | 2003 | FORD | F-450 | FLATRACK TRUCK | 194159 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Reno Pavement Markings | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
3C7WRLEL0MG621781 | 916 | 11F | C723 | C723 | C723 | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 4X4 SERVICE TRUCK | 676 | DIESEL | ELKO | 2021-02-04 | 2021-07-01 | 2022-08-15 |  |  |  | A | New - Nov 2022 | Elko District Repair Shop | Elko | District 3 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 3C7WRLEL0MG621781 |  |  |  |  | 11.29.2022
1HTWZAHR54J091035 | 917 | 11A | C767 | C240 | C767 | 2003 | INTL | 7600 | AERIAL LIFT TRUCK BIO-DSL | 66119 | DIESEL | WASHOE | 2002-07-02 | 2006-08-21 | 2006-08-21 |  |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4HY2HED94532 | 921 | 11E | C726 | C372 | C726 | 2017 | FORD | F-450 | 1 TON DUMP TRUCK | 86117 | UNLEADED | HUMBOLDT | 2017-03-13 | 2017-08-01 | 2017-12-07 |  |  | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCNCNEHXJZ260007 | 923 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 14875 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-19 | 2018-10-08 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4HY4HED45415 | 925 | 11F | C724 | C724 | C724 | 2017 | FORD | F-450 | SERVICE TRUCK 4X4 | 96977 | UNLEADED | WHITE PINE | 2017-02-03 | 2017-07-26 | 2017-12-15 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2018 WESTERN MULE REAR BUMPER CRANE | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDUF4HY2HED94502 | 926 | 11H | C724 | C342 | C724 | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | 69500 | UNLEADED | WHITE PINE | 2017-03-13 | 2018-01-26 | 2018-03-23 |  |  | A | A |  | Ely Striping Crew | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCNCNEH4JZ261928 | 927 | 5 | C767 | C910 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | 11964 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-03-20 | 2018-08-16 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes | JENSEN-MODEL 43058 | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH6JZ261994 | 928 | 5 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 26409 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-04-19 | 2019-01-14 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX47P53EC58361 | 931 | 11J | C767 | C245 | C767 | 2003 | FORD | F-450 | UTILITY TRUCK 4X4 | 208240 | DIESEL | WASHOE | 2003-01-07 | 2003-07-21 | 2003-08-14 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
3C7WRLEL6MG621722 | 932 | 11E | C723 | C331 | C723 | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 4X4 1 TON DUMP TRUCK | 3000 | DIESEL | WHITE PINE | 2021-01-20 | 2021-12-10 | 2022-08-04 | BUCHER |  |  | A | New - Nov 2022 | Ruby Valley Maintenance Crew | Elko | District 3 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 3C7WRLEL6MG621722 |  |  |  |  | 11.30.2022
1FDXX47P13EC58356 | 933 | 11J | C767 | C245 | C767 | 2003 | FORD | F-450 | UTILITY TRUCK | 159528 | DIESEL | WASHOE | 2003-01-07 | 2003-07-01 | 2003-08-14 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46P83EC58360 | 936 | 11J | C720 | C102 | C720 | 2003 | FORD | F-450 | UTILITY TRUCK | 109036 | DIESEL | CLARK | 2003-01-07 | 2003-07-01 | 2003-07-30 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project | Pre-Pilot | 1FDXF46P83EC58360
3C7WRNFJ7MG602007 | 937 | 11H | C724 | C724 | C724 | 2021 | RAM | 5500 | 2021 DODGE 5500 FLATRACK 4 X4 | 3135 | UNLEADED | WHITE PINE | 2021-01-11 | 2021-05-27 | 2022-08-10 |  |  |  | A | New - Nov 2022 | Ely District Repair Shop | Ely | District 3 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4HY2HED45414 | 939 | 11J | C723 | C302 | C723 | 2017 | FORD | F-450 | UTILITY TRUCK | 79583 | UNLEADED | ELKO | 2017-02-03 | 2017-07-26 | 2017-12-15 |  |  | A | A |  | Elko Service Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDUF4HY2HED45414 |  | Yes |  |  | 11.28.2022
1GCNCNEH2JZ257683 | 940 | 5 | C767 | C910 | C767 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO | 56744 | FLEX FUEL | WASHOE | 2017-12-05 | 2018-04-11 | 2018-05-30 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R98EB92096 | 941 | 3 | C722 | C907 | C722 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 113318 | DIESEL | CARSON CITY | 2007-11-16 | 2007-12-04 | 2007-12-18 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4GY9HED45413 | 942 | 11J | C724 | C724 | C724 | 2017 | FORD | F-450 | UTILITY TRUCK | 34357 | UNLEADED | WHITE PINE | 2017-02-02 | 2017-07-26 | 2017-12-15 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF47P84EB52233 | 943 | 11F | C726 | C726 | C726 | 2004 | FORD | F-450 | UTILITY TRUCK W/CRANE 4X4 | 159601 | DIESEL | HUMBOLDT | 2002-07-02 | 2004-03-30 | 2004-05-21 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTWX31R78EE27274 | 945 | 6 | C767 | C767 | C767 | 2008 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | 111424 | DIESEL | WASHOE | 2008-03-24 | 2008-06-16 | 2008-09-26 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTSX21R79EA12417 | 946 | 3 | C721 | C017 | C721 | 2009 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 172429 | DIESEL | CARSON CITY | 2008-05-02 | 2008-12-11 | 2009-04-06 |  |  | A | A |  | Location | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRNFJ5MG595168 | 948 | 11H | C724 | C319 | C724 | 2021 | RAM | 5500 | 2021 DODGE 5500 FLATRACK 4 X4 | 6877 | DIESEL | WHITE PINE | 2021-01-11 | 2021-05-27 | 2022-06-01 |  |  |  | A | New - Nov 2022 | Ely Yard Stockpile Control | Ely | District 3 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X47D653146 | 950 | 13 | C720 | C126 | C720 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 99973 | DIESEL | CLARK | 2002-07-01 | 2006-12-01 | 2006-12-12 |  |  | A | A |  | Mountain Springs Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2007 HENKE PLOW REVERSIBLE,FLINK SANDER 8 YARD | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X5JD487189 | 952 | 13 | C726 | C373 | C726 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 19118 | DIESEL | HUMBOLDT | 2017-06-29 | 2018-01-24 | 2018-12-14 | DANFOSS | DANFOSS | A | A |  | Quinn River Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
5KKHAEDEX6PW67238 | 954 | 13S | C726 | C371 | C726 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/ HOOK LIFT | 146727 | DIESEL | HUMBOLDT | 2002-07-01 | 2006-07-10 | 2006-07-31 | PARKER | PARKER | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 15 FOOT SWAPLOADER DUMP BODY,2006 HENKE PLOW REVERSIBLE,2006 FLINK SANDER 8 YARD,SWAPLOADER WATER TANK | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE96PW45943 | 955 | 13 | C722 | C271 | C722 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 207582 | DIESEL | CARSON CITY | 2003-07-01 | 2006-02-10 | 2006-03-23 | PARKER | PARKER | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | EPOKE |  |  |  | SANDER EPOKE,HEAVY DUTY PATROL WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X77D652590 | 956 | 13 | C722 | C235 | C722 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 188621 | DIESEL | LYON | 2002-07-01 | 2006-09-22 | 2006-10-18 | PARKER | PARKER | A | A |  | Wellington Maintenance Crew | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 2018 REVERSIBLE PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X77D653139 | 958 | 13 | C724 | C381 | C724 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 291818 | DIESEL | WHITE PINE | 2002-07-01 | 2006-12-01 | 2006-12-12 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X77D653142 | 961 | 13 | C724 | C380 | C724 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 218021 | DIESEL | WHITE PINE | 2002-07-01 | 2006-08-03 | 2006-08-26 |  |  | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE76PW45942 | 962 | 13 | C728 | C282 | C728 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 212530 | DIESEL | CHURCHILL | 2004-07-01 | 2006-01-11 | 2006-02-16 | PARKER | PARKER | A | A |  | Cold Springs Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD,SLIDE IN PRAYER,PLOW,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE36PW45937 | 963 | 13 | C724 | C381 | C724 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 318397 | DIESEL | WHITE PINE | 2002-07-01 | 2006-03-06 | 2006-05-15 | PARKER | PARKER | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 900 GALLON DE-ICING SPRAYER,PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X3JD487188 | 964 | 13 | C723 | C336 | C723 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 50411 | DIESEL | ELKO | 2017-06-29 | 2018-01-25 | 2019-01-30 | DANFOSS | DANFOSS | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X07D652589 | 966 | 13 | C767 | C231 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 249749 | DIESEL | WASHOE | 2002-07-01 | 2006-10-09 | 2006-10-18 | PARKER | PARKER | A | A |  | Nixon Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1HTGEAHR5TH229985 | 967 | 12 | C724 | C385 | C724 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 186269 | DIESEL | LANDER | 1995-10-18 | 1995-10-18 | 1995-10-18 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 YD,1996 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B63KEC51756 | 968 | 3 | C722 | C270 | C722 | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | 56270 | UNLEADED | CARSON CITY | 2018-06-06 | 2018-10-02 | 2019-01-18 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG8JF211053 | 969 | 3 | C728 | C237 | C728 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 96394 | UNLEADED | CHURCHILL | 2017-12-13 | 2018-03-07 | 2018-10-29 |  |  | A | A |  | Hawthrone Maintenance Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRNEL6LG238325 | 973 | 11A | C723 | C093 | C723 | 2020 | DODGE | 5500 | 2020 DODGE RAM 5500 FLATRACK | 7457 | DIESEL | ELKO | 2020-04-16 | 2020-10-12 | 2021-01-19 |  |  | A | A |  | Communications Elko | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3C7WRNEL6LG238325 |  |  |  |  | 11.28.2022
3C7WRNFJ7MG595169 | 975 | 11H | C724 | C724 | C724 | 2021 | RAM | 5500 | 2021 DODGE 5500 FLATRACK 4 X4 | 548 | DIESEL | WHITE PINE | 2021-01-11 | 2021-05-27 | 2022-05-11 |  |  |  | A | New - Nov 2022 | Ely District Repair Shop | Ely | District 3 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X37D653137 | 977 | 13 | C725 | C171 | C725 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 191139 | DIESEL | NYE | 2004-07-01 | 2006-10-23 | 2006-11-28 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE WING PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHR7TH229986 | 978 | 12 | C723 | C355 | C723 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 148764 | DIESEL | ELKO | 1995-10-25 | 1996-01-24 | 1996-01-24 |  |  | A | A |  | Elko Bridge Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1995 PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE16PW45936 | 979 | 13S | C728 | C282 | C728 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 203759 | DIESEL | CHURCHILL | 2002-07-01 | 2006-01-11 | 2006-02-23 |  |  | A | A |  | Cold Springs Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X57D653138 | 984 | 13 | C723 | C332 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 166511 | DIESEL | ELKO | 2002-07-01 | 2006-09-29 | 2006-10-10 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,2020 HENKE PLOW,2020 HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE26PW97771 | 985 | 13 | C726 | C371 | C726 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 218535 | DIESEL | LANDER | 2002-07-01 | 2006-05-23 | 2006-06-30 | PARKER | PARKER | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE TRK MTED WING PLOW,SANDER 8 YARD,PLOW REVERSIBLE | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE06PW45944 | 986 | 13 | C722 | C270 | C722 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 162935 | DIESEL | CARSON CITY | 2002-07-01 | 2006-02-10 | 2006-04-10 | PARKER | PARKER | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1XKWD49X83R393773 | 987 | 14 | C767 | C225 | C767 | 2003 | KENW | W900B | TRACTOR TRUCK | 201113 | DIESEL | LYON | 2002-09-27 | 2003-02-04 | 2003-02-27 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 9 | J1939 | [5 empty] | 1995 SANDER | Telematics Device |  |  |  |  | Yes | Yes | No Up Down Sensors needed - Transport Truck | Full Project |  | #N/A
1HTSCNKL7MH367556 | 988 | 11H | C767 | C026 | C767 | 1991 | INTL | 4700 | SINGLE AXLE FLATRACK TRUCK | 62320 | DIESEL | CARSON CITY | 1991-07-16 | 1991-07-16 | 1991-07-16 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GC1KUEG9JF211529 | 989 | 3 | C728 | C283 | C728 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 114351 | TELEMATIC | PERSHING | 2017-12-13 | 2018-04-11 | 2018-06-19 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC2KUEG6HZ232884 | 992 | 3 | C722 | C027 | C722 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 43667 | UNLEADED | CARSON CITY | 2016-12-12 | 2017-06-12 | 2017-10-05 |  |  | A | A |  | Materials Bituminous | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCWGAFF5H1198510 | 993 | 4 | C727 | C040 | C727 | 2017 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | 113303 | UNLEADED | CARSON CITY | 2016-12-13 | 2017-06-06 | 2017-09-05 |  |  | A | A |  | Construction Administration | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV63DK54421 | 994 | 24 | C726 | C371 | C726 | 2002 | WITTKE | FC-70 | STREET SWEEPER | 67615 | DIESEL | HUMBOLDT | 2002-10-02 | 2002-12-18 | 2003-01-22 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH7HG305686 | 995 | 5 | C727 | C013 | C727 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 41009 | FLEX FUEL | CARSON CITY | 2016-12-07 | 2017-03-03 | 2017-05-15 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV13DK44220 | 996 | 24 | C724 | C319 | C724 | 2003 | TYMCO | 600 | SWEEPER DUSTLESS | 108701 | DIESEL | WHITE PINE | 2002-07-29 | 2002-11-14 | 2002-12-05 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1G11A5SA9DF219412 | 1002 | 1 | C725 | C104 | C725 | 2013 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 76781 | UNLEADED | NYE | 2012-10-18 | 2012-12-18 | 2013-01-24 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | Sedan | Yes | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1FM5K8B85DGC16212 | 1003 | 01A | C721 | C101 | C721 | 2013 | FORD | EXPLORER | SUV 4X4 | 20639 | UNLEADED | CLARK | 2012-10-18 | 2013-02-20 | 2013-02-22 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FM5K8B85DGC16212 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FD0W4HT8LEE49093 | 1004 | 11E | C728 | C280 | C728 | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | 23188 | DIESEL | CHURCHILL | 2020-03-10 | 2021-01-12 | 2021-11-17 |  |  |  | A | New - Nov 2022 | Fallon Maintenance Crew 1 | Fallon | District 2 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2BT1DEA24087 | 1006 | 3 | C725 | C171 | C725 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 153767 | DIESEL | NYE | 2012-10-18 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 | 3/4 Ton Pickups | Yes | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH0HZ225814 | 1008 | 5 | C721 | C013 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 E-85 | 59932 | E-85 | CLARK | 2016-12-02 | 2017-02-24 | 2017-05-17 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRNDL4MG526167 | 1009 | 11J | C726 | C726 | C726 | 2020 | RAM | 5500 | 2020 RAM 5500 4X4 UTILITY TRUCK | 0 | DIESEL | HUMBOLDT | 2020-09-27 | 2021-05-06 | 2021-06-08 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2BT3DEA24088 | 1011 | 3 | C721 | C902 | C721 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | 117778 | DIESEL | NYE | 2012-10-18 | 2012-12-14 | 2012-12-14 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2BT5DEA24089 | 1012 | 3 | C721 | C906 | C721 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | 148005 | BIO DIESEL | CLARK | 2012-10-18 | 2012-12-21 | 2013-01-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT6LEE49092 | 1015 | 11E | C728 | C237 | C728 | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | 13904 | DIESEL | MINERAL | 2020-03-10 | 2021-02-09 | 2022-02-28 |  |  |  | A | New - Nov 2022 | Hawthrone Maintenance Crew | Fallon | District 2 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTZPGDR0HHA25939 | 1021 | 11B | C722 | C722 | C722 | 1986 | INTL | 2574 | REBUILD CRANE TRUCK | 2562 | DIESEL | CARSON CITY | 1987-02-06 | 1987-02-06 | 2013-11-15 | SPICER/COMMERCIAL | IMT | A | A |  | Carson City District Repair Shop | Carson City | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FT7W2BT1DEA24090 | 1023 | 3 | C721 | C178 | C721 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 170627 | DIESEL | LINCOLN | 2012-10-19 | 2012-12-14 | 2013-01-08 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | Yes | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New |  | #N/A | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FT7W2BT3DEA24091 | 1025 | 3 | C767 | C250 | C767 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 138564 | DIESEL | CARSON CITY | 2012-10-19 | 2012-12-21 | 2013-01-10 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2BT9DEA24092 | 1026 | 3 | C767 | C201 | C767 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | 94006 | BIO DIESEL | WASHOE | 2012-10-19 | 2012-12-14 | 2013-01-11 |  |  | A | A |  | Reno District Administration | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2BT0DEA24093 | 1027 | 3 | C767 | C201 | C767 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 119128 | BIO DIESEL | WASHOE | 2012-10-19 | 2012-12-21 | 2013-01-11 |  |  | A | A |  | Reno District Administration | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF8HKC87009 | 1028 | 5 | C727 | C013 | C727 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 19965 | FLEX FUEL | CARSON CITY | 2016-12-13 | 2017-04-24 | 2017-12-04 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2BT2DEA24094 | 1029 | 3 | C728 | C280 | C728 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 195328 | DIESEL | CHURCHILL | 2012-10-19 | 2012-12-14 | 2013-01-11 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHR9TH229987 | 1031 | 12 | C723 | C351 | C723 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 186106 | DIESEL | ELKO | 1995-10-04 | 1996-01-10 | 1996-01-10 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1995 PLOW,1995 SANDER,2021 SCORPION ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B61DEA24095 | 1033 | 3 | C723 | C327 | C723 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 155025 | UNLEADED | ELKO | 2012-10-19 | 2012-12-21 | 2013-01-14 |  |  | A | A |  | North Fork Maintenance Crew | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7X2B61DEA24095 | Yes-Pilot |  |  |  | 11.29.2022 | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1HTGEAHROTH229988 | 1034 | 12 | C725 | C173 | C725 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 211012 | DIESEL | NYE | 1995-11-03 | 1995-11-03 | 1995-11-03 |  |  | A | A |  | Blue Jay Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1996 SANDER,PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B63DEA40363 | 1036 | 3 | C723 | C331 | C723 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 245551 | UNLEADED | ELKO | 2012-10-19 | 2013-01-30 | 2013-01-30 |  |  | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7X2B63DEA40363 | Yes |  |  |  | 11.30.2022
1FT7X2B65DEA24097 | 1037 | 3 | C724 | C319 | C724 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 162490 | UNLEADED | WHITE PINE | 2012-10-19 | 2012-12-14 | 2012-12-14 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH4HZ220230 | 1038 | 5 | C721 | C017 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 49516 | E-85 | CLARK | 2016-12-02 | 2017-02-22 | 2017-07-17 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B67DEA24098 | 1039 | 3 | C726 | C374 | C726 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 119209 | UNLEADED | HUMBOLDT | 2012-10-19 | 2012-12-14 | 2013-01-11 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B69DEA24099 | 1043 | 3 | C722 | C017 | C722 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 144772 | UNLEADED | CARSON CITY | 2012-10-19 | 2012-12-14 | 2013-01-14 |  |  | A | A |  | Location | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCVKNEC0JG303238 | 1044 | 5 | C767 | C255 | C767 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | 36013 | FLEX FUEL | WASHOE | 2017-12-13 | 2018-04-11 | 2018-11-09 |  |  | A | A |  | Reno Bridge Maintenance Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH8HZ224460 | 1048 | 5 | C721 | C017 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 30112 | E-85 | CLARK | 2016-12-02 | 2017-03-07 | 2017-07-07 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH9HZ221941 | 1049 | 5 | C727 | C017 | C727 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 41787 | FLEX FUEL | CARSON CITY | 2016-12-02 | 2017-02-28 | 2017-04-17 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B61DEA24100 | 1053 | 3 | C721 | C017 | C721 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 117602 | UNLEADED | CLARK | 2012-10-19 | 2012-12-14 | 2013-01-14 |  |  | A | A |  | Location | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GDHC34J5ME526854 | 1054 | 11F | C725 | C725 | C725 | 1991 | GMC | TC31A | SERVICE TRUCK W/FLATBED | 98964 | DIESEL | NYE | 1991-04-15 | 1991-07-02 | 1991-07-02 |  |  | A | A |  | Tonopah District Repair Shop | Tonopah | District 1 |  | Yes | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH2HZ235857 | 1059 | 5 | C727 | C056 | C727 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 22040 | FLEX FUEL | CARSON CITY | 2016-12-12 | 2017-03-07 | 2017-05-24 |  |  | A | A |  | Architectural | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2BT6DEA24101 | 1061 | 3 | C723 | C324 | C723 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 184721 | DIESEL | ELKO | 2012-10-19 | 2012-12-21 | 2013-01-15 |  |  | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7X2BT6DEA24101 |  |  |  |  | 11.29.2022
1HTGEAHR2TH229989 | 1062 | 12 | C720 | C127 | C720 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 97069 | DIESEL | CLARK | 1995-11-03 | 1995-11-03 | 1995-11-03 |  |  | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SWENSON 1996 SANDER,ONE WAY | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHR9TH229990 | 1063 | 12 | C767 | C252 | C767 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 131640 | DIESEL | WASHOE | 1995-10-25 | 1996-01-10 | 1996-01-10 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,8 Yard Sander | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTNF1EFXDKD70339 | 1064 | 5 | C725 | C104 | C725 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 90503 | UNLEADED | NYE | 2012-10-19 | 2012-12-10 | 2012-12-10 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | ½ Ton Pickups | Yes | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH5HZ221822 | 1067 | 5 | C721 | C926 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 54024 | E-85 | CLARK | 2016-11-30 | 2017-02-22 | 2017-05-18 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH1HZ221493 | 1070 | 5 | C721 | C926 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 54221 | E-85 | CLARK | 2016-11-30 | 2017-02-28 | 2017-06-06 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT4LEE49091 | 1072 | 11H | C725 | C173 | C725 | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | 12382 | DIESEL | NYE | 2020-02-28 | 2021-01-05 | 2022-02-08 |  |  |  | A | New - Nov 2022 | Blue Jay Maintenance Crew | Tonopah | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTZPGDR7HHA26117 | 1073 | 11B | C726 | C726 | C726 | 1987 | INTL | F2574 | CRANE TRUCK | 261486 | DIESEL | HUMBOLDT | 1987-02-11 | 1987-04-09 | 1987-04-09 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTMF1CM9DKD83998 | 1075 | 5 | C721 | C902 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 74276 | E-85 | CLARK | 2012-10-12 | 2013-01-02 | 2013-01-02 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAHT2TH230257 | 1076 | 13 | C724 | C384 | C724 | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 168397 | DIESEL | WHITE PINE | 1995-12-19 | 1996-01-10 | 2012-12-03 | COMMERCIAL INTERTECH |  | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | MODEL #12-99 TENCO 12' REVERSIBLE,8 YARD SANDER,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM0DKD83999 | 1078 | 5 | C721 | C901 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 100604 | E-85 | CLARK | 2012-10-15 | 2013-01-02 | 2013-02-07 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAHT4TH230258 | 1079 | 13 | C722 | C271 | C722 | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | 249120 | DIESEL | CARSON CITY | 1995-11-16 | 1995-12-07 | 1995-12-07 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK SANDER MODEL 15LMC5H | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM1DKD84000 | 1083 | 5 | C721 | C901 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 79112 | E-85 | CLARK | 2012-10-19 | 2013-01-07 | 2013-01-07 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM3DKD84001 | 1084 | 5 | C721 | C903 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 60516 | E-85 | CLARK | 2012-10-12 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH6HZ222929 | 1086 | 5 | C721 | C926 | C721 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 34727 | E-85 | CLARK | 2016-11-30 | 2017-03-08 | 2017-06-06 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM5DKD84002 | 1088 | 5 | C720 | C101 | C720 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 129527 | E-85 | CLARK | 2012-10-12 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FTMF1CM5DKD84002 | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot 10/12/2022: Updated the existing go device column to "Yes" based on the device list received from Norma
1M2K197CX4M024861 | 1089 | 77 | C767 | C241 | C725 | 2003 | MACK | MR688S | LINE STRIPER 700 GALLON | 158935 | DIESEL | WASHOE | 2003-06-27 | 2004-04-09 | 2004-05-05 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes |  |  |  | 10/13/2022: Unit No 772 and 1089. One of these two vehicles is out of service. The vehicle for pilot will be one of these two vehicles and the new vehicle number with unit number 2381
1GCNCNEH6HZ220789 | 1090 | 5 | C722 | C907 | C722 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 32081 | FLEX FUEL | CARSON CITY | 2016-11-30 | 2017-02-17 | 2017-05-15 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM7DKD84003 | 1091 | 5 | C721 | C906 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 104674 | E-85 | CLARK | 2012-10-12 | 2013-01-07 | 2013-01-07 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM9DKD84004 | 1093 | 5 | C721 | C101 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 88598 | E-85 | CLARK | 2012-10-12 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM9DKD84004 |  |  |  |  | 11.22.2022
1M2K197C94M024754 | 1094 | 77 | C723 | C340 | C723 | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | 202060 | DIESEL | ELKO | 2003-06-27 | 2004-04-09 | 2004-05-03 |  |  | A | A |  | Elko Striping Crew | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GCNCNEH4HZ224890 | 1095 | 5 | C722 | C907 | C722 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 50946 | FLEX FUEL | CARSON CITY | 2016-11-30 | 2017-03-03 | 2017-05-23 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH4HZ223352 | 1096 | 5 | C723 | C908 | C723 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 34154 | FLEX FUEL | ELKO | 2016-11-30 | 2017-02-28 | 2017-06-13 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCNEH4HZ223352 |  |  |  |  | 11.28.2022
1FTMF1CM0DKD84005 | 1097 | 5 | C721 | C906 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 102921 | E-85 | CLARK | 2012-10-12 | 2013-01-14 | 2013-01-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM2DKD84006 | 1099 | 5 | C721 | C906 | C721 | 2013 | FORD | F-150 | 1/2 TON PICK UP TRUCK E85 | 96997 | E-85 | CLARK | 2012-10-12 | 2013-01-14 | 2013-01-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAXBTX83D802192 | 1100 | 83 | C767 | C011 | C767 | 2003 | PETERBILT | 357 | UNDERBRIDGE INSPECTION TRUCK | 69068 | DIESEL | CARSON CITY | 2002-07-02 | 2003-04-23 | 2003-06-03 |  |  | A | A |  | Structural Design | Carson City | District 2 |  | No | 7 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pilot |  | #N/A
1FMZU73W34ZA62381 | 1102 | 01A | C723 | C723 | C723 | 2004 | FORD | EXPLORER | SUV 4X4 | 134677 | UNLEADED | ELKO | 2003-07-01 | 2004-01-21 | 2004-02-13 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMZU73W34ZA62381 |  |  |  |  | 11.29.2022
1FT7X2B62KEC51759 | 1104 | 3 | C726 | C373 | C726 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | 45936 | UNLEADED | HUMBOLDT | 2018-06-08 | 2018-10-02 | 2019-04-10 |  |  | A | A |  | Quinn River Maintenance Crew | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A | Yes
1FT7X2B60KEC51758 | 1105 | 3 | C726 | C372 | C726 | 2018 | FORD | F-250 | 2018 FORD F-250 LB EXT CAB 4X4 FFUEL | 51854 | UNLEADED | HUMBOLDT | 2018-06-08 | 2018-09-24 | 2018-11-02 |  |  | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH7HZ224544 | 1106 | 5 | C723 | C912 | C723 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 72017 | FLEX FUEL | ELKO | 2016-11-30 | 2017-03-08 | 2017-06-01 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCNEH7HZ224544 |  |  |  |  | 11.28.2022
1HTGEAUR9RH613847 | 1107 | 28 | C724 | C319 | C724 | 1994 | INTL | 2574 | DISTRIBUTOR TRUCK | 83439 | DIESEL | WHITE PINE | 1994-08-26 | 1994-08-26 | 1994-08-26 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GCNCNEH5HZ222811 | 1108 | 5 | C723 | C912 | C723 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 62593 | FLEX FUEL | ELKO | 2016-11-30 | 2017-02-28 | 2017-06-06 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCNEH5HZ222811 |  |  |  |  | 11.28.2022
1FTMF1CM4DKD84007 | 1109 | 5 | C721 | C926 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 64117 | E-85 | CLARK | 2012-10-12 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH3HZ220927 | 1112 | 5 | C723 | C908 | C723 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 39104 | FLEX FUEL | ELKO | 2016-11-30 | 2017-02-17 | 2017-06-13 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCNEH3HZ220927 |  |  |  |  | 11.28.2022
1G1ND52F84M606811 | 1113 | 1 | C721 | C721 | C721 | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 95706 | UNLEADED | CLARK | 2003-07-01 | 2004-01-16 | 2004-01-30 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ND52F84M606811
1FTMF1CM6DKD84008 | 1115 | 5 | C721 | C902 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 113564 | E-85 | CLARK | 2012-10-12 | 2013-01-14 | 2013-01-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM8DKD84009 | 1117 | 5 | C721 | C901 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | 114418 | E-85 | CLARK | 2012-10-18 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH8HZ223032 | 1118 | 5 | C723 | C033 | C723 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 42290 | FLEX FUEL | ELKO | 2016-11-30 | 2017-02-28 | 2017-05-18 |  |  | A | A |  | Right of Way Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCNEH8HZ223032 |  |  |  |  | 11.29.2022
1HTGGAHT0TH230259 | 1119 | 13 | C722 | C271 | C722 | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | 250203 | DIESEL | CARSON CITY | 1995-12-22 | 1996-01-10 | 1996-01-10 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | ATTENUATOR TRUCK MOUNTED,FLINK 8CU YD-15 LMC 5H | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B69KEC51757 | 1120 | 3 | C726 | C096 | C726 | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 15464 | UNLEADED | ELKO | 2018-06-07 | 2018-10-02 | 2019-01-09 |  |  | A | A |  | Communications Winnemucca | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMZU72K74ZA62382 | 1122 | 01A | C721 | A067 | C721 | 2004 | FORD | EXPLORER | AWD SUV | 55408 | E-85 | CLARK | 2003-07-01 | 2004-01-22 | 2004-06-01 |  |  | A | A |  | Information Services | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM4DKD84010 | 1124 | 5 | C720 | C901 | C720 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 82737 | E-85 | CLARK | 2012-10-12 | 2013-01-15 | 2013-01-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCNEH4HZ225800 | 1125 | 5 | C726 | C920 | C726 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 36461 | FLEX FUEL | HUMBOLDT | 2016-11-30 | 2017-02-24 | 2017-05-15 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC2KUEG7JZ253166 | 1126 | 3 | C721 | C813 | C721 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 67951 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-03-20 | 2018-05-11 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM6DKD84011 | 1127 | 5 | C721 | C906 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 115639 | E-85 | CLARK | 2012-10-12 | 2013-01-15 | 2013-01-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14W7WZ533839 | 1128 | 5 | C725 | C767 | C725 | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | 207048 | UNLEADED | CLARK | 1998-03-16 | 1998-03-30 | 1998-03-30 |  |  | D | D |  | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM8DKD84012 | 1129 | 5 | C721 | C926 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 68777 | E-85 | CLARK | 2012-10-12 | 2013-01-08 | 2013-01-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CMXDKD84013 | 1131 | 5 | C721 | C915 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 52470 | E-85 | CLARK | 2012-10-12 | 2013-01-14 | 2013-01-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAUR8SH620174 | 1132 | 28 | C721 | C152 | C721 | 1995 | INTL | 2574 | TRUCK W/ASPHALT PATCHER | 78448 | DIESEL | CLARK | 1994-08-29 | 1994-09-28 | 1994-09-28 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FTMF1CM1DKD84014 | 1134 | 5 | C721 | C101 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 100300 | E-85 | CLARK | 2012-10-12 | 2013-01-14 | 2013-01-15 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM1DKD84014 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1HTGGAHRXXH211062 | 1135 | 11B | C767 | C241 | C767 | 1999 | INTL | F257A | CRANE TRUCK | 266585 | DIESEL | WASHOE | 1999-06-11 | 1999-06-11 | 1999-06-25 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pilot |  | #N/A |  | Yes
1NPTL70X5JD487192 | 1137 | 13 | C721 | C129 | C721 | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | 25000 | DIESEL | CLARK | 2017-06-29 | 2018-02-08 | 2018-11-09 | DANFOSS | DANFOSS | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | HENKE SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM3DKD84015 | 1139 | 5 | C720 | C159 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 147297 | E-85 | CLARK | 2012-10-12 | 2013-01-14 | 2013-01-16 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
RS685LST55282 | 1142 | 25 | C725 | C170 | C725 | 1980 | MACK | RS685 | TANDEM AXLE WATER TRUCK | 342037 | DIESEL | NYE | 1980-06-11 | 1980-06-11 | 1980-06-11 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRLFJ7MG643628 | 1143 | 11H | C767 | C242 | C767 | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 FLATRACK 4X4 | 2526 | UNLEADED | WASHOE | 2021-02-23 | 2021-08-05 | 2022-07-19 | MAXON |  |  | A | New - Nov 2022 | Reno Pavement Markings | Reno | District 2 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GDKC34J7XF025744 | 1144 | 11D | C721 | C124 | C721 | 1999 | GMC | TC31403 | COMPACTOR TRUCK | 147204 | UNLEADED | CLARK | 1999-07-09 | 1999-07-09 | 1999-07-30 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F5XED06250 | 1147 | 11E | C721 | C145 | C721 | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | 171257 | DIESEL | CLARK | 1999-03-10 | 1999-06-09 | 1999-06-09 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
#N/A | 1150 | 4 | C727 | C813 | #N/A | 2004 | FORD | ECONO | CARGO VAN | 142379 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Planning Traffic | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
1FTMF1CM5DKD84016 | 1151 | 5 | C721 | C901 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 87268 | E-85 | CLARK | 2012-10-12 | 2013-01-24 | 2013-01-31 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GAGG25U241168586 | 1152 | 4 | C724 | C724 | C724 | 2004 | CHEVROLET | EXPRESS | 12 PASSENGER VAN | 97534 | UNLEADED | WHITE PINE | 2003-07-01 | 2004-01-16 | 2004-02-23 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRNEL6MG601949 | 1153 | 11H | C767 | C271 | C767 | 2021 | RAM | 5500 | 2021 DODGE RAM 5500 FLATRACK 4 X 4 | 1849 | DIESEL | WASHOE | 2021-01-06 | 2021-09-10 | 2022-09-12 |  |  |  | A | New - Nov 2022 | Carson City Maintenance Crew 2 | Carson City | District 2 |  |  | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC2KUEG6JZ257211 | 1155 | 3 | C767 | C813 | C767 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 68245 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-03-20 | 2018-06-20 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM7DKD84017 | 1157 | 5 | C721 | C153 | C721 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 141825 | E-85 | CLARK | 2012-10-12 | 2013-01-28 | 2013-01-31 |  |  | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC2KUEG1JZ251719 | 1158 | 3 | C767 | C813 | C722 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON VHEVY SILVERADO 2500 4X4 | 44501 | TELEMATIC | CARSON CITY | 2017-12-05 | 2018-03-07 | 2018-07-17 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM9DKD84018 | 1159 | 5 | C723 | C040 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 119168 | UNLEADED | ELKO | 2012-10-16 | 2013-01-24 | 2013-01-31 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [5 empty] | 2014 PROFILING SYSTEM PANASONIC TOUGHBOO | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 1FTMF1CM9DKD84018 |  |  |  |  | 11.29.2022
1FTMF1CM0DKD84019 | 1161 | 5 | C723 | C908 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 164042 | UNLEADED | ELKO | 2012-10-16 | 2013-01-30 | 2013-02-04 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM0DKD84019 |  |  |  |  | 11.28.2022
1GC2KUEG5JZ255692 | 1162 | 3 | C721 | C813 | C721 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 34924 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-03-20 | 2018-07-02 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM7DKD84020 | 1164 | 5 | C723 | C908 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 109855 | UNLEADED | ELKO | 2012-10-16 | 2013-01-17 | 2013-01-18 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM7DKD84020 |  |  |  |  | 11.28.2022
1FTMF1CM9DKD84021 | 1165 | 5 | C723 | C908 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 130408 | UNLEADED | ELKO | 2012-10-16 | 2013-01-17 | 2013-01-18 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM9DKD84021 |  |  |  |  | 11.28.2022
1FTMF1CM0DKD84022 | 1166 | 5 | C723 | C918 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 81455 | UNLEADED | ELKO | 2012-10-16 | 2013-01-28 | 2013-02-04 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM0DKD84022 |  |  |  |  | 11.29.2022
1FTMF1CM2DKD84023 | 1169 | 5 | C723 | C908 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 89053 | UNLEADED | ELKO | 2012-10-18 | 2013-01-14 | 2013-01-16 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM2DKD84023 |  |  |  |  | 11.28.2022
1FM5K8B87HGC14533 | 1170 | 01A | C727 | C018 | C727 | 2017 | FORD | EXPLORER | 4X4 SUV | 21739 | UNLEADED | CARSON CITY | 2016-11-30 | 2017-04-24 | 2017-08-10 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM4DKD84024 | 1171 | 5 | C723 | C912 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 84551 | UNLEADED | ELKO | 2012-10-18 | 2013-01-14 | 2013-01-16 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM4DKD84024 |  |  |  |  | 11.28.2022
#N/A | 1172 | 5 | C767 | C767 | #N/A | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK AFV | 193120 | BI-FUEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1FTMF1CM6DKD84025 | 1173 | 5 | C723 | C912 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 132419 | UNLEADED | ELKO | 2012-10-18 | 2013-01-14 | 2013-01-16 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM6DKD84025 |  |  |  |  | 11.29.2022
1FTMF1CM8DKD84026 | 1174 | 5 | C723 | C301 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 110132 | UNLEADED | ELKO | 2012-10-18 | 2013-01-14 | 2013-01-16 |  |  | A | A |  | Elko District Administration | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM8DKD84026 |  |  |  |  | 11.29.2022
1FTEX1EF9HKD20728 | 1178 | 5 | C721 | C179 | C721 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 33947 | E-85 | CLARK | 2017-02-01 | 2017-04-24 | 2017-06-20 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CMXDKD84027 | 1179 | 5 | C723 | C912 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 123523 | UNLEADED | ELKO | 2012-10-18 | 2013-01-28 | 2013-02-04 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CMXDKD84027 |  |  |  |  | 11.28.2022
1FTMF1CM1DKD84028 | 1180 | 5 | C723 | C918 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 85417 | UNLEADED | ELKO | 2012-10-18 | 2013-01-17 | 2013-01-18 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM1DKD84028 |  |  |  |  | 11.28.2022
1FTEX1EF7HKD20730 | 1182 | 5 | C721 | C179 | C721 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 29761 | E-85 | CLARK | 2017-02-01 | 2017-04-24 | 2017-06-20 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot New |  | #N/A | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that these vehicle need to get into Pre-Pilot
1FTMF1CM3DKD84029 | 1183 | 5 | C723 | C908 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 107276 | UNLEADED | ELKO | 2012-10-18 | 2013-01-17 | 2013-01-18 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM3DKD84029 |  |  |  |  | 11.28.2022
1FD0X4HY6HEE20434 | 1184 | 11H | C721 | C179 | C726 | 2017 | FORD | F-450 | FLATRACK TRUCK 4X4 | 43113 | UNLEADED | HUMBOLDT | 2017-04-27 | 2017-12-22 | 2018-04-19 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTMF1CMXDKD84030 | 1185 | 5 | C723 | C912 | C723 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 91998 | UNLEADED | ELKO | 2012-10-18 | 2013-01-14 | 2013-01-16 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CMXDKD84030 |  |  |  |  | 11.28.2022
1FTFX1EF7DFA75337 | 1186 | 5 | C767 | C204 | C767 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 188457 | RFG | WASHOE | 2012-10-19 | 2012-12-21 | 2013-01-16 |  |  | A | A |  | Permits | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF9DFA75338 | 1187 | 5 | C767 | C240 | C767 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 86057 | RFG | WASHOE | 2012-10-19 | 2012-12-17 | 2013-01-17 |  |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14V54E317242 | 1188 | 5 | C722 | C911 | C722 | 2004 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | 156376 | UNLEADED | CARSON CITY | 2003-07-02 | 2004-04-29 | 2004-05-24 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAHT4TH230261 | 1189 | 13 | C722 | C271 | C722 | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 83957 | DIESEL | CARSON CITY | 1995-11-16 | 1996-01-24 | 2011-05-01 | COMMERCIAL INTERTECH |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1995 SANDER,HEAVY DUTY PATROL WING,FRINK 12' PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF0DFA75339 | 1191 | 5 | C724 | C034 | C767 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 97870 | UNLEADED | WHITE PINE | 2012-10-19 | 2012-12-21 | 2013-01-17 |  |  | A | D |  | Right of Way Ely | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH6HG324083 | 1193 | 5 | C767 | C218 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 22766 | FLEX FUEL | WASHOE | 2016-12-14 | 2017-03-08 | 2017-09-18 |  |  | A | A |  | Reno Storm Water Inspection Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF6DKD70341 | 1194 | 5 | C724 | C319 | C724 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 197526 | UNLEADED | WHITE PINE | 2012-10-19 | 2012-12-06 | 2012-12-06 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F9XED06249 | 1196 | 11E | C721 | C153 | C721 | 1999 | FORD | F-450 | REBUILD DUMP TRUCK | 119987 | DIESEL | CLARK | 1999-03-22 | 1999-06-09 | 2014-07-17 |  |  | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GC1KUEG3JF209596 | 1197 | 3 | C767 | C905 | C767 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 31122 | TELEMATIC | WASHOE | 2017-12-12 | 2018-03-01 | 2018-07-20 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF8DKD70342 | 1198 | 5 | C726 | C370 | C726 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 142891 | UNLEADED | HUMBOLDT | 2012-10-19 | 2012-12-21 | 2013-01-17 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEH1HG317719 | 1200 | 5 | C767 | C218 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 38285 | FLEX FUEL | WASHOE | 2016-12-13 | 2017-02-22 | 2017-06-20 |  |  | A | A |  | Reno Storm Water Inspection Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTZML6R2EHA46365 | 1201 | 11G | C721 | C127 | C721 | 1984 | INTL | F2574 | ATTENUATOR TRUCK SINGLE AXLE | 182660 | DIESEL | CLARK | 1984-06-21 | 1984-06-21 | 1984-06-21 |  |  | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F7XED06251 | 1203 | 11E | C721 | C121 | C721 | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | 85639 | DIESEL | CLARK | 1999-03-10 | 1999-06-09 | 1999-06-09 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | SANDER | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAHT8TH230263 | 1204 | 13 | C767 | C234 | C767 | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | 120803 | DIESEL | STOREY | 1995-12-20 | 1996-01-29 | 1996-01-29 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 12' ONE WAY,11 FT REVERSIBLE SNOW PLOW,SPRAYER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG7JF211738 | 1205 | 3 | C722 | C907 | C722 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVRADO 2500 4X4 | 50314 | UNLEADED | CARSON CITY | 2017-12-08 | 2018-03-08 | 2018-09-10 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFW1EF0DKD70340 | 1206 | 5 | C767 | C225 | C767 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 203325 | UNLEADED | WASHOE | 2012-10-12 | 2012-12-14 | 2013-01-17 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HY4HED21081 | 1207 | 11E | C767 | C279 | C767 | 2017 | FORD | F-450 | DUMP TRUCK 4X4 | 98714 | RFG | WASHOE | 2017-02-01 | 2017-05-15 | 2017-12-04 |  |  | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD8W3GTXDEA26760 | 1212 | 11J | C721 | C102 | C721 | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | 78680 | BIO DIESEL | CLARK | 2012-10-19 | 2013-01-25 | 2013-02-04 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 1FD8W3GTXDEA26760
1HTGEGBR6LH207716 | 1213 | 11F | C723 | C723 | C723 | 1989 | INTL | 2574 | SERVICE TRUCK W/CRANE | 314458 | DIESEL | ELKO | 1989-09-20 | 1990-02-07 | 1990-02-07 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4HY8HED94504 | 1214 | 11H | C723 | C379 | C723 | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | 34456 | UNLEADED | ELKO | 2017-03-13 | 2018-02-08 | 2018-03-07 |  |  | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4HY8HED94504 |  |  |  |  | 11.29.2022
1FTEX1EF9HKD20731 | 1215 | 5 | C723 | C355 | C723 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 39505 | FLEX FUEL | ELKO | 2017-02-01 | 2017-04-24 | 2017-07-27 |  |  | A | A |  | Elko Bridge Maintenance Crew | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1EF9HKD20731 |  |  |  |  | 11.29.2022
1FT8X3BT5DEA24102 | 1216 | 6 | C767 | C092 | C767 | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 BIO-DIESEL | 336351 | BIO DIESEL | WASHOE | 2012-10-19 | 2012-12-20 | 2013-01-18 |  |  | A | A |  | Communications Reno | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGEGBR8LH207717 | 1217 | 12 | C720 | C178 | C720 | 1989 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 9307 | DIESEL | CLARK | 1989-09-20 | 1989-09-20 | 1989-09-20 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1989 PLOW,SWENSON | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD8W3G60DEA26759 | 1218 | 10 | C767 | C904 | C767 | 2013 | FORD | F-350 | SURVEY UNIT | 156500 | RFG | WASHOE | 2012-10-19 | 2013-01-25 | 2013-02-05 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTSDAAN3WH562811 | 1219 | 20 | C723 | C350 | C723 | 1998 | INTL | 4900 | 1998 CULVERT CLEANER | 13247 | DIESEL | ELKO | 2019-04-04 | 2019-04-12 | 2019-08-20 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEDV3LPLX5846 | 1220 | 13 | C723 | C327 | C723 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TUCK | 16076 | DIESEL | ELKO | 2019-02-14 | 2020-06-02 | 2020-07-31 | PARKER | DANFOSS | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW,2019 HENKE SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot |  |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
5KKHAEDV5LPLX5847 | 1221 | 13 | C724 | C385 | C724 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 8661 | DIESEL | WHITE PINE | 2019-05-17 | 2020-05-04 | 2020-12-29 | PARKER | DANFOSS | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT5DEA64156 | 1222 | 11E | C723 | C322 | C723 | 2013 | FORD | F-450 | DUMP TRUCK | 327136 | DIESEL | ELKO | 2012-11-28 | 2013-01-01 | 2013-06-27 |  |  | A | A |  | Contact Maintenance Crew | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2FTPF17Z64CA81771 | 1223 | 5 | C767 | C905 | C767 | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 132238 | RFG | WASHOE | 2003-07-02 | 2004-06-28 | 2004-08-25 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1EF0HKD20729 | 1224 | 5 | C723 | C335 | C723 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 63422 | FLEX FUEL | ELKO | 2017-02-01 | 2017-04-24 | 2017-12-01 |  |  | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GY7DEA64221 | 1227 | 11H | C723 | C336 | C723 | 2013 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | 267597 | UNLEADED | ELKO | 2012-11-28 | 2013-02-01 | 2013-06-07 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4HY4HEE28163 | 1228 | 11E | C767 | C279 | C767 | 2017 | FORD | F-450 | CAMERA TRUCK | 57582 | UNLEADED | LYON | 2017-05-11 | 2017-09-15 | 2018-06-07 |  |  | A | A |  | Reno Storm Water Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | CULVERT INSPECTION CAMERA | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4HY8HEE28165 | 1231 | 11E | C723 | C379 | C723 | 2017 | FORD | F-450 | CAMERA TRUCK | 37736 | UNLEADED | ELKO | 2017-05-11 | 2017-09-21 | 2018-10-18 |  |  | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | CULVERT INSPECTION CAMERA | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4HY8HEE28165 |  |  |  |  | 11.29.2022
5KKHAEDV7LPLX5848 | 1232 | 13 | C721 | C178 | C721 | 2020 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 5092 | DIESEL | WASHOE | 2019-05-17 | 2020-06-23 | 2020-12-29 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FD0W4HY6HEE28164 | 1234 | 11E | C767 | C251 | C767 | 2017 | FORD | F-450 | 1-2 TON DUMP/GARBAGE TRUCK | 69840 | UNLEADED | ELKO | 2017-05-11 | 2017-09-15 | 2018-01-25 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  | GO9 |  |  | CULVERT INSPECTION CAMERA,2018 SNOWDOGG EX80II SNOW PLOW,2018 SALTDOGG SANDER SHPE2000 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FD0W4HY6HEE28164
1FD0W4GTXDEA64220 | 1235 | 11H | C723 | C324 | C723 | 2013 | FORD | F-450 | FLATRACK W/LIFTGATE | 185411 | DIESEL | ELKO | 2012-11-28 | 2013-05-08 | 2013-05-08 |  |  | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GTXDEA64220 |  |  |  |  | 11.29.2022
#N/A | 1236 | 11J | C723 | C355 | #N/A | 2013 | FORD | F-450 | UTILITY TRUCK W/LIFTGATE | 171982 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Elko Bridge Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FD0W4HT7DEA64223 | 1239 | 11H | C726 | C374 | C767 | 2013 | FORD | F-450 | FLATRACK TRUCK 4X4 | 138572 | DIESEL | HUMBOLDT | 2012-11-28 | 2013-02-15 | 2013-05-20 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2021 ASPHALT HOTBOX | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NKBLJ0X8JR208738 | 1240 | 20 | C721 | C158 | C721 | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | 20706 | DIESEL | CLARK | 2017-06-05 | 2018-02-28 | 2018-04-18 | DANFOSS | VACTOR | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FDUF4GT1DEA64155 | 1241 | 11E | C724 | C382 | C724 | 2013 | FORD | F-450 | DUMP TRUCK | 150479 | DIESEL | WHITE PINE | 2012-11-28 | 2013-02-15 | 2013-06-13 |  |  | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GC1KUEG0JF220488 | 1242 | 3 | C726 | C920 | C726 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 29148 | UNLEADED | HUMBOLDT | 2017-12-08 | 2018-04-19 | 2018-06-27 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2BT3DEA69237 | 1243 | 3 | C728 | C236 | C728 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 144709 | DIESEL | LYON | 2012-12-29 | 2013-03-05 | 2013-03-05 |  |  | A | A |  | Yerington Maintenance Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NKBLJ0X6JR208737 | 1244 | 20 | C723 | C379 | C723 | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | 14417 | DIESEL | WASHOE | 2017-06-05 | 2018-02-28 | 2018-04-18 | DANFOSS | VACTOR | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GC1KUEG3JF211834 | 1246 | 3 | C722 | C247 | C722 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 13958 | UNLEADED | CARSON CITY | 2017-12-13 | 2018-03-01 | 2018-05-30 |  |  | A | A |  | Carson City Landscape Crew 3 | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF1DFB84652 | 1248 | 5 | C767 | C904 | C767 | 2013 | FORD | F-150 | 2013 1/2 TON PICKUP TRUCK | 71770 | RFG | WASHOE | 2012-10-18 | 2013-04-01 | 2013-04-01 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NKBLJ0X4JR208736 | 1249 | 20 | C767 | C252 | C767 | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | 9955 | DIESEL | WASHOE | 2017-06-05 | 2018-02-28 | 2018-04-18 | DANFOSS | VACTOR | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FTFW1EF8DKE41106 | 1250 | 5 | C767 | C201 | C767 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 138453 | RFG | WASHOE | 2012-10-18 | 2013-04-01 | 2013-04-01 |  |  | A | A |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2BT6DEA24096 | 1251 | 3 | C722 | C722 | C722 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 77394 | DIESEL | CARSON CITY | 2012-12-29 | 2013-02-05 | 2013-02-05 |  |  | A | A |  | Carson City District Repair Shop | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCVKNEH4JZ130081 | 1252 | 5 | C767 | C737 | C767 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 11661 | FLEX FUEL | WASHOE | 2017-06-16 | 2017-08-28 | 2017-11-20 |  |  | A | A |  | Equipment Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 1253 | 10 | C767 | C910 | #N/A | 2005 | FORD | F-450 | SURVEY UNIT | 125518 | RFG | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Construction Crew Reno | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A |  | Yes
1FVACXFC0JHJV4642 | 1254 | 24 | C721 | C154 | C721 | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 19602 | DIESEL | CLARK | 2017-05-30 | 2018-01-17 | 2018-03-21 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXFC0JHJV4642 |  | Yes
1GC1KUEGXJF209000 | 1255 | 3 | C722 | C235 | C722 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 103740 | UNLEADED | LYON | 2017-12-13 | 2018-03-07 | 2018-05-01 |  |  | A | A |  | Wellington Maintenance Crew | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG9JF208680 | 1257 | 3 | C722 | C201 | C722 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | 89274 | TELEMATIC | WASHOE | 2017-12-13 | 2018-03-19 | 2018-08-16 |  |  | A | A |  | Reno District Administration | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXFC9JHJV4641 | 1258 | 24 | C721 | C159 | C721 | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | 20182 | DIESEL | CLARK | 2017-05-30 | 2018-02-14 | 2018-05-02 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FVACXFC7JHJV4640 | 1259 | 24 | C721 | C159 | C721 | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | 19847 | DIESEL | CLARK | 2017-05-30 | 2018-03-09 | 2018-05-02 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FDUF4GT7HEF26370 | 1261 | 11E | C721 | C150 | C721 | 2017 | FORD | F-450 | DUMP TRUCK | 43451 | BIO DIESEL | CLARK | 2017-08-17 | 2018-02-09 | 2018-04-11 | BUCHER |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  | GO9 |  |  |  | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FDUF4GT7HEF26370 | [5 empty] | 12/14/2022: VIN Number has been updated based on the email received from Billie
1FDXF46P25EA24511 | 1263 | 11F | C721 | C145 | C721 | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | 159371 | BIO DIESEL | CLARK | 2003-07-02 | 2004-11-30 | 2005-01-12 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1NPTL7OXXJD490895 | 1264 | 13 | C724 | C380 | C724 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 19908 | DIESEL | WHITE PINE | 2017-07-20 | 2018-02-02 | 2019-04-30 | DANFOSS | DANFOSS | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | SANDER,ONE WAY PLOW,WING PLOW PPW9HD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXF46P95EA24506 | 1265 | 11H | C720 | C142 | C720 | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | 207037 | BIO DIESEL | CLARK | 2003-07-02 | 2004-11-03 | 2005-01-13 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | MESSAGE SIGN, VEHICLE MOUNTED | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1HTWCAAR15J129681 | 1267 | 11A | C726 | C341 | C726 | 2005 | INTL | 7400 | AERIAL TRUCK W/PLATFORM | 28822 | DIESEL | HUMBOLDT | 2003-07-03 | 2005-08-18 | 2005-08-24 |  |  | A | A |  | Winnemucca Striping Crew | Winnemucca | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
4V2JABMD4MN812448 | 1268 | 14 | C767 | C767 | C767 | 1991 | GMC | WG42 | REBUILD TRANSPORT TRUCK | 249108 | DIESEL | WASHOE | 1991-07-30 | 1991-07-30 | 2012-10-19 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVHC5DE75HU88941 | 1269 | 11B | C724 | C724 | C724 | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | 21610 | DIESEL | WHITE PINE | 2003-07-01 | 2005-09-02 | 2005-10-05 | SUNFAB |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4PJMCXXKD168347 | 1270 | 01A | C727 | C727 | C727 | 2018 | JEEP | CHEROKEE | SUV 4X4 | 46959 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-04-17 | 2018-05-30 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVHC5DE55HU88940 | 1274 | 11B | C767 | C241 | C767 | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | 207273 | DIESEL | WASHOE | 2003-07-01 | 2005-09-02 | 2006-05-18 | SUNFAB |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FTEX1C56KKE52315 | 1275 | 5 | C721 | C113 | C721 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 8198 | E-85 | CLARK | 2019-08-14 | 2019-09-26 | 2020-04-15 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPCJK8X3LD645366 | 1279 | 15 | C767 | C234 | C767 | 2020 | PETERBILT | 567 | 2020 TANDEM AXLE 4X4 SANDER/PLOW TRUCK | 2874 | DIESEL | LYON | 2018-06-26 | 2020-03-05 | 2020-05-20 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | No | 6 | J1939 | Roadwatch Sensor |  | GO9+ |  |  | 2018 HENKE 40-65-12NV ONE WAY PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1NPCJK8X3LD645366 |  | Yes
1NPTM70X7LD645368 | 1280 | 15 | C722 | C271 | C722 | 2019 | PETERBILT | 367 | 2019 AWDTANDEM AXLE SANDER/PLOW TRUCK | 12275 | DIESEL | CARSON CITY | 2018-07-30 | 2020-03-12 | 2020-04-14 | DANFOSS | DANFOSS | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GC1KUEG2JF210450 | 1281 | 3 | C767 | C802 | C767 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | 12265 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-03-20 | 2018-05-30 |  |  | A | A |  | Transportation / Multimodal Planning (Landmark) | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FVHC5DE95HU88942 | 1284 | 11B | C724 | C342 | C724 | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | 105777 | DIESEL | WHITE PINE | 2003-07-01 | 2005-08-25 | 2005-10-05 | SUNFAB |  | A | A |  | Ely Striping Crew | Ely | District 3 |  | No | 6 | J1939 | [5 empty] | LITEREADER ARROW BOARD V/M,2020 SCORPION ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C58KKE52316 | 1287 | 5 | C721 | C101 | C721 | 2019 | FORD | F-150 | 2019 FORD F-150 1/2 TON PICK UP | 12726 | E-85 | CLARK | 2019-04-17 | 2019-09-26 | 2020-04-06 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C58KKE52316 |  |  |  |  | 11.22.2022
1FVACYDT1FHFZ4498 | 1297 | 24 | C767 | C252 | C767 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | 38472 | DIESEL | WASHOE | 2013-10-01 | 2014-04-30 | 2014-07-09 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACYDT1FHFZ4498
1FVACYDTXFHFZ4497 | 1298 | 24 | C767 | C253 | C767 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | 31404 | DIESEL | WASHOE | 2013-10-01 | 2014-06-20 | 2014-07-09 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACYDTXFHFZ4497
1FVACYDT3FHFZ4499 | 1299 | 24 | C767 | C250 | C767 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | 31922 | DIESEL | WASHOE | 2013-10-01 | 2014-07-10 | 2014-08-05 |  | PARKER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACYDT3FHFZ4499
1FVACYDT6FHFZ4500 | 1300 | 24 | C722 | C271 | C722 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER DSL | 30043 | DIESEL | CLARK | 2014-06-26 | 2014-07-10 | 2014-08-05 |  | PARKER | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACYDT6FHFZ4500
5KKHAEDV1KPKV7535 | 1301 | 13 | C725 | C172 | C725 | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | 4631 | DIESEL | NYE | 2019-05-14 | 2019-08-08 | 2019-10-08 | PARKER | DANFOSS | A | A |  | Big Smokey Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDVXKPLC8372 | 1302 | 13H | C720 | C154 | C720 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 25313 | DIESEL | NYE | 2018-06-12 | 2019-04-02 | 2019-04-09 | MUNCIE |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 8 | J1939 | [5 empty] | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FDXF46P44ED93109 | 1304 | 11D | C720 | C152 | C720 | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | 218461 | BIO DIESEL | CLARK | 2003-07-01 | 2004-11-23 | 2004-12-27 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot |  | #N/A
5KKHAEDV3KPKV7536 | 1305 | 13 | C725 | C177 | C725 | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | 18625 | DIESEL | WASHOE | 2018-05-14 | 2019-08-07 | 2019-10-08 | PARKER | DANFOSS | A | A |  | Montgomery Pass Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVACYDT8FHFZ4501 | 1308 | 24 | C767 | C251 | C767 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | 26046 | DIESEL | WASHOE | 2013-10-01 | 2014-07-14 | 2014-08-05 |  | PARKER | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACYDT8FHFZ4501
1FDXF46P75EA24519 | 1312 | 11S | C720 | C157 | C720 | 2005 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | 246465 | BIO DIESEL | CLARK | 2003-07-02 | 2004-12-10 | 2005-02-14 | PARKER |  | A | A |  | Las Vegas Night Maintenance Crew 6 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | SWAPLOADER DUMP BODY,SWAPLOADER FLATRACK | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FVACXDTXGHHK8985 | 1313 | 24 | C767 | C243 | C767 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 24685 | DIESEL | WASHOE | 2015-04-30 | 2016-02-04 | 2016-03-21 |  | PARKER | A | A |  | #N/A | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDTXGHHK8985 |  | Yes
5KKHAEDV2KPKV7530 | 1314 | 13 | C725 | C177 | C725 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 13147 | DIESEL | NYE | 2018-05-14 | 2019-06-19 | 2020-01-02 | PARKER | DANFOSS | A | A |  | Montgomery Pass Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE 1-WAY PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXW47Y15EA24524 | 1316 | 11F | C725 | C725 | C725 | 2005 | FORD | F-450 | SERVICE TRUCK W/CRANE | 193298 | UNLEADED | NYE | 2003-07-02 | 2005-03-09 | 2005-03-09 |  |  | A | A |  | Tonopah District Repair Shop | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEDV8KPKV7533 | 1317 | 13 | C767 | C251 | C767 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 5380 | DIESEL | WASHOE | 2018-05-14 | 2019-06-28 | 2020-01-27 | PARKER | DANFOSS | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE EXP11NV REV PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV8KPKV7533 |  | Yes
5KKHAEDVXKPKV7534 | 1318 | 13 | C728 | C236 | C728 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 14990 | DIESEL | LYON | 2018-05-14 | 2019-08-02 | 2020-02-14 | PARKER | DANFOSS | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE EXP11NV REV SNOW PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDVXKPKV7534
5KKHAEDV5KPKV7537 | 1319 | 13 | C722 | C270 | C722 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 19495 | DIESEL | CARSON CITY | 2018-05-14 | 2019-12-13 | 2020-01-15 | PARKER | DANFOSS | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE PPW9HD POSTLESS WING PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV5KPKV7537
1FVACXDT1GHHK8986 | 1320 | 24 | C767 | C252 | C767 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 28411 | DIESEL | WASHOE | 2015-04-30 | 2016-02-02 | 2016-03-21 |  | PARKER | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT1GHHK8986
1FDXX47P35EA24514 | 1322 | 11F | C723 | C093 | C723 | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 | 138965 | DIESEL | ELKO | 2003-11-05 | 2005-03-02 | 2005-03-23 |  |  | A | A |  | Communications Elko | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDXX47P35EA24514 |  |  |  |  | 11.29.2022
1HTZMGBRXJH569752 | 1324 | 11B | C728 | C728 | C728 | 1988 | INTL | 2574 | CRANE TRUCK W/FLATBED | 19418 | DIESEL | CHURCHILL | 1988-01-28 | 1988-01-28 | 1988-01-28 |  |  | A | A |  | Fallon District Repair Shop | Fallon | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTZMGBR0JH569730 | 1325 | 11G | C721 | C121 | C721 | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | 173850 | DIESEL | CLARK | 1988-04-26 | 1988-04-26 | 1988-04-26 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 6 | J1939 | [5 empty] | 2021 SAFE-STOP ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1NPAL09X37D652585 | 1327 | 13 | C767 | C253 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 159622 | DIESEL | WASHOE | 2003-07-01 | 2006-09-29 | 2006-10-18 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW UNDERBODY,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1FVACXDT3GHHK8987 | 1328 | 24 | C767 | C243 | C767 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 26170 | DIESEL | WASHOE | 2015-04-30 | 2016-04-04 | 2016-04-20 |  | PARKER | A | A |  | #N/A | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  | 2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT3GHHK8987
1NPAL09X17D652584 | 1329 | 13 | C728 | C282 | C728 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 180062 | DIESEL | CHURCHILL | 2003-07-01 | 2006-10-09 | 2006-10-18 | PARKER | PARKER | A | A |  | Cold Springs Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT1GHHN1362 | 1330 | 24 | C767 | C243 | C767 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 24323 | DIESEL | WASHOE | 2015-04-30 | 2016-03-28 | 2016-04-15 |  | PARKER | A | A |  | #N/A | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT1GHHN1362
1NPAL09X97D653143 | 1331 | 13 | C723 | C332 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 214880 | DIESEL | ELKO | 2003-07-01 | 2006-09-29 | 2006-11-06 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW WING,SANDER 8 CUBIC YARDS,REVERSIBLE | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV7KPKV7538 | 1332 | 13 | C728 | C283 | C728 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 15483 | DIESEL | PERSHING | 2018-05-14 | 2019-11-22 | 2020-01-13 | PARKER | DANFOSS | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV7KPKV7538
5KKHAEDV9KPKV7525 | 1333 | 13 | C723 | C335 | C723 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 24371 | DIESEL | ELKO | 2018-05-14 | 2019-04-29 | 2019-07-02 | DANFOSS | DANFOSS | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | REVERSIBLE PLOW,2018 HENKE SAND SPREADER,2019 HENKE WING PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV0KPKV7526 | 1334 | 13 | C723 | C351 | C723 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 17433 | DIESEL | ELKO | 2018-05-14 | 2019-04-17 | 2019-05-07 | PARKER | DANFOSS | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09XX7D653135 | 1335 | 13 | C724 | C381 | C724 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 264747 | DIESEL | WHITE PINE | 2003-07-01 | 2006-10-24 | 2006-11-28 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV4KPKV7528 | 1336 | 13 | C724 | C380 | C724 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 30625 | DIESEL | LANDER | 2018-05-14 | 2019-06-19 | 2019-08-20 | PARKER | DANFOSS | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE36PW45940 | 1338 | 13S | C721 | C122 | C721 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 131308 | DIESEL | LINCOLN | 2003-07-01 | 2006-04-24 | 2006-06-08 | PARKER | PARKER | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK WORKMAN SWAPLOADER,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT5GHHK8988 | 1339 | 24 | C767 | C243 | C767 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 26462 | DIESEL | WASHOE | 2015-04-30 | 2016-03-28 | 2016-04-15 |  | PARKER | A | A |  | #N/A | Reno | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT5GHHK8988
1FD0X4GT3LEC51200 | 1340 | 11H | C721 | C142 | C721 | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | 8425 | BIO DIESEL | CLARK | 2019-06-04 | 2020-04-21 | 2020-06-18 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2015 ARROW BOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes |  |  |  | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
5KKHAEDV6KPKV7529 | 1341 | 13 | C724 | C384 | C724 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 22439 | DIESEL | ELKO | 2018-05-14 | 2019-06-19 | 2019-08-06 | PARKER | DANFOSS | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV2KPKV7527 | 1342 | 13 | C726 | C374 | C726 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 10279 | DIESEL | HUMBOLDT | 2018-05-15 | 2019-04-17 | 2019-06-05 | PARKER | DANFOSS | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X57D653141 | 1343 | 13 | C724 | C385 | C724 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 194777 | DIESEL | WHITE PINE | 2003-07-01 | 2006-12-27 | 2007-02-14 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEGBR1LH207719 | 1345 | 11G | C721 | C121 | C721 | 1990 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | 184007 | DIESEL | CLARK | 1989-09-28 | 1989-09-28 | 1989-09-28 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KKHAEDE86PW45951 | 1346 | 13S | C725 | C175 | C725 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 156878 | DIESEL | NYE | 2003-07-01 | 2006-06-19 | 2006-06-28 | PARKER | PARKER | A | A |  | Goldfield Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SWAPLOADER WATER TANK,ONE WAY PLOW,SANDER 8 YARD,DUMP BODY SWAPLOADER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1M2GR4GC0LM011925 | 1347 | 13S | C723 | C379 | C723 | 2018 | MACK | GR64FR | 2018 MACK GRANITE TANDEM AXLE HOOKLIFT | 4409 | DIESEL | ELKO | 2018-07-09 | 2020-10-06 | 2020-11-10 | FORCE AMERICA | FORCE AMERICA | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | FORCE AMERICA |  |  |  |  | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KKHAEDV8KPLC8371 | 1350 | 13H | C721 | C156 | C721 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXEL DUMP TRUCK | 29691 | DIESEL | CLARK | 2018-06-12 | 2019-02-13 | 2019-02-14 | MUNCIE |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No | 8 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE46PW97769 | 1351 | 13 | C723 | C350 | C723 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 223055 | DIESEL | ELKO | 2003-07-01 | 2006-07-19 | 2006-08-01 | PARKER | PARKER | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV9KPKV7539 | 1352 | 13 | C728 | C203 | C728 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 10686 | DIESEL | LYON | 2018-05-15 | 2019-09-11 | 2019-12-27 | PARKER | DANFOSS | A | A |  | Silver Springs Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV9KPKV7539
1NPTX4TX7AD794135 | 1353 | 83 | C767 | C011 | C767 | 2009 | PETERBILT | 367 | UNDER BRIDGE TRUCK | 103719 | DIESEL | CARSON CITY | 2008-12-01 | 2009-09-24 | 2009-12-14 | DANFOSS |  | A | A |  | Structural Design | Carson City | District 2 |  | No | 7 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
5KKHAEDE46PW45932 | 1355 | 13 | C723 | C331 | C723 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 306539 | DIESEL | ELKO | 2003-07-01 | 2006-01-30 | 2006-02-03 | PARKER | PARKER | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
1NPAL09XX7D653149 | 1356 | 13 | C767 | C250 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 179421 | DIESEL | WASHOE | 2003-07-01 | 2006-09-18 | 2006-09-29 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 2014 VARITECH 403 V | Telematics device for Winter Operations | Yes |  |  | Yes | Yes | Yes |  | Pilot |  | #N/A
5KKHAEDV5KPKV7523 | 1358 | 13 | C728 | C203 | C728 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 14306 | DIESEL | LYON | 2018-05-15 | 2019-12-11 | 2019-12-23 | PARKER | DANFOSS | A | A |  | Silver Springs Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV5KPKV7523
1GDJC34J4TE519667 | 1359 | 11F | C767 | C767 | C767 | 1996 | GMC | SIERRA | SERVICE TRUCK | 97397 | RFG | WASHOE | 1996-03-12 | 1996-04-01 | 1996-04-01 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV7KPKV7524 | 1361 | 13 | C728 | C203 | C728 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 14742 | DIESEL | CHURCHILL | 2018-05-15 | 2019-12-12 | 2020-02-07 | PARKER | DANFOSS | A | A |  | Silver Springs Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV7KPKV7524
5KKHAEDE66PW45947 | 1362 | 13 | C728 | C283 | C728 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 215688 | DIESEL | PERSHING | 2003-07-01 | 2006-03-17 | 2006-04-26 | PARKER | PARKER | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X67D653147 | 1363 | 13S | C720 | C150 | C720 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 117888 | DIESEL | CLARK | 2003-07-01 | 2007-01-05 | 2007-01-10 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | DUMP BODY SWAPLOADER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV4KPKV7531 | 1364 | 13 | C721 | C127 | C721 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 7988 | DIESEL | NYE | 2018-05-14 | 2019-07-26 | 2020-01-10 | PARKER | DANFOSS | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE EXP11NV REV SNOW PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes |  |  |  | 12/6/2021: This is a Las Vegas Truck and we do not need Winter Operations on this vehicle
5KKHAEDV6KPKV7532 | 1366 | 13 | C721 | C122 | C721 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 9886 | DIESEL | CLARK | 2018-05-14 | 2019-06-28 | 2019-10-08 | PARKER | DANFOSS | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 HENKE EXP11NV REVERSIBLE SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics Device | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | [5 empty] | 12/6/2021: This is a Las Vegas Truck and we do not need Winter Operations on this vehicle
2FDLF47G9NCA70274 | 1367 | 11F | C767 | C767 | C767 | 1992 | FORD | F-450 | SERVICE TRUCK | 31185 | RFG | WASHOE | 1992-06-09 | 1992-09-29 | 1992-09-29 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPAL09X27D653145 | 1368 | 13 | C723 | C350 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 230301 | DIESEL | ELKO | 2003-07-01 | 2006-09-18 | 2006-10-10 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,SPRATRONICS DE ICER,PLOW REVERSIBLE,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTSCNKN4MH367578 | 1370 | 12 | C726 | C370 | C726 | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | 135761 | DIESEL | HUMBOLDT | 1991-08-21 | 1991-08-21 | 1991-08-21 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X07D653144 | 1372 | 13 | C723 | C351 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 151792 | DIESEL | ELKO | 2003-07-01 | 2006-09-29 | 2006-12-12 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
2009R335 | 1374 | 55B | C723 | C093 | C723 | 2009 | TUCKER | 2000BXL265 | SNOW CAT | 606 | DIESEL | ELKO | 2009-02-17 | 2009-03-19 | 2009-05-20 | PARKER | PARKER | A | A |  | Communications Elko | Elko | District 3 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A | Yes |  |  |  |  | 8/17/2022: In the internal discussion between Billie, Yesh and Priyanka it was decided that not having dual share services on SnowCats is fine since they are rarely used. 8/17/2022: In the internal discussion between Billie, Yesh and Priyanka it was decided that all the SnowCats should have Satellite
1HTSCNKN2MH367577 | 1375 | 12 | C726 | C371 | C726 | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | 269567 | DIESEL | LANDER | 1991-08-21 | 1991-08-21 | 1991-08-21 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  | Yes | Yes | Yes |  | Full Project |  | #N/A
3ALACXFC9LDLG5746 | 1378 | 24 | C728 | C283 | C728 | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | 4332 | DIESEL | PERSHING | 2018-07-24 | 2019-09-10 | 2019-09-19 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 3ALACXFC9LDLG5746
3ALACXFC0LDLG5747 | 1381 | 24 | C723 | C379 | C723 | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | 2018 | DIESEL | ELKO | 2018-07-24 | 2019-09-10 | 2019-09-19 |  |  | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
2HTTEAHRXTC058334 | 1386 | 15 | C724 | C384 | C724 | 1995 | INTL | D3057 | AWD DUMP TRUCK | 141260 | DIESEL | EUREKA | 1995-08-21 | 1995-11-01 | 1995-11-01 |  |  | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | No | 6 | J1939 | Roadwatch Sensor |  |  |  |  | STAINLESS 7 YD SANDER,1995 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE66PW45933 | 1387 | 13 | C723 | C350 | C723 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 236555 | DIESEL | ELKO | 2003-07-01 | 2006-01-10 | 2006-02-03 | PARKER | PARKER | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SPRATRONICS DE ICER,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1XPFD49X94D832973 | 1388 | 14 | C767 | C767 | C767 | 2004 | PETERBILT | 378 | TRUCK TRACTOR | 665414 | DIESEL | WASHOE | 2003-07-01 | 2004-02-06 | 2004-02-09 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FD0X4GTXLEC50917 | 1390 | 11E | C721 | C150 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 DUMP TRUCK | 9150 | BIO DIESEL | CLARK | 2019-04-18 | 2020-08-13 | 2020-08-13 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes |  |  |  | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1FD0X4GT1LEC50918 | 1391 | 11E | C721 | C145 | C721 | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | 14437 | BIO DIESEL | CLARK | 2019-04-18 | 2020-05-05 | 2020-09-02 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1FVACXFC2KHKG9899 | 1395 | 24 | C721 | C156 | C721 | 2018 | ELGIN | EAGLE | STREET SWEEPER | 5738 | DIESEL | CLARK | 2018-01-03 | 2018-11-15 | 2018-12-14 |  |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
3B6MC3665XM559576 | 1397 | 11F | C721 | C721 | C721 | 1999 | DODGE | 3500 | 1 TON SERVICE TRUCK | 46564 | DIESEL | CLARK | 1999-04-12 | 1999-07-14 | 1999-07-14 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3B6MC3665XM559576 |  |  |  |  | 11.22.2022
1FVACXFC0KHKG9898 | 1399 | 24 | C728 | C203 | C728 | 2018 | ELGIN | EAGLE | STREET SWEEPER | 7848 | DIESEL | CHURCHILL | 2018-01-03 | 2018-11-26 | 2018-12-17 |  |  | A | A |  | Silver Springs Crew | Fallon | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXFC0KHKG9898
#N/A | 1400 | 15 | C767 | C234 | #N/A | 1995 | INTL | D3057 | AWD SINGLE AXLE DUMP TRUCK | 165924 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Virginia City Maintenance Crew | Reno | District 2 |  | No | 6 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  | Yes | Yes | Yes |  |  |  | #N/A
1FD0X4GT1KEC51775 | 1403 | 11J | C721 | C145 | C721 | 2018 | FORD | F-450 | 2018 UTILITY TRUCK | 41188 | BIO DIESEL | CLARK | 2018-06-04 | 2018-12-17 | 2019-02-11 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0X4GT1KEC51775 |  | Yes |  |  | 11.22.2022
1FDUF4GT5JEC11606 | 1404 | 11E | C721 | C150 | C721 | 2018 | FORD | F-450 | COMPACTOR TRUCK | 32270 | BIO DIESEL | CLARK | 2017-12-27 | 2018-07-20 | 2018-12-26 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: Replaced this vehicle with other vehicle for Pre-Pilot and moved this to Full Project Phase
1FDUF4GT3JEC11605 | 1405 | 11D | C721 | C160 | C721 | 2018 | FORD | F-450 | COMPACTOR TRUCK | 17474 | BIO DIESEL | CLARK | 2017-12-27 | 2018-09-10 | 2019-06-18 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FDUF4GT7JEC11607 | 1406 | 11D | C721 | C178 | C721 | 2018 | FORD | F-450 | COMPACTOR TRUCK | 40742 | BIO DIESEL | CLARK | 2017-12-27 | 2018-06-20 | 2019-02-12 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
49HAADBV04DN18706 | 1407 | 24 | C720 | C154 | C720 | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | 68638 | DIESEL | CLARK | 2003-07-02 | 2004-09-28 | 2004-10-01 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
3B6MC3663XM559575 | 1409 | 11F | C721 | C721 | C721 | 1999 | DODGE | 3500 | SERVICE TRUCK W/CRANE | 100115 | DIESEL | CLARK | 1999-04-19 | 1999-04-19 | 1999-07-14 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3B6MC3663XM559575 |  |  |  |  | 11.22.2022
1FD0X4GT5KEC51780 | 1410 | 11E | C721 | C145 | C721 | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRCK | 38926 | BIO DIESEL | CLARK | 2018-06-04 | 2019-04-30 | 2019-05-30 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0X4GT5KEC51780 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FD0W4HT1KEC55536 | 1411 | 11E | C767 | C250 | C767 | 2018 | FORD | F-450 | 2018 FORD F-450 DUMP CREW V10 DRW 4X4 | 39646 | BIO DIESEL | WASHOE | 2018-06-12 | 2018-11-28 | 2019-03-05 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD8W3H60KEC35219 | 1413 | 11J | C767 | C202 | C767 | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | 30273 | TELEMATIC | WASHOE | 2018-02-21 | 2019-01-18 | 2019-03-13 |  |  | A | A |  | Reno Service Crew | Reno | District 2 |  | No | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD8W3H67KEC35220 | 1414 | 11J | C767 | C202 | C767 | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | 39126 | TELEMATIC | WASHOE | 2018-02-22 | 2018-11-29 | 2019-03-13 |  |  | A | A |  | Reno Service Crew | Reno | District 2 |  | No | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD8W3H69KEC35221 | 1417 | 11J | C767 | C202 | C767 | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | 41940 | TELEMATIC | WASHOE | 2018-02-22 | 2019-02-08 | 2019-05-22 |  |  | A | A |  | Reno Service Crew | Reno | District 2 |  | No | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
49HHADBV94DN18705 | 1418 | 24 | C720 | C159 | C720 | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | 75161 | DIESEL | CLARK | 2003-07-02 | 2004-09-28 | 2004-10-01 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEATR5TH369252 | 1419 | 12 | C721 | C178 | C767 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 155836 | DIESEL | LINCOLN | 1996-06-25 | 1996-11-07 | 1996-11-07 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1969 BOUMAN SANDER,1996 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT0JEC11610 | 1421 | 11E | C726 | C371 | C726 | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | 47492 | DIESEL | HUMBOLDT | 2017-12-26 | 2018-07-20 | 2018-10-02 |  |  | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4HT2JEC11611 | 1424 | 11E | C726 | C370 | C726 | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | 29730 | DIESEL | HUMBOLDT | 2017-12-26 | 2018-07-20 | 2019-01-14 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
3C7WRNBL0JG291068 | 1425 | 11F | C723 | C723 | C723 | 2018 | DODGE | RAM 5500 | SERVICE TRUCK 4X4 | 13382 | DIESEL | ELKO | 2017-12-26 | 2018-10-03 | 2018-11-26 | PARKER |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3C7WRNBL0JG291068 |  | Yes |  |  | 11.30.2022
1FTEX1C5XKKE52317 | 1426 | 5 | C721 | C101 | C721 | 2019 | FORD | F-150 | 2019 FORD F150 1/2 TON EXT CAB S/B | 14909 | E-85 | CLARK | 2019-04-17 | 2019-08-14 | 2020-06-18 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C5XKKE52317 |  |  |  |  | 11.23.2022
1HTGEATR5TH369249 | 1427 | 12 | C721 | C129 | C721 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 116292 | DIESEL | CLARK | 1996-06-27 | 1996-07-10 | 1996-07-10 |  |  | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 11' LAWTON STR DBL SWING,FLINK 10' LMC5H 5CU YD | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT8JEC11614 | 1428 | 11H | C723 | C340 | C723 | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | 56531 | DIESEL | ELKO | 2018-01-09 | 2018-09-19 | 2018-11-20 |  |  | A | A |  | Elko Striping Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4HT8JEC11614 |  |  |  |  | 11.29.2022
1FD0W4HT6JEC11613 | 1429 | 11H | C723 | C331 | C723 | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | 45334 | DIESEL | ELKO | 2018-01-09 | 2018-08-31 | 2018-12-17 |  |  | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4HT6JEC11613 | Yes |  |  |  | 11.29.2022
2HSFBX6R6MC048188 | 1430 | 14 | C724 | C319 | C724 | 1991 | INTL | 9300 | REBUILD TRACTOR TRUCK | 99643 | DIESEL | WHITE PINE | 1992-01-02 | 1992-01-02 | 2011-01-19 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDUF4GY4JEC11608 | 1432 | 11J | C723 | C302 | C723 | 2018 | FORD | F-450 | UTILITY TRUCK | 20514 | UNLEADED | ELKO | 2018-01-09 | 2018-07-20 | 2018-08-16 |  |  | A | A |  | Elko Service Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDUF4GY4JEC11608 |  | Yes |  |  | 11.29.2022
1HTGEATR3TH369248 | 1434 | 12 | C723 | C332 | C723 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 212154 | DIESEL | ELKO | 1996-06-24 | 1996-07-11 | 1996-07-11 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE,1996 SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDOW4HT4JEC11609 | 1438 | 11E | C721 | C179 | C721 | 2018 | FORD | F-450 | 2018 FORD F450 SNGL AXEL DUMP TRUCK 4X4 | 59560 | DIESEL | WASHOE | 2017-12-13 | 2018-07-20 | 2018-11-13 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 1440 | 12 | C767 | C767 | #N/A | 1992 | FORD | L9000 | SINGLE AXLE DUMP TRUCK | 97833 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | JENSEN 3/38/60 PLOW,5 YRD SANDER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  |  |  | #N/A
1FT7W2B61JEC65699 | 1441 | 3 | C721 | C915 | C721 | 2018 | FORD | F-250 | 2018 FORD F250 3/4T 4X4 CREW | 26390 | E-85 | CLARK | 2018-01-17 | 2018-06-25 | 2018-10-17 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT06J341699 | 1442 | 25 | C722 | C227 | C722 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | 61387 | DIESEL | DOUGLAS | 2003-07-01 | 2006-06-26 | 2006-07-24 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FT7W2B64JEC65700 | 1444 | 3 | C726 | C920 | C726 | 2018 | FORD | F-250 | 2018 FORD F250 3/4T TRUCK 4X4 CREW CAB | 27783 | UNLEADED | HUMBOLDT | 2018-01-17 | 2018-06-25 | 2018-09-18 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4HY6JEC65698 | 1445 | 11A | C724 | C342 | C767 | 2018 | FORD | F-450 | AERIAL TRUCK F-450 1 TON | 18172 | UNLEADED | WHITE PINE | 2017-12-26 | 2018-06-25 | 2020-08-19 |  |  | A | A |  | Ely Striping Crew | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HTXKEC82568 | 1447 | 11E | C721 | C129 | C721 | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | 33901 | BIO DIESEL | CLARK | 2018-06-13 | 2019-01-24 | 2019-03-28 |  |  | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FT7X2B66BEB42236 | 1448 | 3 | C722 | C027 | C722 | 2011 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 138970 | UNLEADED | CARSON CITY | 2010-08-31 | 2010-11-15 | 2011-01-11 |  |  | A | A |  | Materials Bituminous | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GDJK34J8XF097213 | 1450 | 11F | C726 | C726 | C726 | 1999 | GMC | TK310 | AWD SERVICE TRUCK | 176265 | UNLEADED | HUMBOLDT | 1999-08-06 | 1999-08-06 | 1999-08-18 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 1451 | 12 | C724 | C319 | #N/A | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | 220726 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Ely Yard Stockpile Control | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1FD0X4HY4JEC11618 | 1452 | 11E | C767 | C253 | C767 | 2018 | FORD | F-450 | 2018 FORD F-450 1 TON DUMP 4X4 | 39262 | TELEMATIC | WASHOE | 2018-01-09 | 2018-07-20 | 2018-11-14 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  | Yes | 2018 SNOWDOGG 9' STRAIGHT PLOW,2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTSCAAN0TH410158 | 1454 | 12 | C726 | C374 | C726 | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | 185127 | DIESEL | HUMBOLDT | 1996-08-12 | 1996-08-12 | 1996-08-12 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HY2JEC11617 | 1456 | 11E | C728 | C283 | C728 | 2018 | FORD | F-450 | 2018 1 - 2 TON DUMP/GARBAGE TRCK | 67622 | TELEMATIC | WASHOE | 2018-01-09 | 2018-07-20 | 2019-05-22 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY0JEC11616 | 1457 | 11E | C767 | C231 | C767 | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | 58120 | TELEMATIC | WASHOE | 2018-01-09 | 2018-07-20 | 2019-08-20 |  |  | A | A |  | Nixon Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 1469 | 13 | C724 | C384 | #N/A | 1990 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 110300 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Eureka Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 8 YD | Telematics Device | Yes |  |  | Yes | Yes | Yes |  |  |  | #N/A
1FTMF1C52KKE52312 | 1470 | 5 | C721 | C926 | C721 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 8092 | E-85 | CLARK | 2019-04-17 | 2019-09-19 | 2020-05-28 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGGDR6LH207707 | 1474 | 13 | C767 | C251 | C767 | 1989 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 32284 | DIESEL | WASHOE | 1989-12-13 | 1990-04-16 | 2015-03-13 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE WING PLOW,REVERSIBLE 11' SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1FD0X4HT7JEC11620 | 1476 | 11E | C721 | C156 | C721 | 2018 | FORD | F-450 | 2018 FORD F-450 1T V10 DUMP EXT CAB 4X4 | 45140 | BIO DIESEL | CLARK | 2017-12-13 | 2018-08-07 | 2018-10-15 |  |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HT0JEC11619 | 1480 | 11E | C721 | C156 | C721 | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRCK | 64122 | BIO DIESEL | CLARK | 2017-12-13 | 2018-08-09 | 2018-09-28 |  |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPTM70X2CD151502 | 1482 | 11A | C767 | C240 | C767 | 2011 | PETERBILT | 367 | PETERBILT 6X6 AERIAL LIFT TRUCK | 14998 | DIESEL | ELKO | 2011-04-06 | 2011-10-20 | 2012-02-15 | EATON |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
#N/A | 1483 | 12 | C767 | C225 | #N/A | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 196768 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Fernley Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 YRD HENDERSON CHIEF,2000 PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  |  |  | #N/A
#N/A | 1484 | 12 | C767 | C241 | #N/A | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 218330 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Reno Striping Crew 2 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1988 SANDER,1988 REV PLOW,REVERSIBLE PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  |  |  | #N/A
1FVACXDT8BDBC6436 | 1486 | 24 | C767 | C251 | C767 | 2011 | FREIGHTLNR | M2 | 2011 FREIGHTLINER M2 | 33878 | DIESEL | WASHOE | 2010-12-01 | 2011-08-11 | 2011-09-28 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEATR1TH369250 | 1489 | 12 | C726 | C374 | C726 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 82477 | DIESEL | HUMBOLDT | 1996-06-27 | 1996-10-23 | 1996-10-23 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SNOW PLOW,ATTENUATOR, V/M,2000 SNOW PLOW | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FVACXDTXBDBC6437 | 1491 | 24 | C767 | C243 | C767 | 2011 | FREIGHTLNR | M2 | ELGIN EAGLE SWEEPER | 40783 | DIESEL | WASHOE | 2010-12-01 | 2011-08-11 | 2011-09-28 |  |  | A | A |  | #N/A | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1GTEK14WXWZ502135 | 1500 | 5 | C722 | C712 | C722 | 1998 | GMC | TK109 | 1/2 TON PICKUP TRUCK | 252827 | UNLEADED | CARSON CITY | 1997-09-09 | 1997-10-17 | 1997-10-17 |  |  | A | A |  | Carson City Equipment Stockroom | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B88JGA91718 | 1505 | 01A | C721 | C101 | C721 | 2018 | FORD | EXPLORER | SUV 4X4 | 11796 | E-85 | CLARK | 2017-12-13 | 2018-04-27 | 2018-06-05 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FM5K8B88JGA91718 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1GNEVFKW5KJ245036 | 1508 | 01A | C727 | A002 | C727 | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | 2675 | TELEMATIC | WASHOE | 2019-02-11 | 2019-04-23 | 2019-05-23 |  |  | A | A |  | Office of the Director | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B80JGC76684 | 1511 | 01A | C767 | C201 | C767 | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 4X4 | 20072 | TELEMATIC | WASHOE | 2017-12-13 | 2018-09-10 | 2018-10-19 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR1JH569736 | 1512 | 12 | C767 | C201 | C767 | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 149730 | DIESEL | WASHOE | 1988-04-26 | 1988-09-06 | 1988-09-06 |  |  | A | A |  | Reno District Administration | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B89JGC76683 | 1516 | 01A | C723 | C033 | C723 | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 3.5L V6 4WD | 13543 | UNLEADED | ELKO | 2018-05-16 | 2018-09-14 | 2018-11-02 |  |  | A | A |  | Right of Way Elko | Elko | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FM5K8B89JGC76683 |  | Yes |  |  | 11.29.2022
1HTGGAET4TH369245 | 1518 | 13 | C724 | C382 | C724 | 1996 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 113773 | DIESEL | WHITE PINE | 1996-06-27 | 1996-07-16 | 2015-04-10 | PARKER 13 | PARKER | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,1990 HENDERSON SANDER 10 YD,ONE-WAY PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
2HTTEGDR6KCO29484 | 1521 | 15 | C722 | C271 | C722 | 1989 | INTL | 5070 | AWD DUMP TRUCK | 136841 | DIESEL | CARSON CITY | 1989-06-13 | 1989-06-13 | 1989-06-13 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 6 | J1939 | Roadwatch Sensor |  |  |  |  | 11' REVERSIBLE PLOW,MONROE A39-52-10 ONE WAY PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GNEVFKW3KJ247660 | 1527 | 01A | C723 | C301 | C723 | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | 5721 | UNLEADED | ELKO | 2019-02-11 | 2019-05-06 | 2019-05-16 |  |  | A | A |  | Elko District Administration | Elko | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GNEVFKW3KJ247660 |  | Yes |  |  | 11.28.2022
1FTBF2AT8CEB85241 | 1529 | 3 | C721 | C101 | C721 | 2012 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 100949 | BIO DIESEL | CLARK | 2012-01-01 | 2012-02-21 | 2012-06-01 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTBF2AT8CEB85241
1FTMF1CM7CKD70388 | 1533 | 5 | C721 | C901 | C721 | 2012 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | 107254 | E-85 | CLARK | 2012-02-16 | 2012-05-21 | 2012-08-09 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GNEVFKW2KJ243888 | 1534 | 01A | C721 | A003 | C721 | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | 4141 | UNLEADED | CLARK | 2019-02-11 | 2019-04-11 | 2019-05-06 |  |  | A | A |  | Public Information & Publications | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4PJMCX1KD168351 | 1537 | 01A | C767 | C767 | C767 | 2019 | JEEP | CHEROKEE | 2019 JEEP CHEROKEE SUV 4X4 UNLEAD | 7735 | TELEMATIC | WASHOE | 2018-01-17 | 2018-04-16 | 2018-06-21 |  |  | A | A |  | Equipment Shop | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C55KKE52305 | 1545 | 5 | C721 | C901 | C721 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 3350 | E-85 | CLARK | 2019-08-14 | 2019-09-25 | 2020-08-04 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4PJMCX8KD168346 | 1549 | 01A | C727 | C727 | C727 | 2019 | JEEP | CHEROKEE | SUV 4X4 | 50276 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-04-13 | 2018-06-21 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4RJFAG5JC309725 | 1550 | 01A | C727 | C016 | C727 | 2018 | JEEP | CHEROKEE | 2019 JEEP GRAND CHEROKEE SUV 4X4 | 28712 | UNLEADED | CARSON CITY | 2017-12-05 | 2018-03-08 | 2018-04-01 |  |  | A | A |  | Traffic Operations | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4PJMCX1KD168348 | 1553 | 01A | C767 | C767 | C767 | 2019 | JEEP | CHEROKEE | SUV 4X4 | 15431 | TELEMATIC | WASHOE | 2017-12-05 | 2018-04-17 | 2018-05-31 |  |  | A | A |  | Equipment Shop | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C59KKE52310 | 1555 | 5 | C721 | C922 | C721 | 2019 | FORD | F-150 | 1/2 TON PICK UP | 8125 | E-85 | CLARK | 2019-08-14 | 2019-09-25 | 2020-01-21 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4RJFAGXJC309722 | 1558 | 01A | C727 | A002 | C726 | 2018 | JEEP | CHEROKEE | 2018 JEEP GRAND CHEROKEE SUV 4X4 | 10429 | UNLEADED | CARSON CITY | 2017-12-04 | 2018-03-08 | 2018-04-30 |  |  | A | A |  | Office of the Director | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4RJFAG1JC309723 | 1560 | 01A | C727 | C050 | C727 | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | 15601 | UNLEADED | CARSON CITY | 2017-12-06 | 2018-03-08 | 2018-05-01 |  |  | A | A |  | Maintenance and Asset Mgmt | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1M2P14104KW007833 | 1562 | 25 | C723 | C332 | C723 | 1989 | MACK | RD688 | 3500 GALLON WATER TRUCK | 119889 | DIESEL | ELKO | 1989-07-14 | 1989-07-14 | 1989-07-14 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGJUR5LH207727 | 1563 | 25 | C726 | C370 | C726 | 1990 | INTL | F2574 | TANDEM AXLE WATER TRUCK | 153381 | DIESEL | HUMBOLDT | 1989-08-18 | 1989-08-18 | 1989-08-18 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHR9YH223467 | 1565 | 12 | C767 | C767 | C767 | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 177017 | DIESEL | ELKO | 2000-01-18 | 2000-01-18 | 2000-04-05 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | MODEL #12-99 TENCO,1999 SANDER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHROYH223468 | 1569 | 12 | C721 | C129 | C721 | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 120441 | DIESEL | CLARK | 1999-12-23 | 1999-12-23 | 2000-03-16 |  |  | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 11' SWING PLOW,SANDER | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGGAET6TH369246 | 1570 | 13 | C767 | C253 | C767 | 1996 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | 197208 | DIESEL | WASHOE | 1996-07-05 | 1996-07-05 | 1996-07-05 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENDERSON CHIEF 5 YARD,1996 PLOW,HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1C4PJMCX3KD168349 | 1583 | 01A | C767 | C201 | C767 | 2018 | JEEP | CHEROKEE | 2019 JEEP LATITUDE CHEROKEE SUV 4X4 | 20711 | TELEMATIC | WASHOE | 2017-12-05 | 2018-04-13 | 2018-05-02 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B8XJGA91719 | 1589 | 01A | C767 | C201 | C767 | 2018 | FORD | EXPLORER | SUV 4X4 | 18782 | TELEMATIC | WASHOE | 2017-12-04 | 2018-04-27 | 2018-07-20 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C57KKE52306 | 1591 | 5 | C721 | C903 | C721 | 2019 | FORD | F-150 | 1/2 TON PICK UP | 10020 | E-85 | CLARK | 2019-04-17 | 2019-10-02 | 2020-06-15 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEGBR5LH207724 | 1593 | 28 | C723 | C351 | C723 | 1989 | INTL | 2574 | OIL DISTRIBUTOR | 105682 | DIESEL | ELKO | 1989-08-15 | 1989-08-15 | 1989-08-15 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1C4PJMCX6KD168345 | 1595 | 01A | C727 | A078 | C727 | 2019 | JEEP | CHEROKEE | SUV 4X4 | 3596 | UNLEADED | WASHOE | 2017-12-04 | 2018-04-13 | 2018-06-26 |  |  | A | A |  | Human Resources - Industrial Safety | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2BT3KED14537 | 1605 | 3 | C728 | C203 | C728 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | 70503 | DIESEL | LYON | 2017-12-18 | 2018-11-29 | 2019-02-25 |  |  | A | A |  | Silver Springs Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTMMAAN2EH038976 | 1612 | 24 | C722 | C271 | C722 | 2014 | TYMCO | DST6 | INTL TYMCO SWEEPER | 28594 | DIESEL | CARSON CITY | 2013-09-18 | 2014-04-08 | 2014-05-07 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1HTMMAAN2EH038976
1HTGEGBR7LH207725 | 1613 | 28 | C723 | C336 | C723 | 1989 | INTL | 2574 | OIL DISTRIBUTOR | 107782 | DIESEL | ELKO | 1989-08-15 | 1989-08-15 | 1989-08-15 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDUF4GT4EEB28206 | 1614 | 11S | C720 | C150 | C720 | 2014 | FORD | F-450 | DUMP TRUCK W/SWAPLOADER BIODSL | 106550 | BIO DIESEL | CLARK | 2013-02-01 | 2014-03-31 | 2014-05-07 | CHELSEA/PARKER |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  | GO9 |  |  | 2014 WILLIAMSEN SWAPLOADER BED | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FDUF4GT4EEB28206 |  | Yes
1GC1KUEGXJF241462 | 1615 | 3 | C723 | C301 | C723 | 2018 | CHEVROLET | SILVERADO | 2018 CHEVEROLET SIVERADO 2500 4X4 | 49337 | UNLEADED | ELKO | 2018-01-31 | 2018-05-07 | 2019-01-25 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GC1KUEGXJF241462 |  |  |  |  | 11.30.2022
#N/A | 1622 | 12 | C723 | C327 | #N/A | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 195254 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | North Fork Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  |  |  | #N/A | Yes-Pilot | Yes |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
5KKHAEDV6NPNG9611 | 1624 | 13 | C723 | C723 | C723 | 2021 | WESTERN ST | 4900SF | 2021 WESTERN STAR 4900SF TANDEM AXEL DUMP TRUCK | 1257 | DIESEL | ELKO | 2020-12-08 | 2022-03-01 | 2022-10-11 | DANFOSS | DANFOSS |  | A | New - Nov 2022 | Elko District Repair Shop | Elko | District 3 |  |  | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations |  |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGGAETXYH223472 | 1628 | 13 | C724 | C384 | C724 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 164431 | DIESEL | WHITE PINE | 1999-08-30 | 1999-08-30 | 2015-07-15 | PARKER | PARKER | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SANDER,HENKE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXH70C4TVA31975 | 1630 | 24 | C723 | C335 | C723 | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | 75388 | DIESEL | ELKO | 1996-06-08 | 1996-07-03 | 1996-07-03 |  |  | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FDXH70C8TVA31977 | 1631 | 24 | C723 | C336 | C723 | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | 1050588 | DIESEL | ELKO | 1996-06-21 | 1996-07-03 | 1996-07-03 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET7YH223476 | 1632 | 13 | C728 | C203 | C728 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 12981 | DIESEL | WASHOE | 1999-11-17 | 1999-11-17 | 2017-11-07 | PARKER | PARKER | A | A |  | Silver Springs Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR4GHA30703 | 1633 | 11G | C724 | C342 | C724 | 1986 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | 181926 | DIESEL | WHITE PINE | 1986-03-13 | 1986-03-13 | 1986-03-13 |  |  | A | A |  | Ely Striping Crew | Ely | District 3 |  | No | 6 | J1939 | [5 empty] | 1986 SANDER | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1FDXH70C6TVA31976 | 1638 | 24 | C724 | C319 | C724 | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | 51252 | DIESEL | WHITE PINE | 1996-06-21 | 1996-07-03 | 1996-07-03 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1M2K197C04M024755 | 1639 | 77 | C724 | C342 | C724 | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | 116910 | DIESEL | WHITE PINE | 2003-06-27 | 2004-04-09 | 2004-05-03 |  |  | A | A |  | Ely Striping Crew | Ely | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C52KKE52309 | 1640 | 5 | C721 | C915 | C767 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 13180 | E-85 | CLARK | 2019-04-17 | 2019-08-14 | 2020-07-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV3NPPNG9615 | 1641 | 13 | C728 | C237 | C728 | 2021 | WESTERN ST | 4900SF | 2021 WESTERN STAR 4900SF TANDEM AXEL DUMP TRUCK | 929 | DIESEL | MINERAL | 2020-12-08 | 2022-05-24 | 2022-10-11 | DANFOSS | DANFOSS |  | A | New - Nov 2022 | Hawthrone Maintenance Crew | Fallon | District 2 |  |  | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  |  | Telematics device for Winter Operations |  |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET5YH223475 | 1642 | 13 | C726 | C374 | C726 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 222199 | DIESEL | HUMBOLDT | 1999-08-30 | 1999-08-30 | 1999-10-08 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2016 WING PLOW,1991 PLOW,FLINK 8 YD | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FMJU1GT5JEA59933 | 1643 | 01A | C767 | C092 | C767 | 2018 | FORD | EXPEDITION | 2018 FORD EXPEDITION SUV 4X4 | 15362 | TELEMATIC | WASHOE | 2018-05-16 | 2018-10-09 | 2019-01-14 |  |  | A | A |  | Communications Reno | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEATR8TH368595 | 1649 | 28 | C724 | C319 | C724 | 1996 | INTL | 2574 | OIL DISTRIBUTOR | 70843 | DIESEL | WHITE PINE | 1996-06-10 | 1996-07-01 | 1996-07-01 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAET2YH223479 | 1650 | 13 | C728 | C280 | C728 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 194014 | DIESEL | CHURCHILL | 1999-12-07 | 1999-12-07 | 2000-01-06 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 8 YRD FLINK,REVERSIBLE JENSEN MDL 34058 | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAETOYH223478 | 1651 | 13 | C722 | C270 | C722 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 227729 | DIESEL | CARSON CITY | 1999-08-30 | 1999-08-30 | 1999-10-08 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | VARITECH 1750 GAL BRINE TANK,MONROE 11' REVERSIBLE PLOW 540-58-11,PLOW REVERSIBLE ALASKA EXPRESSWAY,2014 HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
3GCUKNEC0JG458307 | 1653 | 5 | C727 | C027 | C727 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | 7530 | FLEX FUEL | CARSON CITY | 2018-05-16 | 2018-08-14 | 2019-02-20 |  |  | A | A |  | Materials Bituminous | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCPCNEC2JG459324 | 1656 | 5 | C721 | C906 | C721 | 2018 | CHEVROLET | SILVERADO | 18 CHEVY SILVERADO 1/2 T CREW CAB 4X2 | 40172 | E-85 | CLARK | 2018-05-18 | 2018-08-09 | 2018-08-27 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCPCNECXJG455232 | 1658 | 5 | C721 | C903 | C721 | 2018 | CHEVROLET | 2500 | 2018 CHEVY SILVERADO 1/2T CREW CAB SB V8 | 18877 | E-85 | CLARK | 2018-05-18 | 2018-08-09 | 2018-10-11 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXW46P04ED93110 | 1659 | 11D | C721 | C145 | C721 | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | 118327 | BIO DIESEL | CLARK | 2003-07-01 | 2004-11-23 | 2004-12-27 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDXW46P04ED93110 |  |  |  |  | 11.22.2022
3GCPCNEC6JG459682 | 1664 | 5 | C721 | C906 | C721 | 2018 | CHEVROLET | 2500 | 2018 CHEV SILVERADO 1/2T CREW CAB SB V8 | 60109 | E-85 | CLARK | 2018-05-18 | 2018-08-09 | 2018-08-27 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF5GTXHDA03095 | 1665 | 11A | C721 | C155 | C721 | 2017 | FORD | F-550 | AERIAL TRUCK | 15126 | DIESEL | CLARK | 2016-10-20 | 2017-07-24 | 2017-10-09 | PARKER | VERSALIFT | A | A |  | Las Vegas Bridge Maintenance | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGEATR8TH368596 | 1668 | 28 | C723 | C332 | C723 | 1996 | INTL | 2574 | OIL DISTRIBUTOR | 77812 | DIESEL | ELKO | 1996-06-10 | 1996-07-01 | 1996-07-01 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTMF1C59KKE52307 | 1669 | 5 | C721 | C916 | C721 | 2019 | FORD | F-150 | 1/2 TON PICK UP | 4582 | E-85 | CLARK | 2019-04-17 | 2019-08-14 | 2020-08-13 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR4JH569729 | 1670 | 12 | C722 | C272 | C722 | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 157054 | DIESEL | CARSON CITY | 1988-04-26 | 1988-04-26 | 1988-04-26 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENDERSEN 5 CU YD SANDER,11' SNOW PLOW, REVERSIBLE, LAWTON EQUIPM | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 1671 | 13 | C767 | C767 | #N/A | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 216799 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,BRINE DISTRIBUTOR | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Blank - 1/24/2023 |  | #N/A
1FD8X3F62KEE89353 | 1673 | 11J | C767 | C757 | C767 | 2019 | FORD | F-350 | 2019 FORD F-350 4X4 UTILITY TRUCK | 17644 | TELEMATIC | WASHOE | 2018-06-26 | 2019-06-04 | 2019-12-12 |  |  | A | A |  | Equipment Stockroom | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FT7X2B60KEC61156 | 1675 | 3 | C726 | C726 | C726 | 2019 | FORD | 250 | 2019 3/4 TON PICKUP TRUCK 4X4 | 3941 | UNLEADED | HUMBOLDT | 2018-06-26 | 2018-10-17 | 2019-12-12 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B67KEE89352 | 1676 | 3 | C727 | C816 | C727 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | 1440 | UNLEADED | CARSON CITY | 2019-01-30 | 2019-09-19 | 2019-12-17 |  |  | A | A |  | Planning - Traffic Safety Engineering | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E56JKF37543 | 1678 | 5 | C721 | C916 | C721 | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 18792 | E-85 | CLARK | 2018-06-28 | 2018-11-29 | 2018-12-21 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E54JKF37542 | 1679 | 5 | C721 | C914 | C721 | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 29764 | FLEX FUEL | NYE | 2018-06-28 | 2018-11-05 | 2018-11-27 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E58JKF30576 | 1680 | 5 | C767 | C767 | C767 | 2018 | FORD | 150 | 2018 1/2 TON PICK UP | 4132 | FLEX FUEL | WASHOE | 2018-06-25 | 2018-11-15 | 2019-01-03 |  |  | A | A |  | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGA6R8MH367566 | 1682 | 25 | C723 | C336 | C723 | 1991 | INTL | F2574 | REBUILD TANDEM AXLE WATER TRUCK | 22510 | DIESEL | ELKO | 1991-07-02 | 1991-12-03 | 2015-09-03 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET9YH223477 | 1684 | 13 | C728 | C281 | C728 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 201169 | DIESEL | CHURCHILL | 1999-08-30 | 1999-08-30 | 1999-10-08 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 8 YRD FLINK SANDER,12' PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B82KGA17034 | 1686 | 01A | C725 | C104 | C725 | 2018 | FORD | EXPLORER | 2018 FORD EXPL SUV 1/2T 5.3 4WD 6 PASS | 24251 | FLEX FUEL | NYE | 2018-07-02 | 2018-10-24 | 2018-12-05 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | AWD Passenger Vehicles | Yes | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HT2LEE33906 | 1687 | 11H | C721 | C179 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | 19 | BIO DIESEL | CLARK | 2020-02-28 | 2020-12-09 | 2021-07-12 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1XKWD40X0MR441068 | 1688 | 14 | C767 | C767 | C767 | 2020 | KENWORTH | W900L | 2020 KENWORTH W900L TRANSPORT TRACTOR | 34889 | DIESEL | WASHOE | 2020-01-02 | 2020-10-08 | 2020-12-01 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1FT7X2B60KEC69919 | 1689 | 3 | C725 | C104 | C725 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | 53946 | FLEX FUEL | NYE | 2018-07-02 | 2018-10-15 | 2019-03-28 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | 3/4 Ton Pickups | Yes | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET4YH223483 | 1690 | 13 | C723 | C331 | C723 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 348143 | DIESEL | ELKO | 1999-09-10 | 1999-09-10 | 1999-09-20 |  |  | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2000 SANDER,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
1HTGGAET2YH223482 | 1691 | 13 | C723 | C335 | C723 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 278387 | DIESEL | ELKO | 1999-10-26 | 1999-10-26 | 1999-11-02 |  |  | D | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 8 YD SANDER,SPRATRONICS DE ICER,REVERSIBLE PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTZMGBR5GHA30838 | 1692 | 28 | C726 | C320 | C726 | 1986 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | 120740 | DIESEL | HUMBOLDT | 1986-03-13 | 1986-03-13 | 1986-03-13 |  |  | A | A |  | Winnemucca Yard Stockpile Control | Winnemucca | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2GCRCNEC3K1112619 | 1693 | 5 | C721 | C101 | C721 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON PICK UPS | 29346 | UNLEADED | CLARK | 2018-07-02 | 2018-09-07 | 2019-01-23 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 2GCRCNEC3K1112619 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FTEW1EB0JKF42547 | 1694 | 5 | C767 | C245 | C767 | 2018 | FORD | F-150 | 2018 1/2 TON PICK UP | 18451 | FLEX FUEL | WASHOE | 2018-07-02 | 2018-11-15 | 2019-07-23 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B69KEC69918 | 1695 | 3 | C767 | C241 | C767 | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | 49089 | TELEMATIC | WASHOE | 2018-07-02 | 2018-10-24 | 2019-05-01 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B67KEC69917 | 1697 | 3 | C728 | C281 | C728 | 2019 | FORD | 250 | 3/4 TON PICKUP TRUCK | 50687 | TELEMATIC | WASHOE | 2018-07-02 | 2018-10-24 | 2019-05-06 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4HY1KDA05071 | 1699 | 11J | C724 | C308 | C724 | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | 19009 | UNLEADED | WHITE PINE | 2018-07-02 | 2019-07-19 | 2019-07-19 |  |  | A | A |  | Ely Service Crew | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2018 SNOWDOGG 9' TE STRAIGHT PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GKDT13S952252289 | 1700 | 01A | C721 | C844 | C721 | 2005 | GMC | ENVOY | SUV 4X4 | 90890 | UNLEADED | CLARK | 2004-07-07 | 2005-02-08 | 2005-03-01 |  |  | A | A |  | Transportation / Multimodal Planning Las Vegas | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GKDT13S652252475 | 1701 | 01A | C721 | C844 | C721 | 2005 | GMC | ENVOY | AWD SUV | 57290 | UNLEADED | CLARK | 2004-07-07 | 2005-02-08 | 2005-03-01 |  |  | A | A |  | Transportation / Multimodal Planning Las Vegas | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET3YH223474 | 1702 | 13 | C723 | C351 | C723 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 314499 | DIESEL | ELKO | 1999-08-30 | 1999-08-30 | 1999-10-08 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2000 PLOW,8 YD SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1M2GR3GC1LM011376 | 1704 | 25 | C721 | C179 | C721 | 2018 | MACK | GR64F | 2018 WATER TRUCK | 24568 | DIESEL | CLARK | 2018-05-15 | 2019-05-30 | 2019-07-23 |  |  | A | A |  | Las Vegas Storm Water Maintenance Crew | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGGAET8YH223471 | 1705 | 13 | C724 | C381 | C724 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 101009 | DIESEL | WHITE PINE | 1999-11-05 | 1999-11-05 | 2014-08-05 | PARKER | PARKER | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 2000 PLOW PLOWS,REBUILD 2006 SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGA6R0MH367562 | 1706 | 13 | C723 | C351 | C723 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 66942 | DIESEL | ELKO | 1991-07-02 | 1991-12-03 | 2014-08-12 | PARKER 13 IQUAN | PARKER | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE 12FT RGHT HAND DISCHARGE,REVERSIBLE,REBUILD 2008 HENDERSON SANDER/HOPPER TYP | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1M2GR3GC3LM011377 | 1707 | 25 | C725 | C169 | C725 | 2018 | MACK | GR64F | 2018 WATER TRUCK | 9728 | DIESEL | CLARK | 2018-05-16 | 2019-05-30 | 2019-06-26 |  |  | A | A |  | Tonopah Storm Water Maintenance Crew | Tonopah | District 1 |  | Yes | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
3HTDTAPT4KN540057 | 1708 | 25 | C720 | C156 | C720 | 2019 | INTL | HX620 | 2019 INT'L HX 620 WATER TRUCK | 9707 | DIESEL | CLARK | 2018-05-30 | 2018-11-26 | 2019-01-08 |  |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FT7W2B61KEC69916 | 1710 | 3 | C723 | C301 | C723 | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 20972 | UNLEADED | ELKO | 2018-07-02 | 2018-10-09 | 2019-02-08 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7W2B61KEC69916 |  |  |  |  | 11.29.2022
1GAWGEFG0K1156729 | 1711 | 4 | C726 | C726 | C726 | 2019 | CHEVROLET | EXPRESS | PASSANGER VAN | 13823 | UNLEADED | ELKO | 2018-07-02 | 2018-11-20 | 2019-01-15 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ND52F75M180479 | 1712 | 1 | C721 | C721 | C721 | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 111728 | UNLEADED | CLARK | 2004-07-02 | 2005-02-08 | 2005-03-01 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ND52F75M180479
1GC1KREG8KF132643 | 1714 | 3 | C722 | C911 | C722 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | 26990 | TELEMATIC | WASHOE | 2018-07-12 | 2018-09-20 | 2019-06-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT6KED00874 | 1715 | 11E | C728 | C203 | C728 | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | 21103 | DIESEL | CHURCHILL | 2018-07-23 | 2019-02-08 | 2019-11-23 |  |  | A | A |  | Silver Springs Crew | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAET6YH223470 | 1722 | 13 | C728 | C281 | C728 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 157629 | DIESEL | CHURCHILL | 1999-10-06 | 1999-10-06 | 1999-10-08 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE JENSEN PLOW,8 YRD FLIMK SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1G1ND52F95M180239 | 1724 | 1 | C727 | A077 | C727 | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 85623 | UNLEADED | CARSON CITY | 2004-07-02 | 2005-02-08 | 2005-03-01 |  |  | A | A |  | Human Resources - Training | Carson City | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1HTGGAET9YH223480 | 1728 | 13 | C724 | C380 | C724 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 100299 | DIESEL | WHITE PINE | 1999-08-30 | 1999-08-30 | 2014-08-05 | PARKER | PARKER | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | REBUILD 2000 SANDER,REBUILD 2000 PLOWS,REBUILD 1999 PLOWS | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAYR5PH520976 | 1730 | 28 | C726 | C320 | C726 | 1993 | INTL | 2574 | DISTRIBUTOR TRUCK | 53959 | DIESEL | HUMBOLDT | 1993-06-17 | 1993-06-17 | 1993-06-17 |  |  | A | A |  | Winnemucca Yard Stockpile Control | Winnemucca | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1C4RJFAG8JC309721 | 1737 | 01A | C727 | C727 | C727 | 2018 | JEEP | CHEROKEE | 2018 GRAND CHAEROKEE SUV 4X4 | 43447 | UNLEADED | CARSON CITY | 2017-12-04 | 2018-03-08 | 2018-04-12 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZC5ST4KF111596 | 1741 | 1 | C721 | C052 | C721 | 2019 | CHEVROLET | MALIBU | 2019 CHEV MALIBU 1.5L TURBO | 3065 | SMARTWAY | CLARK | 2018-08-30 | 2018-11-15 | 2018-11-29 |  |  | A | A |  | External Civil Rights | Carson City | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
3C7WRNBL0LG253200 | 1742 | 11A | C721 | C102 | C721 | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 AERIAL LIFT | 4206 | BIO DIESEL | CLARK | 2020-08-20 | 2021-08-17 | 2021-12-01 |  |  |  | A | New - Nov 2022 | Las Vegas Facilities Crew | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | 3C7WRNBL0LG253200 | [5 empty] | 1/18/2023: VIN number has been corrected based on the email received from Billie.
1GNEVFKW8KJ247640 | 1743 | 01A | C727 | C727 | C727 | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | 23619 | E-85 | CLARK | 2019-02-11 | 2019-05-06 | 2019-08-21 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4GT5LED97274 | 1744 | 11E | C721 | C153 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | 16051 | BIO DIESEL | CLARK | 2020-01-29 | 2020-11-10 | 2021-04-05 |  |  | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FDSF35Y66EA69936 | 1745 | 11J | C727 | C813 | C727 | 2006 | FORD | F-350 | UTILITY TRUCK | 136239 | UNLEADED | CARSON CITY | 2003-07-01 | 2005-11-30 | 2005-12-15 |  |  | A | A |  | Planning Traffic | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KREY0KF229019 | 1748 | 3 | C767 | C201 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | 64348 | BIO DIESEL | WASHOE | 2018-10-03 | 2019-05-14 | 2019-08-13 |  |  | A | A |  | Reno District Administration | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KREG4KF230021 | 1749 | 3 | C767 | C243 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | 15563 | TELEMATIC | WASHOE | 2018-10-03 | 2019-03-22 | 2019-09-10 |  |  | A | A |  | #N/A | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT4LED97270 | 1750 | 11E | C721 | C145 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | 2471 | BIO DIESEL | CLARK | 2020-02-04 | 2020-12-11 | 2021-07-06 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GT4LED97270 |  |  |  |  | 11.22.2022
2HSCHAER1YC042949 | 1751 | 14 | C722 | C272 | C722 | 2000 | INTL | 9900 | TRACTOR TRUCK | 175094 | DIESEL | CARSON CITY | 1999-12-17 | 1999-12-17 | 2000-02-08 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGLANT0YH260179 | 1752 | 20 | C721 | C158 | C721 | 2000 | INTL | 2674 | CULVERT CLEANER | 127444 | DIESEL | CLARK | 1999-10-04 | 1999-10-04 | 1999-10-18 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 1753 | 3 | C767 | C767 | #N/A | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 272793 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
2HSFMAMR2RCO10202 | 1757 | 14 | C725 | C170 | C725 | 1994 | INTL | F9200 | TRACTOR TRUCK | 299578 | DIESEL | NYE | 1994-07-28 | 1994-12-29 | 1994-12-29 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 9 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTSF20PX5EC29280 | 1759 | 3 | C721 | C902 | C721 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 185681 | BIO DIESEL | CLARK | 2004-07-02 | 2005-04-08 | 2005-05-11 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KREG6KF231574 | 1761 | 3 | C724 | C342 | C724 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | 40135 | FLEX FUEL | WHITE PINE | 2018-10-03 | 2019-05-14 | 2019-12-23 |  |  | A | A |  | Ely Striping Crew | Ely | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1KREG8KF228370 | 1763 | 3 | C724 | C385 | C724 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | 13844 | UNLEADED | WHITE PINE | 2018-01-03 | 2019-05-06 | 2019-08-11 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
2GC2KREG2K1159817 | 1766 | 3 | C767 | C028 | C767 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICKUP | 16919 | UNLEADED | CARSON CITY | 2018-10-17 | 2019-03-14 | 2019-09-16 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12225NB01206 | 1767 | 5 | C722 | C905 | C767 | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 142997 | UNLEADED | CARSON CITY | 2004-07-02 | 2005-03-01 | 2005-05-10 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT8LED97269 | 1768 | 11E | C721 | C721 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | 434 | BIO DIESEL | CLARK | 2020-02-04 | 2020-12-11 | 2021-08-02 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GT8LED97269 |  |  |  |  | 11.23.2022
1GC1KREG7KF229932 | 1769 | 3 | C721 | C901 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | 5285 | E-85 | CLARK | 2018-10-03 | 2019-05-14 | 2019-11-26 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GC1CREG3KF231271 | 1771 | 3 | C723 | C301 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP TRUCK | 17762 | UNLEADED | CLARK | 2018-10-03 | 2019-05-14 | 2019-12-16 |  |  | A | A |  | Elko District Administration | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
796-2115 | 1773 | 42 | C767 | C250 | C767 | 1996 | KODIAK | 6060- | ROTARY SNOW BLOWER | 1311 | DIESEL | WASHOE | 1996-07-24 | 1996-11-12 | 1996-11-12 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Full Project |  | #N/A
1GC1CREG7KF231970 | 1778 | 3 | C723 | C908 | C723 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | 39773 | UNLEADED | ELKO | 2018-01-03 | 2019-05-08 | 2019-11-05 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GC1CREG7KF231970 |  | Yes |  |  | 11.28.2022
1GC1CREG3KF228208 | 1780 | 3 | C723 | C723 | C723 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | 23386 | UNLEADED | ELKO | 2018-10-03 | 2019-05-06 | 2019-12-12 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GC1CREG3KF228208 |  | Yes |  |  | 11.28.2022
1GCRYAEF7KZ343048 | 1782 | 5 | C722 | C911 | C722 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 14802 | FLEX FUEL | WASHOE | 2018-10-03 | 2019-06-04 | 2019-11-26 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1CCSKDTRL14012100 | 1788 | 76 | C767 | C026 | C767 | 1996 | CYBR | SFT50 | REBUILT 2021 INTERNATIONAL CYBERNETICS SKID TRAILER | 46700 |  | WASHOE | 1996-02-15 | 1996-03-13 | 1996-03-13 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P15EC29278 | 1789 | 3 | C721 | C926 | C721 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 158483 | BIO DIESEL | CLARK | 2004-07-03 | 2005-04-12 | 2005-05-16 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12245NB01207 | 1791 | 5 | C728 | C718 | C728 | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 219693 | UNLEADED | CHURCHILL | 2004-07-02 | 2005-02-18 | 2005-07-06 |  |  | A | A |  | Fallon Stockroom | Fallon | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEF7KZ343275 | 1792 | 5 | C767 | C904 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 17207 | FLEX FUEL | WASHOE | 2018-10-03 | 2019-06-04 | 2019-11-26 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEF1KZ344535 | 1795 | 5 | C767 | C905 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 2237 | FLEX FUEL | WASHOE | 2018-10-03 | 2019-06-13 | 2019-11-14 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEF7KZ343793 | 1796 | 5 | C767 | C910 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK | 3255 | FLEX FUEL | WASHOE | 2018-10-03 | 2019-07-17 | 2019-09-30 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E57KKC71642 | 1798 | 5 | C722 | C907 | C722 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 20542 | E-85 | CLARK | 2018-10-29 | 2019-03-04 | 2019-09-03 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20PX5EC29277 | 1801 | 3 | C721 | C922 | C721 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 129470 | BIO DIESEL | CLARK | 2004-07-02 | 2005-04-11 | 2005-05-27 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12265NB01208 | 1803 | 5 | C723 | C918 | C723 | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 167236 | UNLEADED | ELKO | 2004-07-02 | 2005-02-18 | 2005-04-13 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTRF12265NB01208 |  |  |  |  | 11.28.2022
1FTEX1C53KKC71639 | 1804 | 5 | C722 | C911 | C722 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 2228 | FLEX FUEL | CARSON CITY | 2018-10-29 | 2019-03-04 | 2020-05-12 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSX21P25EC29284 | 1805 | 3 | C767 | C240 | C767 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 201015 | BIO DIESEL | WASHOE | 2004-07-02 | 2005-04-01 | 2005-09-08 |  |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT6LED97271 | 1807 | 11E | C721 | C141 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | 6752 | BIO DIESEL | CLARK | 2020-02-04 | 2021-01-05 | 2021-03-08 |  |  | A | A |  | Las Vegas Striping Crew 2 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GT6LED97271 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
5KKHAEDV6NPNC5513 | 1808 | 25 | C723 | C350 | C723 | 2021 | WESTERN ST | 4900 | 2021 WESTERN STAR 4900 WATER TRUCK | 3933 | DIESEL | ELKO | 2020-11-03 | 2021-05-27 | 2022-01-27 | CASAPPA |  |  | A | New - Nov 2022 | Elko Maintenance Crew 1 | Elko | District 3 |  |  | 8 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C51KKC71641 | 1814 | 5 | C767 | C904 | C767 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | 7586 | FLEX FUEL | WASHOE | 2018-10-29 | 2019-03-04 | 2020-06-08 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGA6R4MH367564 | 1821 | 11B | C767 | C767 | C767 | 1991 | INTL | F2574 | TANDEM AXLE CRANE TRUCK REBUILD | 1484 | DIESEL | WASHOE | 1991-07-02 | 1991-12-03 | 2017-11-06 | SUNFAB |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 6 | J1939 | [5 empty] | SPRATRONICS DE ICER | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pilot |  | #N/A
1FTFX1E51KKE96689 | 1823 | 5 | C767 | C910 | C767 | 2019 | FORD | F-150 | 2019 FORD 1/2 TON PICK UP | 3062 | FLEX FUEL | WASHOE | 2019-06-06 | 2019-10-10 | 2020-05-27 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV5NPNE5753 | 1825 | 25 | C721 | C122 | C721 | 2021 | WESTERN ST | 4900 | 2021 WESTERN STAR 4900 WATER TRUCK | 2311 | DIESEL | CLARK | 2020-11-18 | 2022-04-07 | 2022-04-18 | CASAPPA |  |  | A | New - Nov 2022 | Alamo Maintenance Crew | Las Vegas | District 1 |  |  | 8 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 1826 | 11H | C723 | C331 | #N/A | 2007 | FORD | F-450 | FLATRACK TRUCK | 251074 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Ruby Valley Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A | Yes
1FD0X4GT1LED97272 | 1827 | 11E | C721 | C151 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | 1908 | BIO DIESEL | CLARK | 2020-01-29 | 2020-12-09 | 2021-07-19 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0X4GT1LED97272 |  |  |  |  | 11.22.2022
3ALHG3DV0PDNJ2062 | 1828 | 28 | C725 | C170 | C725 | 2021 | FREIGHTLNR | 114SD | 2021 FREIGHTLINER 114SD TANDEM AXEL DISTRIBTOR TRUCK | 1712 | DIESEL | NYE | 2021-06-24 | 2022-04-26 | 2022-08-04 | DANFOSS |  |  | A | New - Nov 2022 | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  |  | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDAF56P45EC20655 | 1829 | 11A | C723 | C340 | C723 | 2005 | FORD | F-550 | FLANNIGAN SHOP TRUCK | 203951 | DIESEL | ELKO | 2004-07-02 | 2005-04-15 | 2005-05-02 |  |  | A | A |  | Elko Striping Crew | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FDAF56P45EC20655 |  | Yes |  |  | 11.29.2022
1FDXF47P66EB73133 | 1830 | 11J | C722 | C271 | C722 | 2006 | FORD | F-450 | UTILITY TRUCK 4X4 | 83702 | DIESEL | CARSON CITY | 2004-07-01 | 2006-04-13 | 2006-08-21 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1A9N25DB5XR059001 | 1832 | 24 | C723 | C324 | C723 | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | 81155 | DIESEL | ELKO | 1998-12-15 | 1998-12-15 | 1999-02-02 |  |  | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1C52KKD06198 | 1833 | 5 | C723 | C301 | C723 | 2019 | FORD | F-150 | 2019 1/2 TON PICKUP TRUCK | 20632 | FLEX FUEL | ELKO | 2018-12-17 | 2019-03-18 | 2019-07-24 |  |  | A | A |  | Elko District Administration | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1C52KKD06198 |  |  |  |  | 11.29.2022
1HTZPGDR5GHA28804 | 1834 | 11B | C725 | C725 | C725 | 1986 | INTL | F2574 | CRANE TRUCK CONVERTED | 312970 | DIESEL | NYE | 1986-02-26 | 1986-04-11 | 1986-04-11 |  |  | A | A |  | Tonopah District Repair Shop | Tonopah | District 1 |  | Yes | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDAF57PX5ED37090 | 1835 | 11H | C725 | C143 | C725 | 2005 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | 181651 | DIESEL | NYE | 2004-07-01 | 2005-07-26 | 2005-08-04 |  |  | A | A |  | Tonopah Striping Crew 1 | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2NPLHD8X56M642538 | 1836 | 11C | C720 | C159 | C720 | 2005 | PETERBILT | 335 | FUEL LUBE TRUCK | 176140 | DIESEL | CLARK | 2004-09-29 | 2006-01-24 | 2006-01-31 | PARKER |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FDXF46P05EB40385 | 1837 | 11D | C721 | C160 | C721 | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | 132537 | BIO DIESEL | CLARK | 2004-07-07 | 2005-03-11 | 2005-05-04 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46P25EB40386 | 1838 | 11D | C721 | C160 | C721 | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | 138323 | BIO DIESEL | CLARK | 2004-07-07 | 2005-03-11 | 2005-04-11 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXX47P67EA85780 | 1840 | 11E | C722 | C272 | C722 | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | 302184 | DIESEL | CARSON CITY | 2004-07-01 | 2007-01-18 | 2007-03-02 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FM5K8B86KGA77754 | 1844 | 01A | C767 | C201 | C767 | 2018 | FORD | EXPLORER | 2018 SUV | 11140 | TELEMATIC | WASHOE | 2018-09-25 | 2019-01-18 | 2019-04-09 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1A9N25DB7XR059002 | 1847 | 24 | C726 | C372 | C726 | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | 46421 | DIESEL | HUMBOLDT | 1998-12-15 | 1998-12-15 | 1999-02-01 |  |  | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1GCUYAEF4KZ336620 | 1849 | 5 | C728 | C201 | C728 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 26786 | FLEX FUEL | LYON | 2018-10-03 | 2019-06-04 | 2020-03-06 |  |  | A | A |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCUYAEFXKZ336220 | 1850 | 5 | C767 | C204 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 38527 | FLEX FUEL | WASHOE | 2018-10-03 | 2019-06-04 | 2019-09-16 |  |  | A | A |  | Permits | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEFXKZ343979 | 1851 | 5 | C767 | C040 | C767 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 14021 | FLEX FUEL | CARSON CITY | 2018-10-03 | 2019-01-01 | 2019-11-15 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HT9LED97275 | 1852 | 11E | C721 | C129 | C721 | 2020 | FORD | F-450 | 2020 FORD F-450 1-2 TON DUMP/GARBAGE TRUCK | 11602 | BIO DIESEL | CLARK | 2020-01-31 | 2021-01-12 | 2022-02-22 |  |  |  | A | New - Nov 2022 | Charleston Maintenance Crew | Las Vegas | District 1 |  |  | 5 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KJJAED19LPLU1039 | 1853 | 14 | C723 | C723 | C723 | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | 12949 | DIESEL | ELKO | 2018-12-18 | 2019-08-06 | 2019-09-24 | MUNCIE |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KJJAED17LPLU1038 | 1854 | 14 | C767 | C028 | C767 | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | 5211 | DIESEL | CARSON CITY | 2018-12-18 | 2019-07-26 | 2019-08-29 | MUNCIE |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF47PX7EA85770 | 1856 | 11E | C767 | C252 | C767 | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | 277692 | BIO DIESEL | WASHOE | 2004-07-01 | 2006-12-14 | 2007-04-13 | DYNA JACK |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X5HT4KEF20341 | 1857 | 11F | C721 | C721 | C721 | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | 31149 | BIO DIESEL | CLARK | 2019-08-16 | 2019-11-20 | 2019-12-10 | PARKER |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FD0X5HT4KEF20341 |  | Yes | 11.21.2022 | 11.21.2022 | 11.21.2022
1FD0X5HT2KEF20340 | 1858 | 11F | C720 | C720 | C720 | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | 17318 | BIO DIESEL | CLARK | 2019-08-16 | 2019-11-20 | 2019-12-19 | PARKER |  | A | A |  | South Las Vegas District Repair Shop | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FD0X5HT2KEF20340 |  | Yes | 11.21.2022 | 11.21.2022 | 11.21.2022
1FD0X5HT6KEF20339 | 1859 | 11F | C728 | C728 | C728 | 2019 | FORD | F-550 | F-550 SERVICE TRUCK | 10622 | DIESEL | CHURCHILL | 2019-08-16 | 2019-11-20 | 2020-04-14 | PARKER |  | A | A |  | Fallon District Repair Shop | Fallon | District 2 | Service Truck | No | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4GT0KED95463 | 1860 | 11D | C721 | C122 | C721 | 2019 | FORD | F-450 | 2019 FORD COMPACTOR TRUCK | 25467 | DIESEL | LINCOLN | 2018-10-29 | 2019-07-26 | 2020-05-05 | FORCE |  | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FD0X4GT2KED95464 | 1862 | 11E | C721 | C154 | C721 | 2019 | FORD | F-450 | 2019 FORD 1/2 TON DUMP/GARBAGE TRUCK | 16570 | BIO DIESEL | CLARK | 2018-10-29 | 2019-05-21 | 2020-03-19 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 1863 | 11S | C721 | C145 | #N/A | 2007 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | 165124 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | FLATRACK BODY SWAPLOADER,DUMP BODY SWAPLOADER,ARROWBOARD VEHICLE MOUNTED | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Deleted |  | #N/A
1HTGGA6R7MH367560 | 1865 | 13 | C726 | C370 | C726 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 39190 | DIESEL | HUMBOLDT | 1991-05-17 | 1991-05-17 | 2014-05-28 | PARKER 13 IQUAN | PARKER | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | TWO-WAY SWING PLOW,FLINK SANDER 8 CU YD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HY9KED95460 | 1866 | 11E | C767 | C225 | C767 | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | 24559 | TELEMATIC | WASHOE | 2018-10-29 | 2019-06-11 | 2020-09-21 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
3FRPF65E18V647601 | 1868 | 11F | C723 | C723 | C723 | 2008 | FORD | F-650 | SERVICE TRUCK W/AUTOCRANE | 133163 | DIESEL | ELKO | 2004-07-01 | 2007-08-10 | 2007-09-11 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3FRPF65E18V647601 |  |  |  |  | 11.30.2022
1FDAF57P45EC20654 | 1869 | 11F | C767 | C767 | C767 | 2005 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DIESEL | 208813 | BIO DIESEL | WASHOE | 2004-10-18 | 2005-07-11 | 2005-07-20 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX47P76EB73140 | 1872 | 11J | C723 | C093 | C723 | 2006 | FORD | F-450 | UTILITY TRUCK | 261241 | DIESEL | WHITE PINE | 2004-07-01 | 2006-02-13 | 2006-03-02 |  |  | A | A |  | Communications Elko | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A | [5 empty] | 11/16/2022: This vehicle got transferred to Ely and no longer belongs to Elko. So need to replace this vehicle targeted intially for Pre-Pilot with some other light duty vehicle from Elko. Also, updated the location of this vehicle from Elko to Ely.
1FD0W4HY0KED95461 | 1874 | 11E | C722 | C235 | C722 | 2019 | FORD | F-450 | 2019 FORD F-450 1 TON DUMP TRUCK 4X4 | 20532 | UNLEADED | CARSON CITY | 2018-10-30 | 2019-03-14 | 2020-11-03 |  |  | A | A |  | Wellington Maintenance Crew | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GTEC14W5WZ533595 | 1876 | 5 | C767 | C202 | C767 | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | 144618 | RFG | WASHOE | 1998-03-26 | 1998-04-27 | 1998-04-27 |  |  | A | A |  | Reno Service Crew | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT7KED95462 | 1877 | 11E | C767 | C250 | C767 | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | 37229 | DIESEL | WASHOE | 2018-10-30 | 2019-05-29 | 2019-11-08 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FDUF4HY9KDA13435 | 1879 | 11E | C724 | C385 | C724 | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | 26350 | UNLEADED | EUREKA | 2018-10-30 | 2019-05-06 | 2019-10-10 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDUF4HY7KDA13434 | 1881 | 11E | C724 | C384 | C724 | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | 30109 | UNLEADED | LANDER | 2018-10-30 | 2019-05-06 | 2020-02-12 |  |  | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY1KED95465 | 1882 | 11E | C724 | C319 | C724 | 2019 | FORD | F-450 | 2019 1/2 TON DUMP/GARBAGE TRUCK | 25149 | UNLEADED | WHITE PINE | 2018-10-30 | 2019-04-03 | 2020-02-19 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITEREADER ARROWBOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2GCVKNEC0K1161648 | 1883 | 5 | C723 | C040 | C723 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 17474 | FLEX FUEL | ELKO | 2018-10-30 | 2019-03-22 | 2020-01-06 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 2GCVKNEC0K1161648 |  |  |  |  | 11.29.2022
1FDXX47P96EB73141 | 1884 | 11F | C721 | C021 | C721 | 2006 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | 38267 | BIO DIESEL | CLARK | 2004-07-01 | 2006-04-05 | 2006-06-21 |  |  | A | A |  | Materials Las Vegas Lab | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDXX47P96EB73141 |  |  |  |  | 11.23.2022
1GCPWAEF6KZ336962 | 1886 | 5 | C721 | C926 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 21565 | E-85 | CLARK | 2018-11-29 | 2019-07-03 | 2019-12-16 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
2XKDDB9X3JM510885 | 1887 | 14 | C725 | C171 | C725 | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | 430471 | DIESEL | NYE | 1990-11-09 | 1991-01-18 | 2010-03-23 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCPWAEF3KZ337907 | 1888 | 5 | C721 | C903 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 11629 | E-85 | CLARK | 2018-11-29 | 2019-06-04 | 2019-08-29 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCPWAEF0KZ337718 | 1889 | 5 | C721 | C903 | C721 | 2019 | CHEVROLET | 1500 | 2019 1/2 TON PICK UP | 9075 | E-85 | CLARK | 2018-11-29 | 2019-06-04 | 2019-12-09 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCPWAEF9KZ336955 | 1890 | 5 | C721 | C914 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 18410 | E-85 | CLARK | 2018-11-29 | 2019-06-04 | 2019-12-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRYAEF4KZ343136 | 1891 | 5 | C721 | C915 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 21030 | E-85 | CLARK | 2018-11-29 | 2019-06-04 | 2020-01-03 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCPWAEF4KZ337883 | 1892 | 5 | C721 | C916 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 23173 | E-85 | CLARK | 2018-11-29 | 2019-06-04 | 2019-11-04 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRWAEF4KZ343904 | 1893 | 5 | C721 | C926 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 13726 | E-85 | CLARK | 2018-11-29 | 2019-06-13 | 2020-01-31 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X37D653140 | 1895 | 13 | C723 | C324 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 201573 | DIESEL | ELKO | 2004-07-01 | 2006-12-29 | 2007-01-11 | PARKER | PARKER | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDEX6PW45935 | 1896 | 13 | C723 | C327 | C723 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 244412 | DIESEL | ELKO | 2004-07-01 | 2006-01-10 | 2006-02-03 | PARKER | PARKER | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,REVERSIBLE PLOW,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot |  |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
5KKHAEDE26PW45945 | 1897 | 13 | C722 | C227 | C722 | 2006 | WESTERN ST | 4900 | TANDEM AXLE TRUCK | 179775 | DIESEL | DOUGLAS | 2004-07-01 | 2006-02-28 | 2006-03-07 | PARKER | PARKER | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | EPOKE |  |  |  | PLOW WING,JENSEN REVERSIBLE PLOW,SANDER EPOKE | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDEX6PW45949 | 1898 | 13S | C725 | C172 | C725 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 200889 | DIESEL | NYE | 2004-07-01 | 2006-07-13 | 2006-08-01 | PARKER | PARKER | A | A |  | Big Smokey Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE46PW45946 | 1899 | 13 | C722 | C271 | C722 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 166861 | DIESEL | CARSON CITY | 2004-07-01 | 2006-04-06 | 2006-05-25 | PARKER | PARKER | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | EPOKE |  |  |  | SANDER 8 YARD,PLOW ONE WAY,EPOKE SANDER,2021 HENKE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDUF5GT9FEB82138 | 1900 | 11A | C721 | C140 | C721 | 2016 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | 106365 | BIO DIESEL | CLARK | 2015-05-15 | 2015-10-06 | 2015-10-06 |  |  | A | A |  | Las Vegas Sign Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FDUF5GT9FEB82138
2XKDDB9X5JM510886 | 1901 | 14 | C726 | C374 | C726 | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | 645091 | DIESEL | HUMBOLDT | 1990-11-09 | 1990-11-09 | 2011-04-25 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF5GT0FEB82139 | 1903 | 11A | C721 | C140 | C721 | 2015 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | 104505 | BIO DIESEL | CLARK | 2014-08-04 | 2016-02-18 | 2016-10-11 |  |  | A | A |  | Las Vegas Sign Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FDUF5GT0FEB82139
5KKHAEDE86PW45948 | 1904 | 13 | C728 | C280 | C728 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 141175 | DIESEL | CHURCHILL | 2004-07-01 | 2006-01-24 | 2006-03-07 | PARKER | PARKER | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT9FEB71762 | 1905 | 11H | C725 | C176 | C725 | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | 129116 | DIESEL | MINERAL | 2014-07-02 | 2014-09-23 | 2015-02-02 |  |  | A | A |  | Mina Maintenance Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor |  |  |  |  | ARROW BOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HT7FEB82188 | 1906 | 11H | C725 | C171 | C725 | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | 133262 | DIESEL | MINERAL | 2014-07-10 | 2014-09-24 | 2015-01-28 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor |  |  |  |  | ARROW BOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
3GCNWAEF7KG271918 | 1908 | 5 | C721 | C902 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 8230 | E-85 | CLARK | 2018-11-29 | 2019-08-19 | 2020-03-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCNWAEF6KG274020 | 1909 | 5 | C721 | C916 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 11757 | E-85 | CLARK | 2018-11-29 | 2019-08-02 | 2020-03-03 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [5 empty] | SKIDSTER PICKUP BROOM | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT0FEB71763 | 1911 | 11H | C725 | C172 | C725 | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | 122871 | DIESEL | NYE | 2014-07-02 | 2014-09-23 | 2015-02-26 |  |  | A | A |  | Big Smokey Maintenance Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEBGDGPHL1456 | 1912 | 11B | C720 | C141 | C720 | 2015 | WESTERN ST | 4900SF | FLATRACK W/CRANE | 46417 | DIESEL | CLARK | 2015-05-08 | 2016-05-11 | 2016-05-25 | FORCE AMERICA | DANFOSS | A | A |  | Las Vegas Striping Crew 2 | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTZMGBR2JH569728 | 1914 | 11G | C721 | C121 | C721 | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | 191219 | DIESEL | CLARK | 1988-04-26 | 1988-06-29 | 1988-06-29 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 6 | J1939 | [5 empty] | 2001 ATTENUATOR TRUCK MOUNTED | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X87D653148 | 1915 | 13 | C722 | C272 | C722 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 150210 | DIESEL | CARSON CITY | 2004-07-01 | 2006-10-12 | 2006-12-05 | PARKER | PARKER | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | FLINK SANDER,HEAVY DUTY WING PLOW,PLOW REVERSIBLE | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDUF4HT0FEB61834 | 1916 | 11E | C725 | C147 | C725 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 212600 | DIESEL | NYE | 2014-07-03 | 2014-09-24 | 2015-02-26 |  |  | A | A |  | Tonopah Landscape Crew 1 | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HT8FEB71765 | 1917 | 11E | C720 | C126 | C720 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 119278 | DIESEL | CLARK | 2014-07-02 | 2014-09-23 | 2015-02-26 |  |  | A | A |  | Mountain Springs Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKHAEDE86PW45934 | 1918 | 13 | C723 | C351 | C723 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | 196755 | DIESEL | ELKO | 2004-07-01 | 2006-01-24 | 2006-02-03 | PARKER | PARKER | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HT6FEB71764 | 1919 | 11E | C720 | C152 | C720 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 106764 | DIESEL | CLARK | 2014-07-02 | 2014-09-23 | 2015-03-26 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0X4HT6FEB71764 |  |  |  |  | 11.22.2022
1FVACYDTXFHGS1326 | 1920 | 24 | C720 | C154 | C720 | 2015 | ELGIN | EAGLE | SELF PROPELLED DUSTLESS SWEEPER | 62426 | DIESEL | CLARK | 2014-06-20 | 2014-09-23 | 2015-08-04 |  | SN-SF | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACYDTXFHGS1326
1GCRWAEF6KZ342690 | 1921 | 5 | C721 | C914 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 7768 | E-85 | CLARK | 2018-11-29 | 2019-06-04 | 2020-03-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3GCNWAEF0KG271906 | 1922 | 5 | C721 | C906 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 3932 | E-85 | CLARK | 2018-11-29 | 2019-08-02 | 2020-02-25 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HY4FEB82189 | 1923 | 11H | C767 | C241 | C767 | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | 83336 | RFG | WASHOE | 2014-07-01 | 2014-09-24 | 2015-06-04 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD8X3F68FEB55530 | 1924 | 11F | C767 | C092 | C767 | 2015 | FORD | F-350 | 1 TON SERVICE TRUCK 4X4 | 59645 | RFG | WASHOE | 2014-07-02 | 2014-09-25 | 2015-01-05 |  |  | A | A |  | Communications Reno | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
5KKHAEDE56PW45941 | 1925 | 13S | C726 | C372 | C726 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 141853 | DIESEL | HUMBOLDT | 2004-07-01 | 2006-04-28 | 2006-07-31 | PARKER | PARKER | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW,8 YD STAINLESS STEEL SANDER,PLOW ONE WAY,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0X5HT8FEB55460 | 1926 | 11A | C767 | C240 | C767 | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 BIO-DIESEL | 112989 | BIO DIESEL | WASHOE | 2014-07-02 | 2014-09-25 | 2015-04-08 |  |  | A | A |  | Reno Sign Crew 1 | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTZMGBR2JH569731 | 1928 | 11G | C720 | C142 | C720 | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | 205339 | DIESEL | CLARK | 1988-04-26 | 1988-04-26 | 1988-04-26 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 6 | J1939 | [5 empty] | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE76PW45939 | 1929 | 13S | C721 | C151 | C721 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 138195 | DIESEL | CLARK | 2004-07-01 | 2006-06-30 | 2006-07-17 | PARKER | PARKER | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
3GCNWAEF0KG273638 | 1930 | 5 | C721 | C903 | C721 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | 19506 | E-85 | CLARK | 2018-11-29 | 2019-08-19 | 2019-11-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE66PW45950 | 1932 | 13S | C720 | C152 | C720 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 184877 | DIESEL | CLARK | 2004-07-01 | 2006-06-15 | 2006-07-10 | PARKER | PARKER | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0X5HT1FEB55459 | 1934 | 11A | C728 | C283 | C728 | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | 100910 | DIESEL | PERSHING | 2014-07-02 | 2014-09-25 | 2015-06-24 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDEX6PW45952 | 1935 | 13S | C720 | C150 | C720 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 107271 | DIESEL | CLARK | 2004-07-01 | 2006-04-13 | 2006-06-02 | PARKER | PARKER | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HT5FEB71805 | 1936 | 11D | C767 | C245 | C767 | 2015 | FORD | F-450 | TRASH COMPACTOR 4X4 BIO-DIESEL | 32356 | BIO DIESEL | WASHOE | 2014-07-02 | 2014-09-24 | 2015-03-06 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FD0X4HT1FEB71803 | 1937 | 11D | C767 | C245 | C767 | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 BIO-DIESEL | 36639 | BIO DIESEL | WASHOE | 2014-07-02 | 2014-09-24 | 2015-03-06 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FD0X4HT3FEB71804 | 1938 | 11D | C722 | C247 | C722 | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 | 90665 | DIESEL | CARSON CITY | 2014-07-02 | 2014-12-15 | 2015-03-06 |  |  | A | A |  | Carson City Landscape Crew 3 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY4FEB71726 | 1939 | 11E | C728 | C281 | C728 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 66086 | UNLEADED | CHURCHILL | 2014-07-01 | 2014-12-04 | 2016-11-21 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY2FEB71725 | 1940 | 11E | C767 | C253 | C767 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 103449 | RFG | WASHOE | 2014-07-01 | 2014-09-23 | 2015-04-23 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTWYSBT55J131306 | 1942 | 20 | C723 | C350 | C723 | 2005 | INTL | 7600 | CULVERT CLEANER | 32879 | DIESEL | ELKO | 2004-07-02 | 2005-05-09 | 2005-07-12 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY9FEB71723 | 1943 | 11E | C728 | C236 | C728 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 125435 | UNLEADED | LYON | 2014-07-02 | 2014-12-01 | 2016-02-23 |  |  | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HTXFEB71721 | 1947 | 11E | C767 | C234 | C767 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 127747 | DIESEL | STOREY | 2014-07-01 | 2014-09-24 | 2015-05-20 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | SNOWPLOW 8' | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HT1FEB71722 | 1948 | 11E | C722 | C227 | C722 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 117059 | DIESEL | DOUGLAS | 2014-07-02 | 2014-11-05 | 2015-12-21 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | SNOW PLOW,ARROW BOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY9FED57620 | 1949 | 11E | C727 | A073 | C727 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 42854 | RFG | WASHOE | 2014-07-02 | 2015-07-20 | 2016-05-05 |  |  | A | A |  | Building & Grounds | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2014 SNOW PLOW SNOW DOGG,2014 SALT DOGG SPREADER | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY0FEB71724 | 1952 | 11E | C767 | C252 | C767 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 111497 | RFG | WASHOE | 2014-07-02 | 2014-09-25 | 2015-08-27 |  |  | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  | GO9 |  |  |  | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FD0X4HY0FEB71724
1FD0W4HYXFEB71720 | 1953 | 11E | C728 | C282 | C728 | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | 117159 | UNLEADED | CHURCHILL | 2014-07-02 | 2014-10-30 | 2015-07-21 |  |  | A | A |  | Cold Springs Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | ROCK PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X5HY8GEA29709 | 1954 | 11F | C728 | C728 | C728 | 2016 | FORD | F-550 | SERVICE TRUCK 4X4 | 30462 | UNLEADED | CHURCHILL | 2015-04-16 | 2015-04-29 | 2015-09-29 |  |  | A | A |  | Fallon District Repair Shop | Fallon | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
2NP2HJ7X9GM355054 | 1955 | 11H | C767 | C253 | C767 | 2016 | PETERBILT | 337 | SINGLE AXLE FLATRACK TRUCK | 5232 | DIESEL | WASHOE | 2015-06-23 | 2015-12-21 | 2016-05-17 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1NPTL70XXGD350998 | 1956 | 13 | C767 | C253 | C767 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 30943 | DIESEL | WASHOE | 2015-06-15 | 2015-12-02 | 2016-07-06 | PARKER IQUAN | PARKER IQUAN | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1FTMF1CM4EKF79462 | 1959 | 5 | C723 | C908 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 104505 | UNLEADED | ELKO | 2014-07-02 | 2014-09-25 | 2015-02-02 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM4EKF79462 |  |  |  |  | 11.30.2022
1FD0W4GY8FEB61835 | 1960 | 11H | C723 | C351 | C723 | 2015 | FORD | F-450 | FLATRACK TRUCK | 141229 | UNLEADED | ELKO | 2014-07-01 | 2014-09-23 | 2015-02-09 |  |  | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | HENKE 11 FT REV SNOW PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GY8FEB61835 |  |  |  |  | 11.28.2022
1FD0W4GYXFEB61836 | 1961 | 11H | C723 | C332 | C723 | 2015 | FORD | F-450 | FLATRACK TRUCK | 161676 | UNLEADED | ELKO | 2014-07-01 | 2014-09-23 | 2015-02-27 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4GY6FEB61803 | 1962 | 11H | C723 | C335 | C723 | 2015 | FORD | F-450 | FLATRACK TRUCK W/LIFT GATE | 193308 | UNLEADED | ELKO | 2014-07-01 | 2014-09-23 | 2015-03-06 |  |  | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0W4GY1FEB61837 | 1963 | 11E | C723 | C350 | C723 | 2015 | FORD | F-450 | DUMP TRUCK | 153484 | UNLEADED | ELKO | 2014-07-01 | 2014-09-24 | 2015-02-27 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GY1FEB61837 |  |  |  |  | 11.29.2022
1FDUF4GY2FEB61833 | 1964 | 11E | C723 | C327 | C723 | 2015 | FORD | F-450 | DUMP TRUCK | 102647 | UNLEADED | ELKO | 2014-07-01 | 2014-09-24 | 2015-02-05 |  |  | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDUF4GY2FEB61833 | Yes-Pilot |  |  |  | 11.29.2022 | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1NPTL70X6GD351002 | 1965 | 13 | C723 | C332 | C723 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 42653 | DIESEL | ELKO | 2015-06-15 | 2015-12-02 | 2016-09-23 | PARKER IQUAN | PARKER IQUAN | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X2GD351000 | 1966 | 13 | C723 | C350 | C723 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 51017 | DIESEL | ELKO | 2015-06-15 | 2015-12-02 | 2016-12-02 | PARKER IQUAN | PARKER IQUAN | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GY9KEE58221 | 1967 | 11H | C723 | C350 | C723 | 2019 | FORD | F-450 | 2019 FLATRACK | 34176 | UNLEADED | ELKO | 2018-12-06 | 2019-08-06 | 2020-04-06 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GY9KEE58221 |  | Yes |  |  | 11.29.2022
1NPTL70X4GD351001 | 1968 | 13 | C723 | C351 | C723 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 26811 | DIESEL | ELKO | 2015-06-15 | 2015-12-02 | 2016-09-23 | PARKER IQUAN | PARKER IQUAN | A | A |  | Elko Maintenance Crew 2 | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FM5K8B82FGB03661 | 1969 | 01A | C727 | C805 | C727 | 2015 | FORD | EXPLORER | SUV 4X4 | 68399 | UNLEADED | CARSON CITY | 2014-08-06 | 2014-09-25 | 2015-01-06 |  |  | A | A |  | Roadway Systems | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT5KEE58222 | 1970 | 11J | C721 | C152 | C721 | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | 24487 | BIO DIESEL | CLARK | 2018-12-06 | 2019-08-02 | 2020-01-21 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4GT5KEE58222 |  | Yes |  |  | 11.22.2022
1FT7X2B65FEB36904 | 1971 | 3 | C727 | C813 | C727 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/ CAMPERSHELL 4X4 | 66097 | UNLEADED | CARSON CITY | 2014-07-09 | 2014-09-23 | 2015-02-26 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B62FEB55457 | 1972 | 3 | C721 | C813 | C721 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 82796 | UNLEADED | CLARK | 2014-07-09 | 2014-09-23 | 2015-04-23 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B64FEB55458 | 1973 | 3 | C720 | C017 | C720 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 96360 | E-85 | CLARK | 2014-07-09 | 2014-09-23 | 2015-02-02 |  |  | A | A |  | Location | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B60FEB55456 | 1974 | 3 | C727 | C017 | C727 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 105615 | UNLEADED | CARSON CITY | 2014-07-09 | 2014-09-23 | 2015-02-02 |  |  | A | A |  | Location | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B62FEB45661 | 1976 | 3 | C727 | C011 | C727 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 73111 | UNLEADED | CARSON CITY | 2014-07-01 | 2014-09-23 | 2015-04-14 |  |  | A | A |  | Structural Design | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCWGFCF8F1280889 | 1977 | 4 | C727 | C040 | C727 | 2015 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | 159457 | UNLEADED | CARSON CITY | 2015-01-28 | 2015-10-29 | 2015-12-08 |  |  | A | A |  | Construction Administration | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF7EKF56147 | 1978 | 5 | C727 | C017 | C727 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 118417 | UNLEADED | CARSON CITY | 2014-06-20 | 2014-09-23 | 2014-10-27 |  |  | A | A |  | Location | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HY4KEE58223 | 1979 | 11H | C723 | C327 | C723 | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | 35723 | UNLEADED | ELKO | 2018-12-06 | 2019-08-06 | 2020-01-28 |  |  | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FD0W4HY4KEE58223 | Yes-Pilot | Yes |  |  | 11.29.2022 | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1FDUF4HT9KEE58191 | 1981 | 11F | C722 | C028 | C722 | 2019 | FORD | F-450 | 2019 1 TON SERVICE TRUCK | 15473 | DIESEL | CARSON CITY | 2018-12-06 | 2019-09-27 | 2020-09-11 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTMF1CM5EKF62847 | 1982 | 5 | C726 | C920 | C726 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 66119 | UNLEADED | HUMBOLDT | 2014-06-20 | 2014-09-23 | 2014-11-24 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT2KEE58193 | 1984 | 11F | C721 | C145 | C721 | 2019 | FORD | F-450 | 2019 SERVICE TRUCK | 16859 | DIESEL | CLARK | 2018-12-06 | 2019-06-12 | 2019-09-24 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot |  | #N/A
2005R815 | 1997 | 55B | C724 | C094 | C724 | 2005 | TUCKER | 2000BXL265 | SNOW CAT | 410 | DIESEL | WHITE PINE | 2003-07-02 | 2004-11-30 | 2004-12-07 |  |  | A | A |  | Communications Ely | Ely | District 3 |  | No | OFF ROAD / NA | None- wired direct | [5 empty] | 6 WAY STRAIGHT BLADE | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A | Yes |  |  |  |  | 8/17/2022: In the internal discussion between Billie, Yesh and Priyanka it was decided that all the SnowCats should have Satellite
1FTMF1CM7EKF62848 | 2001 | 5 | C723 | C908 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 65824 | UNLEADED | ELKO | 2014-06-20 | 2014-09-23 | 2014-11-26 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM7EKF62848 |  |  |  |  | 11.28.2022
1FTFX1EF9EKF56148 | 2003 | 5 | C727 | C011 | C727 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 89274 | UNLEADED | CARSON CITY | 2014-06-20 | 2014-09-23 | 2015-04-21 |  |  | A | A |  | Structural Design | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFW1EF1EKF56146 | 2005 | 5 | C722 | C013 | C722 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 102818 | UNLEADED | CARSON CITY | 2014-06-20 | 2014-09-23 | 2014-10-27 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1EF0EKF56149 | 2006 | 5 | C722 | C013 | C722 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 78547 | UNLEADED | CARSON CITY | 2014-06-20 | 2014-09-23 | 2014-10-27 |  |  | A | A |  | Environmental Service | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV6LPLU1044 | 2007 | 13S | C721 | C153 | C721 | 2019 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | 2015 | DIESEL | CLARK | 2019-08-26 | 2019-12-12 | 2020-01-13 | EATON | FORCE AMERICA | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | FORCE AMERICA |  |  |  | FLAT RACK SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes |  |  |  | 12/6/2021: This is a Las Vegas Truck and we do not need Winter Operations on this vehicle
1NPTL70X9JD487194 | 2014 | 13 | C721 | C156 | C721 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 17718 | DIESEL | WASHOE | 2017-06-29 | 2018-01-12 | 2018-12-10 | DANFOSS | DANFOSS | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | ONE-WAY PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | [5 empty] | 12/6/2021: This is a Las Vegas Truck and we do not need Winter Operations on this vehicle
1FTMF1CMXEKF79465 | 2015 | 5 | C723 | C918 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 73607 | UNLEADED | ELKO | 2014-06-30 | 2014-09-23 | 2014-11-26 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CMXEKF79465 |  |  |  |  | 11.28.2022
1FTFX1EFXEKF79471 | 2016 | 5 | C721 | C018 | C721 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 65256 | E-85 | CLARK | 2014-06-30 | 2014-09-23 | 2015-01-05 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM7EKF79469 | 2017 | 5 | C723 | C912 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 128750 | UNLEADED | ELKO | 2014-06-30 | 2014-09-23 | 2014-11-26 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM7EKF79469 |  |  |  |  | 11.28.2022
1FTMF1CM8EKF79464 | 2018 | 5 | C723 | C912 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 70264 | UNLEADED | ELKO | 2014-06-30 | 2014-09-23 | 2015-01-05 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM8EKF79464 |  |  |  |  | 11.28.2022
1FTMF1CM3EKF79467 | 2019 | 5 | C724 | C914 | C724 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 57768 | UNLEADED | WHITE PINE | 2014-06-30 | 2014-09-23 | 2015-01-05 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM1EKF79466 | 2020 | 5 | C723 | C918 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 76475 | UNLEADED | ELKO | 2014-06-30 | 2014-09-23 | 2014-11-26 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM1EKF79466 |  |  |  |  | 11.28.2022
1FTMF1CM5EKF79468 | 2021 | 5 | C723 | C918 | C723 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 81017 | UNLEADED | ELKO | 2014-06-30 | 2014-09-23 | 2014-12-10 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTMF1CM5EKF79468 |  |  |  |  | 11.30.2022
1FTMF1CM6EKF79463 | 2023 | 5 | C722 | C907 | C722 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 47859 | UNLEADED | CARSON CITY | 2014-07-01 | 2014-09-23 | 2014-12-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1EM7EKF79470 | 2024 | 5 | C727 | C805 | C727 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | 60000 | UNLEADED | CARSON CITY | 2014-06-30 | 2014-09-23 | 2015-01-05 |  |  | A | A |  | Roadway Systems | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTMF1CM2EKF79461 | 2025 | 5 | C722 | C907 | C722 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 68041 | UNLEADED | CARSON CITY | 2014-06-30 | 2014-09-23 | 2014-12-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X1GD350999 | 2038 | 13 | C767 | C252 | C767 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 19603 | DIESEL | NYE | 2015-06-15 | 2015-12-02 | 2016-06-24 | PARKER IQUAN | PARKER IQUAN | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE 11FT REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1C4RJFAG3LC184789 | 2039 | 01A | C767 | C201 | C767 | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | 5161 | UNLEADED | WASHOE | 2019-09-09 | 2020-02-05 | 2020-04-20 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X8GD351003 | 2041 | 13 | C725 | C173 | C725 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 49456 | DIESEL | NYE | 2015-06-15 | 2015-12-02 | 2016-11-29 | PARKER IQUAN | PARKER IQUAN | A | A |  | Blue Jay Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | ONE WAY PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVACXDT8GHHK8984 | 2046 | 24 | C720 | C154 | C720 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 33183 | DIESEL | CLARK | 2015-04-09 | 2015-12-21 | 2016-02-02 |  | PARKER | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT8GHHK8984
1FVACXDT6GHHK8983 | 2052 | 24 | C720 | C154 | C720 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | 31520 | DIESEL | CLARK | 2015-04-09 | 2016-01-07 | 2016-02-08 |  | PARKER | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 |  |  | GO9 |  |  |  | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FVACXDT6GHHK8983
1C4RJFAGXLC184790 | 2054 | 01A | C767 | C201 | C767 | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | 5204 | UNLEADED | WASHOE | 2019-09-19 | 2020-02-05 | 2020-04-30 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KKHALDV0LPLX5856 | 2056 | 11B | C723 | C340 | C723 | 2019 | WESTERN ST | 4900SF | 2019 WESTERN STAR FLAT RACK | 5380 | DIESEL | ELKO | 2019-08-23 | 2020-07-28 | 2020-10-14 |  |  | A | A |  | Elko Striping Crew | Elko | District 3 |  | No | 6 | J1939 | [5 empty] | 2021 SCORPION ATTENUATOR,2021 LITEREADER ARROWBOARD | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KKHAEDV3LPLP2767 | 2058 | 13 | C725 | C176 | C725 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | 11805 | DIESEL | NYE | 2019-02-14 | 2019-12-26 | 2020-04-14 | METARIS | PRINCE | A | A |  | Mina Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV5LPLP2768 | 2059 | 13 | C725 | C170 | C725 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | 10320 | DIESEL | CLARK | 2019-02-14 | 2019-12-26 | 2020-04-15 | DANFOSS | DANFOSS | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV2LPLU1073 | 2060 | 13 | C728 | C283 | C728 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 6407 | DIESEL | CHURCHILL | 2019-02-14 | 2020-04-01 | 2020-11-05 | PARKER | DANFOSS | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV2LPLU1073
5KKHAEDV4LPLU1074 | 2062 | 13 | C767 | C225 | C767 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM DUMP TRUCK | 5398 | DIESEL | LYON | 2019-02-14 | 2020-03-24 | 2020-05-21 | METARIS | PRINCE | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV4LPLU1074 |  | Yes |  |  |  | 10/13/2022: Changed the Existing CIRUS/Parker IQAN… column to CIRUS
1FMSK8BB2LGB67595 | 2063 | 01A | C721 | C101 | C721 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 SUV | 3858 | E-85 | CLARK | 2019-09-09 | 2020-03-03 | 2020-04-20 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMSK8BB2LGB67595 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
5KKHAEDV5LPLP2771 | 2064 | 13 | C722 | C270 | C722 | 2019 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | 5751 | DIESEL | CARSON CITY | 2019-02-14 | 2020-03-31 | 2020-11-05 | DANFOSS | DANFOSS | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV5LPLP2771
5KKHAEDV7LPLP2772 | 2065 | 13 | C722 | C272 | C722 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 6258 | DIESEL | CARSON CITY | 2019-02-14 | 2020-04-14 | 2020-11-05 | DANFOSS | DANFOSS | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW,2020 ASPHALT HOTBOX | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV7LPLP2772
5KKHAEDV0LPLU1041 | 2067 | 13 | C767 | C253 | C767 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 7917 |  | 0 | 2019-02-14 | 2020-04-14 | 2020-06-24 | DANFOSS | DANFOSS | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS | GO9+ |  |  | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 5KKHAEDV0LPLU1041 |  | Yes
5KKHAEDV3LPLU1048 | 2068 | 13 | C723 | C324 | C723 | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | 22081 | DIESEL | ELKO | 2019-02-14 | 2019-12-06 | 2020-02-20 | DANFOSS | DANFOSS | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | PLOW,SANDER,2021 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1C4RJFAG3LC366248 | 2069 | 01A | C727 | C016 | C727 | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | 2684 | UNLEADED | CARSON CITY | 2020-03-10 | 2020-08-04 | 2020-09-03 |  |  | A | A |  | Traffic Operations | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BB4LGB67596 | 2070 | 01A | C727 | C017 | C727 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | 1001 | FLEX FUEL | CARSON CITY | 2019-09-09 | 2020-02-24 | 2020-06-01 |  |  | A | A |  | Location | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDV8LPLU1045 | 2071 | 13 | C724 | C382 | C724 | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | 8368 | DIESEL | ELKO | 2019-02-14 | 2020-03-26 | 2020-06-23 | DANFOSS | DANFOSS | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDVXLPLU1046 | 2072 | 13 | C726 | C373 | C726 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | 17443 | DIESEL | HUMBOLDT | 2019-02-14 | 2020-02-10 | 2020-04-09 |  |  | A | A |  | Quinn River Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
5KKHAEDV1LPLU1047 | 2073 | 13 | C726 | C371 | C726 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | 15399 | DIESEL | HUMBOLDT | 2019-02-14 | 2020-03-24 | 2020-04-14 | PARKER | DANFOSS | A | A |  | Battle Mountain Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | CIRUS |  |  |  | 2019 FLINK SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
3BKBHJ7X0LF416359 | 2074 | 11 | C767 | C251 | C767 | 2019 | KENWORTH | T440 | 2021 KENWORTH T400 | 737 | DIESEL | WASHOE | 2019-05-07 | 2020-04-21 | 2021-04-27 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTEX1C50LKE17013 | 2077 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 1698 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2020-10-20 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C56LKE17016 | 2078 | 5 | C721 | C721 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 1736 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2021-03-25 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C56LKE17016 |  |  |  |  | 11.22.2022
1FTEX1C59LKE17012 | 2079 | 5 | C721 | C101 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | 2199 | E-85 | CLARK | 2020-01-15 | 2020-04-28 | 2021-05-04 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C59LKE17012 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FTEX1C52LKE17014 | 2080 | 5 | C721 | C160 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 12279 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2020-12-17 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTEX1C52LKE17014 | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FTEX1C54LKE17015 | 2081 | 5 | C721 | C157 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 1935 | E-85 | CLARK | 2020-01-16 | 2020-04-28 | 2021-03-23 |  |  | A | A |  | Las Vegas Night Maintenance Crew 6 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C58LKE17017 | 2082 | 5 | C721 | C113 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 2509 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2021-03-16 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZT51F46F210081 | 2083 | 1 | C767 | C767 | C767 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 109200 | RFG | WASHOE | 2006-02-16 | 2006-02-22 | 2006-03-23 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1FT7X2BT4LED39543 | 2085 | 3 | C721 | C091 | C721 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 8709 | BIO DIESEL | CLARK | 2020-01-28 | 2020-04-28 | 2020-09-09 |  |  | A | A |  | Communications Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  | GO9 |  |  |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FT7X2BT4LED39543 | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
3ALAC4CY4GDHM1927 | 2087 | 11 | C722 | C247 | C722 | 2016 | FREIGHTLNR | M2 112 | HERBICIDE SPRAY TRUCK | 18639 | DIESEL | CARSON CITY | 2015-06-30 | 2015-11-05 | 2017-08-14 | EATON |  | A | A |  | Carson City Landscape Crew 3 | Carson City | District 2 |  | No | 5 | J1939 | [5 empty] | INJECTION SPRAYER | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W5GY7GEA66724 | 2088 | 11H | C767 | C242 | C767 | 2016 | FORD | F-550 | 1 1/2 TON FLATRACK TRUCK W/LIFTGATE | 71863 | UNLEADED | WASHOE | 2015-04-17 | 2015-11-09 | 2016-08-19 |  |  | A | A |  | Reno Pavement Markings | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTEX1C5XLKE17018 | 2090 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 9 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2020-12-25 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X5HY9GEA66705 | 2091 | 11C | C767 | C225 | C767 | 2016 | FORD | F-550 | LUBE TRUCK 4X4 | 74322 | UNLEADED | LYON | 2015-04-16 | 2015-10-07 | 2015-12-07 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FT7W2BTXLED69682 | 2092 | 3 | C728 | C283 | C767 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 0 | DIESEL | WASHOE | 2020-02-28 | 2020-07-30 | 2021-09-27 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E52LKE48148 | 2093 | 5 | C728 | C201 | C728 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 5246 | FLEX FUEL | LYON | 2020-03-10 | 2020-06-25 | 2021-05-25 |  |  | A | A |  | Reno District Administration | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2BT3LED69684 | 2094 | 3 | C767 | C234 | C767 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 7727 | FLEX FUEL | WASHOE | 2020-02-28 | 2020-07-30 | 2021-02-18 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FT7W2BT1LED69683 | 2095 | 3 | C722 | C271 | C722 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 8079 | FLEX FUEL | CARSON CITY | 2020-02-28 | 2020-07-30 | 2022-08-04 |  |  |  | A | New - Nov 2022 | Carson City Maintenance Crew 2 | Carson City | District 2 |  |  | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B68LED79119 | 2096 | 3 | C767 | C241 | C767 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 8871 | FLEX FUEL | WASHOE | 2020-03-02 | 2020-07-24 | 2022-01-03 |  |  |  | A | New - Nov 2022 | Reno Striping Crew 2 | Reno | District 2 |  |  | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FT7W2B64LED79120 | 2097 | 3 | C722 | C272 | C722 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 3129 | FLEX FUEL | WASHOE | 2020-03-02 | 2020-07-30 | 2021-05-19 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E54LKE48149 | 2099 | 5 | C767 | C242 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 5277 | FLEX FUEL | WASHOE | 2020-03-10 | 2020-06-25 | 2021-06-02 |  |  | A | A |  | Reno Pavement Markings | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMEU73E17UA88730 | 2102 | 01A | C724 | C307 | C724 | 2007 | FORD | EXPLORER | SUV 4X4 | 138404 | UNLEADED | WHITE PINE | 2006-07-01 | 2007-01-31 | 2007-03-25 |  |  | A | A |  | Ely District Administration | Ely | District 3 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2103 | 25 | C721 | C122 | #N/A | 1987 | INTL | F2574 | TANDEM AXLE WATER TRUCK | 155304 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Alamo Maintenance Crew | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Deleted |  | #N/A
1FT7WZBT5LED69685 | 2104 | 3 | C767 | C253 | C767 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 10316 | FLEX FUEL | WASHOE | 2020-02-28 | 2020-07-28 | 2020-12-09 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FMEU73E37UA88731 | 2106 | 01A | C767 | C767 | C767 | 2007 | FORD | EXPLORER | SUV 4X4 | 104714 | UNLEADED | CARSON CITY | 2006-07-01 | 2007-01-31 | 2007-03-29 |  |  | A | A |  | Equipment Shop | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMEU73E57UA88732 | 2107 | 01A | C725 | C767 | C725 | 2007 | FORD | EXPLORER | SUV 4X4 | 161258 | RFG | WASHOE | 2006-07-01 | 2007-01-31 | 2007-08-31 |  |  | D | A |  | Equipment Shop | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E50LKE48147 | 2110 | 5 | C724 | C307 | C724 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 5730 | FLEX FUEL | ELKO | 2020-03-10 | 2020-06-25 | 2021-03-17 |  |  | A | A |  | Ely District Administration | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMEU73E77UA88733 | 2115 | 01A | C767 | C241 | C767 | 2007 | FORD | EXPLORER | SUV 4X4 | 145901 | RFG | WASHOE | 2006-07-01 | 2007-01-31 | 2007-05-04 |  |  | A | A |  | Reno Striping Crew 2 | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2BT8LED69681 | 2116 | 3 | C725 | C104 | C725 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 2264 | DIESEL | NYE | 2020-03-02 | 2020-07-24 | 2021-04-28 |  |  | A | A |  | Tonopah Administration | Tonopah | District 1 | 3/4 Ton Pickups | Yes | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E50LKE48150 | 2117 | 5 | C726 | C726 | C726 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 2855 | FLEX FUEL | ELKO | 2020-03-10 | 2020-06-25 | 2021-02-04 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C55LKE26161 | 2118 | 5 | C721 | C031 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 1107 | E-85 | CLARK | 2020-01-30 | 2020-04-21 | 2021-01-19 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C55LKE26161 |  |  |  |  | 11.22.2022
1FTEX1C52LKE26148 | 2119 | 5 | C721 | C031 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 1837 | E-85 | CLARK | 2020-01-30 | 2020-04-28 | 2020-08-31 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C52LKE26148
1FTEX1C53LKE26160 | 2120 | 5 | C721 | C031 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 4421 | E-85 | CLARK | 2020-01-30 | 2020-04-28 | 2021-01-19 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C53LKE26160 |  |  | 11.21.2022 |  | 11.22.2022
1G1ZS57F57F169634 | 2121 | 1 | C721 | C721 | C721 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 45447 | UNLEADED | CLARK | 2006-07-01 | 2006-11-29 | 2006-12-12 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1G1ZS57F57F169634
1FTEX1C54LKE26149 | 2122 | 5 | C721 | C901 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 6057 | FLEX FUEL | CLARK | 2020-01-30 | 2020-04-14 | 2020-10-12 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P07EB44398 | 2123 | 3 | C721 | C158 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 232594 | BIO DIESEL | CLARK | 2006-09-28 | 2007-01-23 | 2007-05-03 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C55LKE26158 | 2124 | 5 | C721 | C906 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 5838 | E-85 | CLARK | 2020-01-30 | 2020-04-21 | 2020-10-05 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P27EB44399 | 2128 | 3 | C721 | C122 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 178263 | DIESEL | LINCOLN | 2006-07-01 | 2006-12-27 | 2007-02-14 |  |  | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTSW21P27EB44399 | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FTSW21P57EB44400 | 2131 | 3 | C721 | C154 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 150413 | BIO DIESEL | CLARK | 2006-07-01 | 2006-12-27 | 2007-01-17 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New |  | #N/A | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1G1ZS57F07F168990 | 2132 | 1 | C767 | C767 | C767 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 115120 | RFG | WASHOE | 2006-07-01 | 2006-11-29 | 2006-12-12 |  |  | A | A |  | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1FTEX1C59LKE26079 | 2135 | 5 | C721 | C906 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 9605 | E-85 | CLARK | 2020-01-30 | 2020-04-28 | 2021-01-19 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C54LKE26152 | 2136 | 5 | C721 | C901 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 2121 | E-85 | CLARK | 2020-01-30 | 2020-04-28 | 2021-01-19 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C52LKE26151 | 2137 | 5 | C721 | C902 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 11692 | FLEX FUEL | CLARK | 2020-01-30 | 2020-04-28 | 2020-11-05 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P77EB44401 | 2138 | 3 | C721 | C124 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 372079 | BIO DIESEL | CLARK | 2006-07-01 | 2006-12-27 | 2007-02-14 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P97EB44402 | 2139 | 3 | C725 | C170 | C725 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 167245 | DIESEL | NYE | 2006-07-01 | 2006-12-27 | 2007-02-13 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 | 3/4 Ton Pickups | Yes | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P07EB44403 | 2140 | 3 | C721 | C101 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 121873 | BIO DIESEL | CLARK | 2006-07-01 | 2006-12-27 | 2007-02-13 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSW21P07EB44403
1FTEX1C56LKE26153 | 2141 | 5 | C721 | C915 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 20 | E-85 | CLARK | 2020-01-30 | 2020-04-28 | 2021-01-19 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C50LKE26150 | 2142 | 5 | C721 | C915 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 4220 | FLEX FUEL | CLARK | 2020-01-30 | 2020-06-18 | 2020-10-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P27EB44404 | 2151 | 3 | C721 | C129 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 264507 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-02 | 2007-02-14 |  |  | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | Yes | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTSW21P27EB44404 |  |  |  |  | 11.23.2022 | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FTSW21P47EB44405 | 2152 | 3 | C721 | C160 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 175857 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-02 | 2007-01-17 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2153 | 3 | C728 | C283 | #N/A | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 326989 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Lovelock Maintenance Crew | Fallon | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
1FTEX1C57LKE26159 | 2154 | 5 | C721 | C915 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 2310 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2020-12-01 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0X4HT5GEA73245 | 2155 | 11E | C722 | C271 | C722 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | 114095 | DIESEL | CARSON CITY | 2015-04-29 | 2015-10-07 | 2016-06-09 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD0X4HY2GEA73246 | 2156 | 11E | C728 | C281 | C728 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | 118325 | UNLEADED | CHURCHILL | 2015-04-29 | 2015-10-07 | 2016-05-13 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTEX1C50LKE26147 | 2157 | 5 | C721 | C903 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 3114 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2020-11-16 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C59LKE26146 | 2158 | 5 | C721 | C903 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 8635 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2020-11-10 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSX21P17EB44388 | 2159 | 3 | C722 | C722 | C722 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 201935 | DIESEL | CARSON CITY | 2006-07-01 | 2007-01-02 | 2007-03-22 |  |  | A | A |  | Carson City District Repair Shop | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDBF3F69FED69628 | 2160 | 11F | C767 | C255 | C767 | 2015 | FORD | F-350 | SERVICE TRUCK 4X4 | 29146 | RFG | WASHOE | 2015-02-26 | 2015-03-27 | 2015-08-19 |  |  | A | A |  | Reno Bridge Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1NPTL70XXGD351004 | 2162 | 13 | C725 | C171 | C725 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 49256 | DIESEL | NYE | 2015-06-15 | 2015-12-02 | 2016-11-02 | PARKER | PARKER | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SNOW PLOW,SANDER W/PREWET SYSTEM | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X1GD351005 | 2163 | 13 | C767 | C252 | C767 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 49571 | DIESEL | WASHOE | 2015-06-15 | 2015-12-02 | 2016-11-02 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | REVERSIBLE PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
#N/A | 2164 | 15 | C767 | C767 | #N/A | 1988 | INTL | F5070 | AWD 6X6 DUMP TRUCK | 135674 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 6 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,PLOW WING,1988 SANDER | Telematics Device |  |  | Plow Up Down Sensor Wing Up Down Sensor |  | Yes | Yes |  |  |  | #N/A
1FTSX21548EA79827 | 2165 | 3 | C722 | C028 | C722 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 144623 | UNLEADED | CARSON CITY | 2006-09-28 | 2007-04-23 | 2007-07-31 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSX21P37EB44408 | 2166 | 3 | C767 | C905 | C767 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 169210 | BIO DIESEL | WASHOE | 2006-07-01 | 2007-01-05 | 2007-01-09 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTNF21588EA79829 | 2167 | 3 | C723 | C723 | C723 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 228794 | UNLEADED | ELKO | 2006-09-28 | 2007-05-01 | 2007-05-31 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTNF21588EA79829 |  |  |  |  | 11.29.2022 | 12/2/2022: highlighted in red because there are some discrepancies in the Device vs License Plate based on the installation history report downloaded from Gov5 server. Need to verify with GofFleet.
1FTSX21PX7EB44406 | 2168 | 3 | C767 | C032 | C767 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | 172716 | BIO DIESEL | WASHOE | 2006-07-01 | 2007-01-05 | 2007-04-11 |  |  | A | A |  | Right of Way Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A | [5 empty] | 12/2/2022: highlighted in red because there are some discrepancies in the Device vs License Plate based on the installation history report downloaded from Gov5 server. Need to verify with GofFleet.
1FTSF20P77EB44397 | 2170 | 3 | C721 | C031 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 149113 | BIO DIESEL | CLARK | 2006-07-01 | 2007-02-07 | 2007-04-04 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSF20P77EB44397 |  |  | 11.21.2022 |  | 11.22.2022
1FDYK90L4JVA43560 | 2172 | 28 | C721 | C130 | C721 | 1988 | FORD | 9000 | OIL DISTRIBUTOR | 25933 | DIESEL | CLARK | 1988-07-29 | 1988-07-29 | 1988-07-29 |  |  | A | A |  | South Las Vegas Yard and Stockpile Control | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GCNCPEH4FZ276366 | 2173 | 5 | C724 | C307 | C724 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 43664 | UNLEADED | WHITE PINE | 2015-01-28 | 2015-04-01 | 2015-05-20 |  |  | A | A |  | Ely District Administration | Ely | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C5XLKE26155 | 2175 | 5 | C721 | C902 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 532 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2021-02-01 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20R88EB25974 | 2179 | 3 | C767 | C910 | C767 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 125213 | BIO DIESEL | WASHOE | 2006-07-01 | 2007-06-08 | 2007-09-21 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P37EB44395 | 2180 | 3 | C721 | C901 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 159134 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-05 | 2007-02-14 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4GY2GEA04532 | 2181 | 11E | C724 | C381 | C724 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 128928 | UNLEADED | WHITE PINE | 2015-09-04 | 2015-09-14 | 2015-10-20 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GTEC14W3WZ533742 | 2183 | 5 | C727 | C027 | C767 | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | 173159 | UNLEADED | CARSON CITY | 1998-03-26 | 1998-05-08 | 1998-05-08 |  |  | A | D |  | Materials Bituminous | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C58LKE26154 | 2189 | 5 | C721 | C914 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 2783 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2020-12-02 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C53LKE26157 | 2193 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 511 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2021-03-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDUF4GY0GEA04531 | 2196 | 11E | C724 | C380 | C724 | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | 126390 | UNLEADED | WHITE PINE | 2015-01-14 | 2015-04-02 | 2015-10-20 |  |  | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTEW1C59LKD81471 | 2198 | 5 | C721 | C155 | C721 | 2020 | FORD | F-150 | 2020 F-150 1/2 TON PICK UP TRUCK | 5352 | E-85 | CLARK | 2019-10-17 | 2020-03-04 | 2021-02-03 |  |  | A | A |  | Las Vegas Bridge Maintenance | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E58LKD58519 | 2201 | 5 | C721 | C101 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 3062 | FLEX FUEL | WASHOE | 2019-10-17 | 2020-02-24 | 2021-02-24 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFX1E58LKD58519
1FTEX1C51LKE26156 | 2203 | 5 | C721 | C914 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 8954 | E-85 | CLARK | 2020-01-30 | 2020-06-23 | 2021-02-03 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E56LKE17020 | 2204 | 5 | C721 | C152 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 5668 | E-85 | CLARK | 2020-01-15 | 2020-06-23 | 2021-04-08 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFX1E56LKE17020 |  |  |  |  | 11.22.2022
1FTFX1E5XLKE17019 | 2205 | 5 | C721 | C101 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 1673 | E-85 | CLARK | 2020-01-15 | 2020-07-30 | 2021-04-07 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFX1E5XLKE17019 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FTEW1C58LKE16999 | 2206 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 7701 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2020-11-18 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C52LKE17002 | 2207 | 5 | C721 | C102 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | 7648 | E-85 | CLARK | 2020-01-16 | 2020-04-28 | 2020-10-05 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTEW1C52LKE17002 | [5 empty] | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1HTSDZ3N8LH207723 | 2209 | 11C | C728 | C281 | C728 | 1990 | INTL | 4900 | LUBE TRUCK | 148914 | DIESEL | CHURCHILL | 1989-05-31 | 1989-05-31 | 1989-05-31 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPTL70X3GD351006 | 2210 | 13 | C724 | C380 | C724 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 70927 | DIESEL | WHITE PINE | 2015-06-15 | 2015-12-02 | 2016-11-02 | PARKER IQUAN | PARKER IQUAN | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | REVERSIBLE PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C50LKE17001 | 2215 | 5 | C721 | C916 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 2180 | E-85 | CLARK | 2020-01-16 | 2020-04-28 | 2020-09-16 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X5GD351007 | 2219 | 13 | C724 | C381 | C724 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 95350 | DIESEL | WHITE PINE | 2015-06-15 | 2015-12-02 | 2016-12-16 | PARKER IQUAN | PARKER IQUAN | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | ONE WAY PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTL70X7GD351008 | 2220 | 13 | C724 | C382 | C724 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 89054 | DIESEL | WHITE PINE | 2015-06-15 | 2015-12-02 | 2016-12-02 | PARKER IQUAN | PARKER IQUAN | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C56LKE16998 | 2221 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 4888 | FLEX FUEL | CLARK | 2020-01-16 | 2020-06-18 | 2020-09-23 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C56LKE17004 | 2222 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 8590 | E-85 | CLARK | 2020-01-16 | 2020-04-29 | 2020-08-26 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C54LKE16997 | 2228 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 3758 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2020-09-17 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXW46R58EB77566 | 2231 | 11J | C728 | C280 | C728 | 2008 | FORD | F-450 | UTILITY TRUCK | 248736 | DIESEL | CHURCHILL | 2006-07-07 | 2007-09-19 | 2008-02-25 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXW47R68EC14770 | 2232 | 11H | C726 | C374 | C726 | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | 212813 | DIESEL | HUMBOLDT | 2006-07-27 | 2007-11-07 | 2007-12-19 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FADP3R42FL348870 | 2234 | 1 | C721 | C721 | C721 | 2015 | FORD | FOCUS | ELECTRIC SEDAN | 7572 | ELECTRIC | CLARK | 2015-02-27 | 2015-04-02 | 2015-09-10 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot |  | #N/A
#N/A | 2235 | 11H | C767 | C767 | #N/A | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | 227579 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FADP3R46FL348869 | 2237 | 1 | C721 | C721 | C721 | 2015 | FORD | FOCUS | ELECTRIC SEDAN | 10886 | ELECTRIC | CLARK | 2015-02-27 | 2015-04-02 | 2015-09-10 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot |  | #N/A
#N/A | 2238 | 11E | C720 | C127 | #N/A | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 208995 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Deleted |  | #N/A
1FDXF46R88EB68246 | 2239 | 11E | C721 | C122 | C721 | 2008 | FORD | F-450 | DUMP TRUCK | 245301 | DIESEL | LINCOLN | 2007-07-27 | 2007-08-29 | 2007-09-13 |  |  | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46RX8EB68247 | 2240 | 11E | C721 | C158 | C721 | 2008 | FORD | F-450 | DUMP TRUCK | 197438 | DIESEL | CLARK | 2006-07-26 | 2007-08-23 | 2007-09-20 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FM5K8B83FGC16695 | 2241 | 01A | C727 | C805 | C727 | 2015 | FORD | EXPLORER | AWD SUV | 78502 | UNLEADED | CARSON CITY | 2015-01-12 | 2015-04-03 | 2015-09-16 |  |  | A | A |  | Roadway Systems | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1C54LKE17003 | 2242 | 5 | C721 | C902 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 3037 | E-85 | CLARK | 2020-01-16 | 2020-04-21 | 2020-10-08 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF47P47EB12185 | 2243 | 11E | C721 | C178 | C721 | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | 229119 | DIESEL | LINCOLN | 2007-03-26 | 2007-04-04 | 2007-05-10 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor |  |  |  |  | HINKER C- PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 2244 | 11H | C725 | C170 | #N/A | 2008 | FORD | F-450 | 1 TON FLATRACK TRUCK 4X4 | 206201 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor |  |  |  |  | MESSAGE BOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FT7X2A64GEA50812 | 2245 | 3 | C722 | C911 | C722 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 50832 | UNLEADED | CARSON CITY | 2015-04-29 | 2015-09-14 | 2015-11-16 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B69FEC99166 | 2246 | 3 | C727 | C813 | C727 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 91653 | UNLEADED | CARSON CITY | 2015-01-28 | 2015-03-27 | 2015-08-19 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46R88EC60411 | 2247 | 11E | C721 | C145 | C721 | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | 142405 | BIO DIESEL | CLARK | 2006-07-27 | 2007-12-06 | 2008-02-06 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDXF46R88EC60411 |  |  |  |  | 11.22.2022
1FTEW1C59LKE17000 | 2248 | 5 | C721 | C922 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | 1078 | E-85 | CLARK | 2020-01-16 | 2020-09-28 | 2020-09-28 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDAF57R98EA55755 | 2249 | 11F | C722 | C722 | C722 | 2008 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE | 128475 | DIESEL | CARSON CITY | 2006-07-27 | 2007-09-26 | 2007-10-02 |  |  | A | A |  | Carson City District Repair Shop | Carson City | District 2 |  | No | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH8FZ272403 | 2251 | 5 | C723 | C713 | C723 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 37793 | UNLEADED | ELKO | 2015-01-28 | 2015-04-03 | 2015-05-05 |  |  | A | A |  | Elko District Stockroom | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCPEH8FZ272403 |  |  |  |  | 11.29.2022
1FT7W2B62LED39540 | 2252 | 3 | C721 | C922 | C721 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 8262 | E-85 | CLARK | 2020-01-16 | 2020-06-25 | 2020-11-18 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
#N/A | 2253 | 11J | C725 | C105 | #N/A | 2008 | FORD | F-450 | UTILITY TRUCK | 195867 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Tonopah Service Crew | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FDSF35R28EC60409 | 2254 | 11J | C726 | C305 | C726 | 2008 | FORD | F-350 | UTILITY TRUCK | 219842 | DIESEL | HUMBOLDT | 2007-07-01 | 2007-12-05 | 2008-01-22 |  |  | A | A |  | Winnemucca Service Crew | Winnemucca | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2255 | 11F | C722 | C028 | #N/A | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | 202175 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Materials Geotechnical | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1FDXX47R18EC14771 | 2256 | 11F | C725 | C725 | C725 | 2008 | FORD | F-450 | 1 TON SERVICE TRUCK 4X4 | 137699 | DIESEL | NYE | 2007-07-27 | 2007-12-19 | 2008-01-17 |  |  | A | A |  | Tonopah District Repair Shop | Tonopah | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKAAEDE18PZ22282 | 2257 | 12 | C721 | C178 | C721 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | 100713 | DIESEL | LINCOLN | 2006-08-17 | 2007-11-26 | 2008-12-03 |  |  | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FT7W2B66LED39539 | 2258 | 3 | C721 | C142 | C721 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 10992 | E-85 | CLARK | 2020-01-16 | 2020-10-09 | 2020-10-14 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7W2B66LED39539 |  | Yes
1FTEW1E59LKE17009 | 2259 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 13861 | FLEX FUEL | WASHOE | 2020-01-15 | 2020-06-23 | 2020-10-29 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GCNCPEH8FZ273499 | 2260 | 5 | C721 | C813 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK W/CAMPERSHELL | 44634 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-09-24 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTSDNHNXLH284448 | 2261 | 11C | C724 | C319 | C724 | 1990 | INTL | 4900 | LUBE TRUCK | 174149 | DIESEL | WHITE PINE | 1990-03-26 | 1990-06-18 | 1990-06-18 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KKAAEDE58PZ22284 | 2262 | 12 | C767 | C231 | C767 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | 104205 | DIESEL | WASHOE | 2006-10-24 | 2007-10-25 | 2008-11-05 |  |  | A | A |  | Nixon Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SKID MOUNTED STAINLESS WATER TANK 1200,SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A |  | Yes
5KKAAEDE38PZ22283 | 2263 | 12 | C728 | C282 | C728 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | 80776 | DIESEL | CHURCHILL | 2006-10-18 | 2007-11-02 | 2008-11-06 |  |  | A | A |  | Cold Springs Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY,REVERSIBLE PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E55LKE17010 | 2264 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 2716 | FLEX FUEL | WASHOE | 2020-01-15 | 2020-07-24 | 2021-01-06 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes | 2013 LIGHT READER 1230 F-4 | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTSCNEMXLH284447 | 2265 | 11 | C720 | C150 | C720 | 1990 | INTL | 4700 | T/M WEED SPRAYER | 43333 | DIESEL | CLARK | 1990-05-09 | 1990-05-09 | 1990-05-09 |  |  | A | A |  | Las Vegas Maintenance Crew 1 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTSCNEM8LH284446 | 2266 | 11 | C767 | C245 | C767 | 1990 | INTL | 4700 | INTL TRUCK W/WEED SPRAYER | 87535 | DIESEL | WASHOE | 1990-05-14 | 1990-05-14 | 1990-05-14 |  |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTSDNHN1LH284449 | 2267 | 11C | C721 | C124 | C721 | 1990 | INTL | 4900 | LUBE TRUCK | 193827 | DIESEL | CLARK | 1990-03-26 | 1990-03-26 | 1990-03-26 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
5KKAAEDE78PZ22285 | 2268 | 12 | C722 | C235 | C722 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | 98155 | DIESEL | LYON | 2006-10-18 | 2007-11-02 | 2008-11-06 |  |  | A | A |  | Wellington Maintenance Crew | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW ONE WAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPALU0X87D739600 | 2269 | 13 | C723 | C335 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 127733 | DIESEL | ELKO | 2006-07-01 | 2007-02-12 | 2008-08-11 |  |  | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW REVERSIBLE,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE07PW80890 | 2270 | 13 | C725 | C170 | C725 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | 167121 | DIESEL | NYE | 2006-07-01 | 2006-10-05 | 2006-12-06 | PARKER | PARKER | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW ONE WAY,SANDER 8 YARD,2012 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPALU0X17D739597 | 2271 | 13 | C723 | C331 | C723 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 206586 | DIESEL | ELKO | 2006-07-01 | 2007-02-15 | 2008-08-18 |  |  | A | A |  | Ruby Valley Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1989 SANDER HOPPER-TYPE 8 CU YD,PLOW REVERSIBLE | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes
1NPAL09XX7D659176 | 2272 | 13 | C767 | C252 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 148161 | DIESEL | WASHOE | 2006-07-01 | 2006-12-12 | 2006-12-12 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1GCNCPEH2FZ275944 | 2273 | 5 | C767 | C910 | C767 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 52523 | RFG | WASHOE | 2015-01-28 | 2015-04-03 | 2015-05-20 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X17D659177 | 2274 | 13 | C767 | C250 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 152754 | DIESEL | WASHOE | 2006-07-01 | 2007-02-12 | 2007-03-09 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | VARITECH 1750 GALLON TANK,SANDER 8 YARD,HEAVY DUTY WING PLOW,ONE WAY PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1NPAL09X37D659178 | 2275 | 13 | C722 | C270 | C722 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 166591 | DIESEL | CARSON CITY | 2006-07-01 | 2006-12-06 | 2006-12-12 | PARKER | PARKER | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X57D659179 | 2276 | 13 | C767 | C231 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 259438 | DIESEL | WASHOE | 2006-07-01 | 2006-12-01 | 2006-12-12 | PARKER | PARKER | A | A |  | Nixon Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | VARITECH BRINE DISTRIBUTION TANK,PLOW REVERSIBLE,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE47PW80889 | 2277 | 13S | C721 | C153 | C721 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 102978 | DIESEL | CLARK | 2006-07-01 | 2006-10-09 | 2006-12-11 | PARKER | PARKER | A | A |  | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | DUMP BODY SWAP-LOADER,WATER TANK WRKMAN SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
INPAL09X17D659180 | 2278 | 13 | C728 | C283 | C728 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 220645 | DIESEL | PERSHING | 2006-07-01 | 2007-03-27 | 2007-05-01 | PARKER | PARKER | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE27PW80891 | 2279 | 13 | C726 | C370 | C726 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | 111202 | DIESEL | HUMBOLDT | 2006-07-01 | 2006-10-24 | 2006-12-05 | PARKER | PARKER | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
5KKHAEDE47PW80892 | 2280 | 13 | C726 | C370 | C726 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | 111769 | DIESEL | HUMBOLDT | 2006-07-01 | 2006-11-20 | 2006-12-21 | PARKER | PARKER | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E53LKE17006 | 2281 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 1882 | FLEX FUEL | WASHOE | 2020-01-15 | 2020-07-30 | 2020-09-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes |  |  |  | 8/17/2022: In an internal discussion between Billie, Yesh, and Priyanka it was decided that we should opt dual share services for two vehicles with latest year per vehicle class from each district.
5KKHAEDE27PW80888 | 2282 | 13 | C721 | C122 | C721 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | 153095 | DIESEL | LINCOLN | 2006-07-01 | 2006-09-29 | 2006-10-31 | PARKER | PARKER | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SANDER 8 YARD,REVERSABLE,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH4FZ274620 | 2283 | 5 | C726 | C920 | C726 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 63349 | UNLEADED | HUMBOLDT | 2015-01-28 | 2015-04-03 | 2015-05-20 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPALU0X37D739598 | 2284 | 13 | C724 | C380 | C724 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 143644 | DIESEL | WHITE PINE | 2006-07-01 | 2007-03-05 | 2008-08-13 |  |  | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 8 CUBIC YARDS,PLOW ALASKAN EXPRESSWAY | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH1FZ275482 | 2285 | 5 | C723 | C918 | C723 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 38723 | UNLEADED | ELKO | 2015-01-28 | 2015-04-03 | 2015-07-15 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCPEH1FZ275482 |  |  |  |  | 11.29.2022
1HTGEGBR1MH283913 | 2286 | 12 | C767 | C251 | C767 | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 168895 | DIESEL | WASHOE | 1990-06-22 | 1990-06-22 | 1990-06-22 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER 5 CUBIC YARDS,PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH2FZ277581 | 2287 | 5 | C721 | C906 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 64978 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-05-05 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E55LKE17007 | 2288 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 2117 | FLEX FUEL | WASHOE | 2020-01-15 | 2020-07-28 | 2020-09-17 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEGBRXMH283912 | 2289 | 12 | C726 | C372 | C726 | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 217810 | DIESEL | HUMBOLDT | 1990-06-22 | 1990-11-28 | 1990-11-28 |  |  | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW REVERSIBLE,5 CUBIC YARD SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPALU0X57D739599 | 2290 | 13 | C724 | C380 | C724 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 206318 | DIESEL | WHITE PINE | 2006-07-01 | 2007-01-18 | 2008-08-20 |  |  | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW ONE WAY,SANDER 8 CUBIC YARDS | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGDR3MH285153 | 2291 | 25 | C723 | C327 | C723 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE WATER TRUCK | 9303 | DIESEL | ELKO | 1990-08-14 | 1990-12-12 | 2017-07-06 |  |  | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot | Yes |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1HTGGGDR7MH285155 | 2292 | 13 | C723 | C327 | C723 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 105445 | DIESEL | ELKO | 1990-08-20 | 1990-12-31 | 2011-03-03 | PARKER 13 IQUAN | PARKER | A | A |  | North Fork Maintenance Crew | Elko | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | JENSEN REVERSIBLE,8 CU YD | Telematics device for Winter Operations | Yes |  |  | Yes | Yes | Yes |  | Full Project |  | #N/A | Yes-Pilot |  |  |  |  | 8/17/2022: In a quick call between Billie and Priyanka, Billie recommended to install satellities for vehicles falling in crew 327 since the coverage is really bad.
1HTGGGDR9MH285156 | 2293 | 25 | C724 | C384 | C724 | 1991 | INTL | F2574 | WATER TRUCK | 253608 | DIESEL | WHITE PINE | 1990-07-23 | 1990-11-28 | 1990-11-28 |  |  | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
IFTEW1E57LKE17008 | 2294 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 5528 | FLEX FUEL | WASHOE | 2020-01-15 | 2020-07-28 | 2020-09-15 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEW1E57LKE17011 | 2295 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 2716 | FLEX FUEL | WASHOE | 2020-01-15 | 2020-07-30 | 2020-12-08 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E55LKE17022 | 2297 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 3187 | FLEX FUEL | WASHOE | 2020-01-16 | 2020-06-23 | 2020-10-23 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH2FZ275877 | 2298 | 5 | C721 | C903 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 57014 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-05-05 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E57LKE17023 | 2299 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 9407 | FLEX FUEL | WASHOE | 2020-01-16 | 2020-06-23 | 2020-11-23 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH9FZ272300 | 2300 | 5 | C726 | C920 | C726 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 64401 | UNLEADED | HUMBOLDT | 2015-01-28 | 2015-04-03 | 2015-07-15 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1E53LKE17021 | 2301 | 5 | C767 | C913 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | 1425 | FLEX FUEL | WASHOE | 2020-01-16 | 2020-07-30 | 2020-12-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B64LED39541 | 2302 | 3 | C767 | C913 | C767 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 4100 | E-85 | WASHOE | 2020-01-29 | 2020-06-23 | 2020-09-10 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2303 | 3 | C767 | C767 | #N/A | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 281315 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  |  |  | #N/A
1XPFD49X67N744820 | 2304 | 14 | C720 | C156 | C720 | 2007 | PETERBILT | 378 | TRACTOR TRUCK W/MANUAL TRANS | 122246 | DIESEL | CLARK | 2006-07-01 | 2007-04-25 | 2007-05-15 | MUNCIE |  | A | A |  | Las Vegas Maintenance Crew 7 | Las Vegas | District 1 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1XPFD49XX7N744819 | 2305 | 14 | C721 | C122 | C721 | 2007 | PETERBILT | 378 | TRUCK TRACTOR W/MANUAL TRANS | 200880 | DIESEL | LINCOLN | 2006-07-01 | 2007-04-19 | 2007-05-17 | MUNCIE |  | A | A |  | Alamo Maintenance Crew | Las Vegas | District 1 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1NPAM40X07D744822 | 2306 | 15 | C722 | C227 | C722 | 2007 | PETERBILT | 357 | AWD TRUCK W/EPOKE SANDER | 131533 | DIESEL | DOUGLAS | 2006-07-01 | 2007-06-07 | 2007-11-05 | PARKER |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | EPOKE |  |  |  | PLOW SLOTTED TRIP,PLOW ONE WAY,JENSEN 12 FT ONE-WAY PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH1FZ277149 | 2307 | 5 | C722 | C911 | C722 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 67235 | RFG | CARSON CITY | 2015-01-28 | 2015-04-03 | 2015-07-02 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDOX4GT3LEC50919 | 2308 | 11E | C721 | C155 | C721 | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | 12504 | BIO DIESEL | CLARK | 2019-04-18 | 2020-08-04 | 2020-08-04 |  |  | A | A |  | Las Vegas Bridge Maintenance | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1C4RJFAG1LC184791 | 2310 | 01A | C767 | C201 | C767 | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | 3428 | UNLEADED | WASHOE | 2019-09-19 | 2020-02-05 | 2020-05-04 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGGGDR2LH283909 | 2314 | 25 | C724 | C319 | C724 | 1990 | INTL | 2574 | TANDEM AXLE WATER TRUCK | 191998 | DIESEL | WHITE PINE | 1990-06-08 | 1990-08-13 | 1990-08-13 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1M2K175C7LM003696 | 2315 | 28 | C723 | C350 | C723 | 1990 | MACK | MR690 | MAINTENANCE DISTRIBUTOR | 90663 | DIESEL | ELKO | 1990-06-06 | 1990-06-06 | 1990-06-06 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTGEGBR9LH283916 | 2316 | 28 | C724 | C319 | C724 | 1990 | INTL | 2574 | OIL DISTRIBUTOR | 64555 | DIESEL | WHITE PINE | 1990-03-27 | 1990-03-27 | 1990-03-27 |  |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FMSK8BB5LGB76579 | 2317 | 01A | C767 | C201 | C767 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | 1906 | FLEX FUEL | WASHOE | 2019-09-09 | 2020-02-24 | 2020-06-01 |  |  | A | A |  | Reno District Administration | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH3FZ274110 | 2318 | 5 | C721 | C916 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 74645 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-05-28 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGCUR5MH367751 | 2319 | 25 | C726 | C374 | C726 | 1991 | INTL | F2574 | TANDEM AXLE WATER TRUCK | 151684 | DIESEL | HUMBOLDT | 1991-06-10 | 1991-10-07 | 1991-10-07 |  |  | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAYR5MH367558 | 2331 | 28 | C728 | C280 | C728 | 1991 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | 128402 | DIESEL | CHURCHILL | 1991-02-26 | 1991-06-11 | 1991-06-11 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
5KJJAED12MPMG7787 | 2334 | 14 | C723 | C379 | C723 | 2019 | WESTERN | 4900SF | TRANSPORT TRUCK | 9023 | DIESEL | 0 | 2019-10-03 | 2019-11-14 | 2020-09-28 | MUNCIE |  | A | A |  | Elko Storm Water Maintenance Crew | Elko | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GCNCPEC1FZ271159 | 2335 | 5 | C727 | C040 | C727 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 42893 | UNLEADED | CARSON CITY | 2015-01-28 | 2015-04-03 | 2015-06-04 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [5 empty] | PROFILING SYSTEM | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCRCPEC7FZ261446 | 2336 | 5 | C721 | C040 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 68656 | E-85 | CLARK | 2015-01-28 | 2015-03-24 | 2015-05-05 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
5KKHALFG8MPMN5700 | 2350 | 83 |  | New | C767 | 2020 | WESTERN ST | 4900 | UNDERBRIDGE INSPECTION TRUCK |  |  | WASHOE | 2020-02-27 | 2021-02-23 | 2021-03-29 |  |  |  | A |  | #N/A | Carson City | District 2 |  | No | 7 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1HTXRSBT96J309026 | 2359 | 25 | C723 | C350 | C723 | 2006 | INTL | 5900I | WATER TRUCK | 65342 | DIESEL | ELKO | 2006-07-01 | 2006-12-06 | 2007-01-12 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTXRSBT06J309030 | 2360 | 25 | C725 | C170 | C725 | 2006 | INTL | 5900I | WATER TRUCK | 142064 | DIESEL | NYE | 2006-07-01 | 2006-12-21 | 2006-12-28 |  |  | A | A |  | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1GCNKPEC4FZ267206 | 2362 | 5 | C727 | C813 | C727 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | 62712 | UNLEADED | CARSON CITY | 2015-01-28 | 2015-03-27 | 2015-08-17 |  |  | A | A |  | Planning Traffic | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BB5LGC36358 | 2365 | 01A | C721 | C028 | C721 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | 3113 | E-85 | WASHOE | 2020-01-09 | 2020-10-06 | 2021-02-23 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E55LKE17025 | 2366 | 5 | C767 | C040 | C767 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 4464 | FLEX FUEL | WASHOE | 2020-01-16 | 2020-07-24 | 2021-04-01 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E53LKE17024 | 2368 | 5 | C727 | C040 | C727 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | 4461 | FLEX FUEL | WASHOE | 2020-01-16 | 2020-07-28 | 2021-02-04 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1C4RJFAG1LC366247 | 2373 | 01A | C727 | C050 | C727 | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | 3193 | UNLEADED | WASHOE | 2020-03-10 | 2020-08-04 | 2020-11-24 |  |  | A | A |  | Maintenance and Asset Mgmt | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT56J309024 | 2374 | 25 | C767 | C251 | C767 | 2006 | INTL | 5900I | WATER TRUCK | 65147 | DIESEL | WASHOE | 2005-07-01 | 2006-12-11 | 2006-12-27 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Pilot |  | #N/A
1GCNCPEH2FZ271957 | 2375 | 5 | C767 | C018 | C767 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 41344 | UNLEADED | CARSON CITY | 2015-01-28 | 2015-04-03 | 2015-05-29 |  |  | A | A |  | Storm Water Program | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BB0LGC67971 | 2377 | 01A | C721 | C101 | C721 | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | 3171 | FLEX FUEL | CLARK | 2020-03-10 | 2020-10-06 | 2020-12-30 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMSK8BB0LGC67971 |  |  |  |  | 11.22.2022
3C7WRNBL8LG214872 | 2379 | 11F | C723 | C723 | C723 | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 UTILITY TRUCK WITH CRANE ASSEMBLY | 1480 | DIESEL | ELKO | 2020-05-04 | 2020-08-19 | 2021-06-07 | parker |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3C7WRNBL8LG214872 |  | Yes |  |  | 11.30.2022 | 12/2/2022: highlighted in red because there are some discrepancies in the Device vs License Plate based on the installation history report downloaded from Gov5 server. Need to verify with GofFleet. 12/1/2022: The unit number is mistyped In the Gov5 database. GoFleet need to correct it from 2389 to 2379.
1C4RJFAG5LC366249 | 2380 | 01A | C727 | C040 | C727 | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE 4X4 | 251 | UNLEADED | CARSON CITY | 2020-03-10 | 2020-08-04 | 2020-10-21 |  |  | A | A |  | Construction Administration | Carson City | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3BPDLK0X3NF111281 | 2381 | 77 | C767 | C241 | C767 | 2022 | PETERBILT | 520 | 2022 PETERBILT 520 FREEWAY LINE STRIPE | 3424 | DIESEL | WASHOE | 2020-06-05 | 2021-10-15 | 2022-06-01 |  |  |  | A | New - Nov 2022 | Reno Striping Crew 2 | Reno | District 2 |  |  | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTEX1C5XLKE81205 | 2382 | 5 | C721 | C915 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | 6990 | FLEX FUEL | CLARK | 2020-09-01 | 2020-09-10 | 2021-02-11 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT36J309023 | 2385 | 25 | C720 | C127 | C720 | 2006 | INTL | 5900I | WATER TRUCK | 89968 | DIESEL | CLARK | 2006-07-06 | 2006-12-06 | 2007-02-13 |  |  | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH8FZ276225 | 2386 | 5 | C726 | C920 | C726 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 37487 | UNLEADED | HUMBOLDT | 2015-01-28 | 2015-04-03 | 2015-05-05 |  |  | A | A |  | Construction Crew Winnemucca | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C52LKE81201 | 2387 | 5 | C721 | C915 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | 11525 | FLEX FUEL | CLARK | 2020-09-01 | 2020-09-10 | 2021-02-11 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C54LKE81202 | 2390 | 5 | C721 | C916 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | 1870 | E-85 | CLARK | 2020-09-01 | 2020-09-10 | 2021-03-11 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C51LKE81206 | 2391 | 5 | C721 | C916 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | 3552 | E-85 | CLARK | 2020-09-01 | 2020-09-10 | 2021-03-16 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C58LKE81204 | 2392 | 5 | C721 | C101 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | 123 | E-85 | CLARK | 2020-09-01 | 2020-09-10 | 2021-05-17 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C58LKE81204 |  |  |  |  | 11.23.2022
1FTEX1C55LKE81208 | 2393 | 5 | C721 | C159 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | 1691 | E-85 | CLARK | 2020-09-01 | 2020-09-10 | 2021-07-06 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot New | Pre-Pilot | 1FTEX1C55LKE81208 |  |  |  |  | 11.22.2022 | 11/16/2022: In an internal meeting Billie mentioned that this vehicle need to get into Pre-Pilot
1FTEX1C53LKE81207 | 2395 | 5 | C721 | C101 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | 537 | E-85 | CLARK | 2020-09-01 | 2020-09-10 | 2021-05-04 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTEX1C53LKE81207 |  | Yes |  |  | 11.22.2022
1GCNCPEH1FZ273442 | 2396 | 5 | C721 | C916 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 30586 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-05-20 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E53LKE81211 | 2397 | 5 | C767 | C911 | C767 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 2726 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2020-11-19 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E55LKE81212 | 2398 | 5 | C727 | C911 | C727 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 859 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2021-05-05 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E50LKE81215 | 2399 | 5 | C727 | C911 | C727 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 5781 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2021-03-04 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E57LKE81213 | 2400 | 5 | C721 | C040 | C721 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 1983 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2021-05-10 |  |  | A | A |  | Construction Administration | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E54LKE81217 | 2401 | 5 | C767 | C904 | C767 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 6285 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2021-05-12 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E56LKE81218 | 2402 | 5 | C767 | C905 | C767 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 232 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2021-02-23 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH0FZ274226 | 2403 | 5 | C723 | C918 | C723 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | 32840 | UNLEADED | ELKO | 2015-01-28 | 2015-04-03 | 2015-07-05 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GCNCPEH0FZ274226 |  |  |  |  | 11.29.2022
1FTFX1E55LKE81209 | 2404 | 5 | C767 | C910 | C767 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 3712 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2021-05-05 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E51LKE81210 | 2405 | 5 | C767 | C910 | C767 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 8137 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2020-12-30 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E52LKE81216 | 2406 | 5 | C767 | C904 | C767 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 12457 | FLEX FUEL | WASHOE | 2020-05-15 | 2020-08-19 | 2020-12-01 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTEX1C56LKE81203 | 2407 | 5 | C721 | C903 | C721 | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | 950 | E-85 | CLARK | 2020-09-01 | 2020-09-10 | 2021-03-18 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FTFX1E59LKE81214 | 2408 | 5 | C723 | C723 | C723 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 6346 | FLEX FUEL | ELKO | 2020-05-15 | 2020-08-19 | 2021-01-26 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFX1E59LKE81214 |  | Yes |  |  | 11.29.2022
1FTFX1E58LKE81219 | 2409 | 5 | C726 | C726 | C726 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 9706 | FLEX FUEL | HUMBOLDT | 2020-05-15 | 2020-08-19 | 2020-10-20 |  |  | A | A |  | Winnemucca District Repair Shop | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFX1E54LKE81220 | 2410 | 5 | C723 | C723 | C723 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | 9778 | FLEX FUEL | ELKO | 2020-05-15 | 2020-08-19 | 2020-12-10 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTFX1E54LKE81220 |  | Yes |  |  | 11.30.2022
1GCNCPEH7FZ276913 | 2421 | 5 | C721 | C903 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 34012 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-07-02 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GCNCPEH3FZ273412 | 2423 | 5 | C721 | C916 | C721 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | 54257 | E-85 | CLARK | 2015-01-28 | 2015-04-03 | 2015-07-02 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4GT8GEA73244 | 2429 | 11F | C767 | C011 | C767 | 2016 | FORD | F-450 | SERVICE TRUCK | 70233 | DIESEL | CARSON CITY | 2015-04-29 | 2015-11-05 | 2016-06-01 |  |  | A | A |  | Structural Design | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FD8X3F69GEA50836 | 2448 | 10 | C722 | C813 | C722 | 2016 | FORD | F-350 | 1 TON TRUCK W/UTILITY BODY | 59140 | UNLEADED | CARSON CITY | 2015-04-29 | 2015-09-28 | 2015-11-05 |  |  | A | A |  | Planning Traffic | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X78D739607 | 2463 | 28 | C724 | C319 | C724 | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | 44594 | DIESEL | WHITE PINE | 2006-07-01 | 2007-06-08 | 2007-06-12 | DANFOSS |  | A | A |  | Ely Yard Stockpile Control | Ely | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X98D739608 | 2464 | 28 | C728 | C280 | C728 | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | 49470 | DIESEL | LYON | 2006-07-01 | 2007-06-08 | 2007-06-26 | DANFOSS |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A | [5 empty] | 10/13/2022: Bring this vehicle to Renot from Fallon during installation.
1M2K194C3MM002897 | 2474 | 77 | C726 | C341 | C726 | 1991 | MACK | MR688 | LINE STRIPER | 217055 | DIESEL | HUMBOLDT | 1991-04-04 | 1991-04-04 | 1991-04-04 |  |  | A | A |  | Winnemucca Striping Crew | Winnemucca | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X08D739609 | 2479 | 28 | C726 | C320 | C726 | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | 31027 | DIESEL | HUMBOLDT | 2006-07-01 | 2007-06-08 | 2007-06-13 | DANFOSS |  | A | A |  | Winnemucca Yard Stockpile Control | Winnemucca | District 3 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGA6T3NH444681 | 2487 | 13 | C767 | C253 | C767 | 1992 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 206367 | DIESEL | WASHOE | 1992-04-21 | 1992-07-06 | 1992-07-06 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE WING PLOW,SANDER,2001 HENKE REV WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
3ALACXFC1MDMJ2743 | 2491 | 24 | C723 | C355 | C723 | 2020 | ELGIN | EAGLE | 2020 SELF PROPELLED TENNANT BR | 1008 | DIESEL | ELKO | 2019-10-22 | 2020-07-28 | 2020-08-26 |  |  | A | A |  | Elko Bridge Maintenance Crew | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1G1ZC5ST6LF114372 | 2525 | 1 | C723 | C723 | C723 | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | 1519 | FLEX FUEL | ELKO | 2020-01-27 | 2020-03-24 | 2020-03-31 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZC5ST6LF114372 |  | Yes |  |  | 11.29.2022
1G1ZC5ST9LF114544 | 2528 | 1 | C723 | C723 | C723 | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | 915 | FLEX FUEL | WASHOE | 2020-01-27 | 2020-03-24 | 2020-03-31 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | 1G1ZC5ST9LF114544 |  | Yes |  |  | 11.29.2022
1FT7X2B6XLED39542 | 2531 | 3 | C723 | C723 | C723 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | 5090 | FLEX FUEL | ELKO | 2020-01-27 | 2020-04-14 | 2022-02-08 |  |  |  | A | New - Nov 2022 | Elko District Repair Shop | Elko | District 3 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7X2B6XLED39542 |  |  |  |  | 11.29.2022
1G1ZC5ST5LF134077 | 2535 | 1 | C726 | C304 | C726 | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | 2404 | FLEX FUEL | HUMBOLDT | 2020-03-20 | 2020-07-15 | 2020-08-03 |  |  | A | A |  | Winnemucca District Administration | Winnemucca | District 3 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1FT8W3CT6LED69686 | 2537 | 6 | C767 | C026 | C767 | 2020 | FORD | F-350 | FORD F-350 1 TON PICKUP TRUCK | 1137 | DIESEL | WASHOE | 2020-02-28 | 2020-07-28 | 2021-08-17 |  |  |  | A | New - Nov 2022 | Materials Pavement Design | Carson City | District 2 |  |  | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GAZGNFGXL1276293 | 2544 | 4 | C721 | C160 | C721 | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS 15 PASSENGER VAN | 647 | E-85 | CLARK | 2020-02-28 | 2020-11-03 | 2020-12-03 |  |  | A | A |  | Las Vegas Maintenance Crew | Las Vegas | District 1 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
0699-2171 | 2545 | 42 | C767 | C250 | C767 | 1999 | KODIAK | CR65 | ROTARY SNOW BLOWER | 2107 | DIESEL | WASHOE | 1999-07-02 | 1999-07-02 | 1999-11-04 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HT1LEE49095 | 2549 | 11E | C767 | C243 | C767 | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | 2283 | DIESEL | WASHOE | 2020-03-10 | 2021-01-12 | 2022-06-09 |  |  |  | A | New - Nov 2022 | #N/A | Reno | District 2 |  |  | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FD0W4HTXLEE49094 | 2550 | 11E | C728 | C203 | C728 | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | 7635 | DIESEL | WASHOE | 2020-03-10 | 2021-02-09 | 2022-05-10 |  |  |  | A | New - Nov 2022 | Silver Springs Crew | Fallon | District 2 |  |  | 5 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
WKU5856SG6R010008 | 2583 | 55B | C767 | C092 | C767 | 2007 | PSTN BULLY | SCOUT | SNOW CAT | 159 | RFG | WASHOE | 2006-07-01 | 2007-04-06 | 2007-05-07 |  |  | A | A |  | Communications Reno | Reno | District 2 |  | No | OFF ROAD / NA | None- wired direct | [5 empty] | BLADE 6-WAY | Telematics Device |  |  |  |  | Yes | Yes |  | Pilot |  | #N/A | Yes | Yes |  |  |  | 8/17/2022: In the internal discussion between Billie, Yesh and Priyanka it was decided that all the SnowCats should have Satellite
8002115 921792Q08 | 2619 | 76 | C767 | C026 | C767 | 1992 | DYNA | TEST | FALLING WEIGHT DEFLECTOMETER | 45383 |  | CARSON CITY | 1992-08-17 | 1992-08-17 | 1992-08-17 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFW1E52NKD26820 | 2621 | 5 | C727 | C027 | C727 | 2022 | FORD | F-150 | 2022 FORD F-150 SHORT BED CREW CAB 4 X4 | 1457 | FLEX FUEL | CARSON CITY | 2021-09-27 | 2022-02-25 | 2022-07-12 |  |  |  | A | New - Nov 2022 | Materials Bituminous | Carson City | District 2 |  |  | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P57EB44396 | 2647 | 3 | C721 | C922 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 145441 | BIO DIESEL | CLARK | 2007-03-23 | 2007-04-19 | 2007-06-19 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
8002-435 | 2666 | 76 | C767 | C026 | C767 | 2018 | DYNA | 8000 | 2018 SKID TESTER | 29 |  | 0 | 2018-03-27 | 2019-04-01 | 2019-05-07 |  |  | A | A |  | Materials Pavement Design | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GDKC34J9VJ513846 | 2670 | 11A | C720 | C102 | C725 | 1997 | GMC | 3500H | AERIAL TRUCK W/MAN LIFT | 126421 | UNLEADED | CLARK | 1997-08-06 | 1997-10-03 | 1997-10-03 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER7WH518343 | 2675 | 12 | C720 | C126 | C720 | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 57074 | DIESEL | CLARK | 1997-10-30 | 1998-01-14 | 1998-01-14 | REXROTH | FORCE AMERICA | A | A |  | Mountain Springs Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 1989 SANDER,HENKE 11' REVERSIBLE PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER5WH518342 | 2676 | 12 | C767 | C252 | C767 | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 147772 | DIESEL | WASHOE | 1997-10-30 | 1998-02-04 | 1998-02-04 | REXROTH | FORCE AMERICA | A | A |  | Reno Maintenance Crew 3 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE PLOW,5 YRD | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER7WH518309 | 2677 | 12 | C721 | C129 | C721 | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 167443 | DIESEL | LINCOLN | 1997-10-03 | 1998-02-19 | 1998-02-19 | REXROTH | FORCE AMERICA | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,1997 SANDER | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET5VH498145 | 2679 | 25 | C724 | C724 | C724 | 1997 | INTL | 2574 | 1997 REBUILT TANDEM AXLE WATER TRUCK | 863 | DIESEL | 0 | 1997-07-08 | 1997-09-12 | 1997-09-12 |  |  | A | A |  | Ely District Repair Shop | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,8 YRD SANDER CHIEF | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTYW96Y8VVA46107 | 2680 | 14 | C721 | C121 | C721 | 1996 | FORD | 9501 | TRACTOR TRUCK | 198084 | DIESEL | CLARK | 1997-04-14 | 1997-05-14 | 1997-05-14 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 9 | J1939 | [5 empty] | BREAKER ATTACHMENT | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTTNAHT2WJ000137 | 2682 | 15 | C767 | C250 | C767 | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | 73861 | DIESEL | WASHOE | 1998-01-09 | 1998-04-22 | 2013-12-06 | INTERNATIONAL/COMMERCIAL | PARKER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 2011 HENKE 10 ONE-WAY SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTTNAHT6WJ000139 | 2684 | 15 | C767 | C250 | C767 | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | 55695 | DIESEL | WASHOE | 1998-01-30 | 1998-03-05 | 2013-11-15 | INTERNATIONAL/COMMERCIAL | PARKER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | ONE WAY PLOW TRUCK PATROL | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXH81C5VVA40711 | 2685 | 24 | C728 | C236 | C728 | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | 39483 | DIESEL | LYON | 1997-09-03 | 1997-10-14 | 1997-10-14 |  |  | A | A |  | Yerington Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2691 | 28 | C767 | C251 | #N/A | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | 37771 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Blank - 1/24/2023 |  | #N/A |  | Yes
4VHJAAPE5VR857929 | 2692 | 28 | C725 | C171 | C725 | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | 95395 | DIESEL | NYE | 1997-06-04 | 1997-07-30 | 1997-07-30 |  |  | A | A |  | Tonopah Maintenance Crew 2 | Tonopah | District 1 |  | Yes | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
297-2133 | 2700 | 42 | C723 | C723 | C723 | 1997 | KODIAK | CR400 | ROTARY SNOW BLOWER | 1969 | DIESEL | WASHOE | 1997-02-20 | 1997-02-24 | 1997-02-24 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GTHK33JOXF009887 | 2733 | 10 | C721 | C121 | C721 | 1998 | GMC | K3094 | SURVEY UNIT | 189907 | UNLEADED | CLARK | 1998-10-09 | 1998-11-16 | 1998-11-16 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAHR3XH663550 | 2741 | 11B | C723 | C723 | C723 | 1998 | INTL | F2574 | CRANE TRUCK W/FLATRACK | 227571 | DIESEL | ELKO | 1998-12-11 | 1998-12-11 | 1999-02-02 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 6 | J1939 | [5 empty] | ARROW SIGNBOARD, T/M,SCORPION ATTENUATOR TRK MNT | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1GDJK34J9XF013366 | 2742 | 11J | C767 | C767 | C767 | 1998 | GMC | TK314 | UTILITY TRUCK | 22653 | RFG | WASHOE | 1998-11-04 | 1998-11-04 | 1998-11-04 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2747 | 11E | C767 | C767 | #N/A | 1998 | GMC | TC31003 | DUMP TRUCK | 208742 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
#N/A | 2753 | 11E | C767 | C767 | #N/A | 1998 | GMC | TC31003 | DUMP TRUCK | 185126 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
J8DF5A12XW3701443 | 2754 | 11J | C721 | C121 | C721 | 1998 | GMC | W5R04 | UTILITY TRUCK | 78567 | DIESEL | CLARK | 1998-06-30 | 1998-07-13 | 1998-07-13 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTGK24R9WZ540092 | 2761 | 3 | C723 | C723 | C723 | 1998 | GMC | SIERRA | 3/4 TON PICKUP TRUCK W/SVC BODY AWD | 107410 | UNLEADED | ELKO | 1998-05-18 | 1998-09-04 | 1998-09-04 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GTGK24R9WZ540092 |  |  |  |  | 11.30.2022
1HTGEAER9XH631230 | 2764 | 12 | C723 | C324 | C723 | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 208105 | DIESEL | EUREKA | 1999-01-27 | 1999-01-27 | 1999-02-05 |  |  | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,5 YD | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER6XH631220 | 2765 | 12 | C723 | C350 | C723 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 177284 | DIESEL | ELKO | 1999-04-30 | 1999-04-30 | 1999-06-09 |  |  | A | A |  | Elko Maintenance Crew 1 | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2000 FLINK SANDER,11 REVERSIBLE | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAERXXH631222 | 2766 | 12 | C723 | C324 | C723 | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 215563 | DIESEL | EUREKA | 1999-01-12 | 1999-01-12 | 1999-03-01 |  |  | A | A |  | Emigrant Pass Maintenance Crew | Elko | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,PLOW,SANDER 5 CU YD,2020 SCORPION VEH MNT ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER0XH631228 | 2767 | 12 | C724 | C381 | C724 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 276719 | DIESEL | WHITE PINE | 1999-05-11 | 1999-05-11 | 1999-07-12 |  |  | A | A |  | Ely Maintenance Crew 2 | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER2XH631229 | 2768 | 12 | C723 | C332 | C723 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 100427 | DIESEL | ELKO | 1999-05-12 | 1999-05-12 | 1999-06-14 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 YD Flink,11 FT. REVERSIBLE SNOW PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER1XH631223 | 2769 | 12 | C722 | C227 | C722 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 246493 | DIESEL | DOUGLAS | 1999-05-19 | 1999-05-19 | 1999-12-10 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSIBLE JENSEN PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER9XH631227 | 2770 | 12 | C723 | C336 | C723 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 221081 | DIESEL | ELKO | 1999-05-19 | 1999-05-19 | 1999-06-14 |  |  | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | FLINK LCM 10NV-59 SANDER,PLOW,ATTENUATOR, TM,ARROW SIGNBOARD, T/M | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER7XH631226 | 2771 | 12 | C723 | C335 | C723 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 135933 | DIESEL | ELKO | 1999-04-20 | 1999-06-09 | 1999-06-09 |  |  | A | A |  | Wells Maintenance Crew 2 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER8XH631221 | 2772 | 12 | C724 | C384 | C724 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 232297 | DIESEL | EUREKA | 1999-04-20 | 1999-07-12 | 1999-07-12 |  |  | A | A |  | Eureka Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 CU YD SANDER,PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAER5XH631225 | 2773 | 12 | C721 | C145 | C721 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 101309 | DIESEL | CLARK | 1999-04-30 | 1999-04-30 | 1999-07-26 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET7XH631216 | 2774 | 13 | C726 | C372 | C726 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 244270 | DIESEL | LANDER | 1999-04-05 | 1999-04-15 | 1999-04-15 |  |  | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,PLOW TENCO WING,8 CU YD SANDER,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET1XH631213 | 2775 | 13 | C723 | C332 | C723 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 309584 | DIESEL | ELKO | 1999-03-31 | 1999-06-09 | 1999-06-09 |  |  | A | A |  | Wells Maintenance Crew 1 | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW,8 YD FLINK | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET9XH631217 | 2776 | 13 | C726 | C370 | C726 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 220122 | DIESEL | HUMBOLDT | 1999-03-16 | 1999-03-16 | 1999-03-30 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE TRK MTED WING PLOW,SANDER 8 CU YD,PLOW REVERSIBLE,PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET6XH631210 | 2777 | 13 | C722 | C271 | C722 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 244970 | DIESEL | CARSON CITY | 1999-02-24 | 1999-02-24 | 1999-02-24 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 2011 HENKE ONE-WAY 10 SNOW PLOW,FLINK/MDL 15 LM C5H 8 CU YRD | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAETXXH631212 | 2778 | 13 | C722 | C227 | C722 | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 103089 | DIESEL | CLARK | 1999-01-28 | 1999-01-28 | 2012-09-27 | COMMERCIAL | PARKER | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | TENCO 11FT REVERSIBLE PLOW,8 YARD FLINK SANDER,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1HTGGAET22XH631219 | 2779 | 13 | C767 | C251 | C767 | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | 53535 | DIESEL | WASHOE | 1999-02-23 | 1999-02-23 | 2011-12-22 | COMMERCIAL | PARKER | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE WING PLOW,1991 PLOW,1991 SANDER,TENCO 11 FT. REVERSIBLE PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1HTGGAET8XH631211 | 2780 | 13 | C722 | C235 | C722 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 216530 | DIESEL | LYON | 1999-03-31 | 1999-03-31 | 1999-03-31 |  |  | A | A |  | Wellington Maintenance Crew | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 YD SANDER,PLOW,11FT JENSEN REVERSIBLE SNOW PLOW,8 YRD,SPRAYER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET3XH631214 | 2783 | 13 | C723 | C322 | C723 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 252769 | DIESEL | ELKO | 1999-03-09 | 1999-03-09 | 1999-06-09 |  |  | A | A |  | Contact Maintenance Crew | Wells | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 8 YD,HENKE REVERSIBLE,PLOW WING | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
2HSFBAERXXC078457 | 2785 | 14 | C726 | C370 | C726 | 1998 | INTL | F9300 | TRACTOR TRUCK | 211221 | DIESEL | HUMBOLDT | 1998-09-10 | 1998-10-05 | 1998-10-05 |  |  | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2HSFBAER8XC078456 | 2786 | 14 | C767 | C028 | C767 | 1998 | INTL | F9300 | TRACTOR TRUCK | 159409 | DIESEL | CARSON CITY | 1998-08-17 | 1998-09-30 | 1998-09-30 |  |  | A | A |  | Materials Geotechnical | Carson City | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2HSFBAER6XC078455 | 2787 | 14 | C767 | C253 | C767 | 1998 | INTL | F9300 | TRACTOR TRUCK | 147597 | DIESEL | WASHOE | 1998-09-25 | 1998-10-26 | 1998-10-26 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTTEAHR5XJ002602 | 2788 | 15 | C721 | C129 | C721 | 1999 | INTL | F5000 | AWD SANDER TRUCK | 89906 | DIESEL | CLARK | 1998-11-25 | 1998-11-25 | 1999-10-12 |  |  | A | A |  | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 6 | J1939 | Roadwatch Sensor |  |  |  |  | ONE-WAY PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTTNAHT2XJ002603 | 2789 | 15 | C767 | C250 | C767 | 1999 | INTL | F5000 | AWD SANDER TRUCK | 218636 | DIESEL | WASHOE | 1998-11-25 | 1999-02-03 | 1999-02-03 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 6 | J1939 | Roadwatch Sensor |  |  |  |  | ONE-WAY PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXH81C7VVA40712 | 2795 | 24 | C722 | C251 | C722 | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | 36241 | DIESEL | CARSON CITY | 1997-09-03 | 1997-09-24 | 1997-09-24 |  |  | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1A9N25DB7WR059001 | 2799 | 24 | C722 | C270 | C722 | 1998 | ATHEY | M-8A | SELF PROPELLED PICKUP BROOM | 80697 | DIESEL | CARSON CITY | 1998-10-02 | 1998-10-26 | 1998-10-26 |  |  |  | A | New - Nov 2022 | Carson City Maintenance Crew 1 | Carson City | District 2 |  |  | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1A9P24DR1WR059009 | 2801 | 24 | C721 | C124 | C721 | 1998 | MOBILE | M-8A | SP PICKUP BROOM HIGH DUMP | 49493 | DIESEL | CLARK | 1998-10-07 | 1998-11-12 | 1998-12-30 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1HTGEAHR5XH637022 | 2803 | 28 | C722 | C270 | C722 | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | 24700 | DIESEL | CARSON CITY | 1998-11-05 | 1998-11-23 | 1998-11-23 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 2804 | 28 | C725 | C170 | #N/A | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | 103737 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Tonopah Maintenance Crew 1 | Tonopah | District 1 |  | Yes | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
3813001 | 2810 | 55B | C725 | C725 | C725 | 1981 | TUCKER | SNOWCAT | SNOW CAT | 738 | UNLEADED | NYE | 2004-05-07 | 2004-06-21 | 2005-01-10 |  |  | A | A |  | Tonopah District Repair Shop | Tonopah | District 1 |  | Yes | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A | Yes |  |  |  |  | 8/17/2022: In the internal discussion between Billie, Yesh and Priyanka it was decided that all the SnowCats should have Satellite
198-2153 | 2826 | 42 | C767 | C250 | C767 | 1998 | KODIAK | CR65 | ROTARY SNOW BLOWER | 1445 | DIESEL | WASHOE | 1998-04-03 | 1998-04-17 | 1998-04-17 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | OFF ROAD / NA | None- wired direct | [6 empty] | Telematics Device | Yes |  | Snow Blower Activation |  | Yes | Yes |  | Full Project |  | #N/A
1FVACYFE5LHLG5647 | 2904 | 11A | C721 | C140 | C721 | 2019 | FREIGHTLNR | M2 | 2019 AERIAL LIFT TRUCK | 4337 | DIESEL | CLARK | 2018-07-24 | 2019-10-18 | 2020-01-08 | TEREX |  | A | A |  | Las Vegas Sign Crew 1 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1GTEK14W2XE553122 | 2906 | 5 | C767 | C767 | C767 | 1999 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | 129643 | RFG | WASHOE | 1999-07-27 | 1999-07-27 | 1999-07-27 |  |  | A | A |  | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3C7WRNBL3JG346242 | 2907 | 11A | C723 | C302 | C723 | 2018 | DODGE | 5500 | 2018 AERIAL LIFT TRUCK | 41788 | DIESEL | ELKO | 2018-07-13 | 2019-08-14 | 2019-08-14 | FORCE |  | A | A |  | Elko Service Crew | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 3C7WRNBL3JG346242 |  | Yes |  |  | 11.29.2022
1NPTM70X5GD351019 | 2909 | 15 | C722 | C227 | C722 | 2016 | PETERBILT | 367 | AWD TANDEM AXLE PLOW TRUCK | 33385 | DIESEL | DOUGLAS | 2015-06-15 | 2015-12-10 | 2017-10-13 | PARKER | CERTIFIED POWER | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | EPOKE |  |  |  | SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPTM70X1GD351020 | 2910 | 15 | C767 | C250 | C767 | 2016 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | 42416 | DIESEL | WASHOE | 2015-06-15 | 2015-12-10 | 2017-01-03 | PARKER | CERTIFIED POWER | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | Yes Final | 6 | J1939 | Roadwatch Sensor | EPOKE | GO9+ |  |  |  | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1NPTM70X1GD351020
1FD0X5HT8KEE25975 | 2911 | 11A | C767 | C011 | C767 | 2019 | FORD | F-550 | 2019 ARIEL LIFT TRUCK | 11344 | DIESEL | CARSON CITY | 2018-06-18 | 2018-12-01 | 2019-11-22 | PARKER | VERSALIFT | A | A |  | Structural Design | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ND52J9Y6217366 | 2912 | 1 | C721 | C721 | C721 | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 132347 | UNLEADED | CLARK | 2000-01-07 | 2000-01-07 | 2000-01-21 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot |  | #N/A
1FTEX1C50MFA39091 | 2913 | 5 | C721 | C101 | C721 | 2021 | FORD | F-150 | 2021 FORD F-150 1/2 TON PICKUP | 29711 | E-85 | CLARK | 2020-09-27 | 2021-02-09 | 2021-12-07 |  |  |  | A | New - Nov 2022 | Las Vegas District Administration | Las Vegas | District 1 |  |  | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMSK8BB9MGA65521 | 2915 | 01A | C721 | C101 | C721 | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER 4X4 | 698 | FLEX FUEL | CLARK | 2020-09-21 | 2021-02-24 | 2021-04-12 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMSK8BB9MGA65521 |  | Yes |  |  | 11.23.2022
1FBAX2C88MKA04793 | 2916 | 4 | C721 | C101 | C721 | 2021 | FORD | T-350 | 2021 FORD T-350 12 PASSENGER TRANSIT VAN | 999 | E-85 | CLARK | 2020-09-29 | 2021-02-09 | 2021-04-13 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FBAX2C88MKA04793 |  | Yes | 11.21.2022 | 11.21.2022 | 11.21.2022
#N/A | 2917 | 1 | C767 | C767 | #N/A | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 125711 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  |  |  | #N/A
1FT7W2B63MEC41005 | 2919 | 3 | C723 | C331 | C723 | 2021 | FORD | F-250 | 2021 FORD F-250 SHORT BED PICKUP 4X4 | 20817 | FLEX FUEL | ELKO | 2020-09-27 | 2021-02-09 | 2021-09-21 |  |  |  | A | New - Nov 2022 | Ruby Valley Maintenance Crew | Elko | District 3 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7W2B63MEC41005 |  |  |  |  | 11.30.2022
1NPTL70X9GD351009 | 2920 | 13 | C721 | C178 | C721 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 48958 | DIESEL | CLARK | 2015-06-15 | 2015-12-02 | 2016-08-10 | PARKER IQUAN | PARKER IQUAN | A | A |  | Panaca Maintenance Crew | Las Vegas | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SNOW PLOW,2001 FLINK SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B67MEC41007 | 2922 | 3 | C723 | C322 | C723 | 2021 | FORD | F-250 | 2021 FORD F-250 SHORT BED PICKUP 4X4 | 20311 | FLEX FUEL | ELKO | 2020-09-27 | 2021-02-09 | 2021-09-21 |  |  |  | A | New - Nov 2022 | Contact Maintenance Crew | Wells | District 3 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B65MEC41006 | 2923 | 3 | C723 | C327 | C723 | 2021 | FORD | F-250 | 2021 FORD F-250 SHORT BED PICKUP 4X4 | 11871 | FLEX FUEL | ELKO | 2020-09-27 | 2021-02-09 | 2021-10-04 |  |  |  | A | New - Nov 2022 | North Fork Maintenance Crew | Elko | District 3 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7W2B65MEC41006 |  |  |  |  | 11.30.2022
1FT7X2B69NEC68952 | 2925 | 3 | C721 | C031 | C721 | 2022 | FORD | F-250 | 2022 FORD F250 EXTENDED CAB SHORT BED 4X4 | 2051 | E-85 | CLARK | 2021-02-23 | 2021-12-02 | 2022-03-22 |  |  |  | A | New - Nov 2022 | Right of Way Las Vegas | Las Vegas | District 1 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FT7X2B69NEC68952 |  |  |  |  | 11.23.2022
1FT7X2B67NEC68951 | 2926 | 3 | C727 | C040 | C727 | 2021 | FORD | F-250 | 2021 FORD F-250 LONG BED 4X4 | 2463 | FLEX FUEL | CARSON CITY | 2021-02-23 | 2021-12-02 | 2022-03-28 |  |  |  | A | New - Nov 2022 | Construction Administration | Carson City | District 2 |  |  | 3 | OBDII | Roadwatch Sensor |  |  |  | Yes |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GKDT13W7YK244831 | 2927 | 01A | C721 | C721 | C721 | 2000 | GMC | JIMMY | AWD SUV | 92087 | UNLEADED | CLARK | 2000-04-26 | 2000-04-26 | 2000-10-01 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GKDT13W7YK244831 |  |  |  |  | 11.22.2022
1NPTL70X9GD351012 | 2928 | 13 | C725 | C173 | C725 | 2016 | PETERBILT | 367 | TANDEM AXLE SWAP LOADER | 37596 | DIESEL | NYE | 2015-06-16 | 2015-12-02 | 2017-05-09 | PARKER | PARKER | A | A |  | Blue Jay Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | ONE WAY PLOW,SANDER,DUMP BODY | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FT7X2B60NEC68953 | 2930 | 3 | C726 | C304 | C726 | 2021 | FORD | F-250 | 2021 FORD F-250 EXTENDED CAB SHORT BED 4X4 | 4011 | UNLEADED | HUMBOLDT | 2021-04-08 | 2021-12-02 | 2022-03-22 |  |  |  | A | New - Nov 2022 | Winnemucca District Administration | Winnemucca | District 3 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FT7W2B61NEC68950 | 2931 | 3 | C723 | C301 | C723 | 2021 | FORD | F-250 | 2021 FORD F-250 CREW CAB SHORT BED 4X4 | 10015 | UNLEADED | ELKO | 2021-04-08 | 2021-12-10 | 2022-03-28 |  |  |  | A | New - Nov 2022 | Elko District Administration | Elko | District 3 |  |  | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
1GTHG35J6Y1135104 | 2932 | 4 | C725 | C095 | C721 | 2000 | GMC | TG31405 | AWD CARGO VAN | 123775 | UNLEADED | CLARK | 2000-06-27 | 2000-06-27 | 2000-07-31 |  |  | A | A |  | Communications Tonopah | Tonopah | District 1 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2941 | 5 | C726 | C726 | #N/A | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | 170489 | UNLEADED | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Winnemucca District Repair Shop | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1GTEC14W4YE341076 | 2943 | 5 | C726 | C716 | C726 | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | 67150 | UNLEADED | HUMBOLDT | 2000-04-14 | 2000-04-14 | 2000-05-05 |  |  | A | A |  | Winnemucca District Stockroom | Winnemucca | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTFW1E57NKD26814 | 2945 | 5 | C727 | C040 | C727 | 2022 | FORD | F-150 | 2022 FORD F-150 SHORT BED CREW CAB 4 X4 | 3501 | FLEX FUEL | WASHOE | 2021-09-27 | 2022-03-17 | 2022-05-17 |  |  |  | A | New - Nov 2022 | Construction Administration | Carson City | District 2 |  |  | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14W0YE341110 | 2951 | 5 | C723 | C723 | C723 | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | 114970 | UNLEADED | ELKO | 2000-04-14 | 2000-04-14 | 2000-04-26 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GTEC14W0YE341110 |  |  |  |  | 11.30.2022
#N/A | 2952 | 5 | C767 | C767 | #N/A | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | 135160 | PROPANE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  |  |  | #N/A
1GTEK14V4YE327088 | 2975 | 5 | C767 | C757 | C767 | 2000 | GMC | SIERRA | 1/2 TON PICKUP AWD | 84883 | RFG | WASHOE | 2000-04-26 | 2000-04-26 | 2000-11-02 |  |  | A | A |  | Equipment Stockroom | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDWW36FXYED68718 | 2984 | 10 | C721 | C158 | C721 | 2000 | FORD | F-350 | SURVEY UNIT | 206074 | DIESEL | CLARK | 2000-07-06 | 2000-07-06 | 2000-08-16 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1FDWW36F1YED68719 | 2987 | 10 | C720 | C157 | C720 | 2000 | FORD | F-350 | SURVEY UNIT | 202928 | DIESEL | NYE | 2000-07-06 | 2000-07-06 | 2000-08-09 |  |  | A | A |  | Las Vegas Night Maintenance Crew 6 | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A |  | Yes
1HTSCABP91H347431 | 2989 | 11H | C767 | C767 | C767 | 2001 | INTL | 4700 | FLAT RACK TRUCK | 16528 | DIESEL | WASHOE | 2000-03-02 | 2000-10-17 | 2000-10-18 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
#N/A | 2990 | 11J | C767 | C767 | #N/A | 2000 | FORD | F-450 | AWD SIGN SHOP TRUCK | 277460 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed |  |  | #N/A
1HTSCABP01H347432 | 2991 | 11F | C723 | C723 | C723 | 2001 | INTL | 4700 | FLAT RACK W/CRANE | 218527 | DIESEL | ELKO | 2000-06-22 | 2000-09-27 | 2000-10-17 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAER31H343754 | 2993 | 11B | C726 | C341 | C726 | 2001 | INTL | F2574 | CRANE TRUCK W/FLATRACK | 137604 | DIESEL | HUMBOLDT | 2000-06-22 | 2001-03-29 | 2001-06-05 |  |  | A | A |  | Winnemucca Striping Crew | Winnemucca | District 3 |  | No | 6 | J1939 | [5 empty] | ATTENUATOR TRUCK MOUNTED | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
#N/A | 2995 | 11E | C721 | C129 | #N/A | 2000 | FORD | F-450 | DUMP TRUCK | 255469 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Charleston Maintenance Crew | Las Vegas | District 1 |  | Yes | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Deleted |  | #N/A
1FDXF46F5YEA97190 | 2996 | 11S | C720 | C152 | C720 | 2000 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOK LIFT | 392016 | BIO DIESEL | CLARK | 2000-06-01 | 2000-06-01 | 2014-08-11 | MUNCIE |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | SWAPLOADER DUMP BODY | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDXF46F5YEA97190 |  |  |  |  | 11.22.2022
1NPTL70X5GD351010 | 2998 | 13 | C723 | C336 | C723 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 115818 | DIESEL | ELKO | 2015-06-15 | 2015-12-02 | 2017-02-06 | PARKER IQUAN | PARKER IQUAN | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SNOW PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F4YEA97200 | 3001 | 11 | C767 | C767 | C767 | 2000 | FORD | F-450 | REBUILD MISC TRUCK - BOX TRUCK | 22792 | BIO DIESEL | WASHOE | 2000-06-01 | 2000-06-01 | 2015-09-21 | MONARCH 12 VOLT |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1NPTL70X7GD351011 | 3004 | 13 | C723 | C336 | C723 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 81911 | DIESEL | ELKO | 2015-06-15 | 2015-12-02 | 2016-12-23 | PARKER IQUAN | PARKER IQUAN | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW,SANDER,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FDXF46FXYEA89599 | 3005 | 11E | C720 | C152 | C720 | 2000 | FORD | F-450 | REBUILD DUMP TRUCK | 310435 | DIESEL | CLARK | 2000-06-01 | 2000-06-01 | 2012-04-02 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | ARROW BOARD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot | Pre-Pilot | 1FDXF46FXYEA89599 |  |  |  |  | 11.22.2022
1HTGEAER11H343757 | 3015 | 12 | C725 | C177 | C725 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 183660 | DIESEL | MINERAL | 2000-06-22 | 2000-10-13 | 2000-12-01 |  |  | A | A |  | Montgomery Pass Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | 5 YD FLINK,HENKE 4530 | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGEAERX1H343756 | 3017 | 12 | C724 | C385 | C724 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | 193716 | DIESEL | LANDER | 2000-06-22 | 2000-10-13 | 2000-12-01 |  |  | A | A |  | Austin Maintenance Crew | Ely | District 3 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SANDER,PLOW,8 YD SANDER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET4YH319811 | 3018 | 13 | C724 | C382 | C724 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 357909 | DIESEL | WHITE PINE | 2000-04-25 | 2000-04-25 | 2000-05-17 | PARKER IQAN | PARKER | A | A |  | Lund Maintenance Crew | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | TENKO 1 WAY PLOW,WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET6YH319826 | 3019 | 13 | C767 | C253 | C767 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 211205 | DIESEL | WASHOE | 2000-02-29 | 2000-07-18 | 2000-08-04 | PARKER IQAN | PARKER | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE WING PLOW,VARITECH 1750 GAL BRINE TANK,PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET2YH319824 | 3020 | 13 | C722 | C271 | C722 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 268614 | DIESEL | CARSON CITY | 2000-02-29 | 2000-05-26 | 2000-06-16 | PARKER IQAN | PARKER | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 8 CU YD FLINK LMC1H SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
#N/A | 3021 | 13 | C767 | C767 | #N/A | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 316508 | DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | D | #N/A | Deleted - Nov 2022 | Equipment Shop | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 2000 SANDER,SPRATRONICS DE ICER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Blank - 1/24/2023 |  | #N/A
1HTGGAET9YH319822 | 3022 | 13 | C722 | C271 | C722 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 267738 | DIESEL | CARSON CITY | 2000-02-29 | 2000-07-18 | 2000-08-04 | PARKER IQAN | PARKER | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | TENCO PLOW,FLINK SANDER 8 CU YRD | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET8YH319827 | 3023 | 13 | C724 | C380 | C724 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 294717 | DIESEL | WHITE PINE | 2000-03-29 | 2000-03-29 | 2000-04-12 | PARKER IQAN | PARKER | A | A |  | Ely Maintenance Crew 1 | Ely | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET5YH319820 | 3024 | 13 | C722 | C227 | C722 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 276867 | DIESEL | DOUGLAS | 2000-02-29 | 2000-05-26 | 2000-06-16 | PARKER IQAN | PARKER | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | FLINK 8 CU YD SANDER,11' TENCO PLOW,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET6YH319812 | 3025 | 13 | C726 | C372 | C726 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 300679 | DIESEL | HUMBOLDT | 2000-04-13 | 2000-04-13 | 2000-05-01 | PARKER IQAN | PARKER | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE TRK MTED WING PLOW,PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET9YH319819 | 3026 | 13 | C723 | C322 | C767 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 307560 | DIESEL | ELKO | 2000-02-29 | 2000-05-26 | 2000-05-26 | PARKER IQAN | PARKER | A | A |  | Contact Maintenance Crew | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | REVERSIBLE,FLINK 8 CUBIC YARD SANDER,PLOW WING | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAETXYH319828 | 3027 | 13 | C726 | C372 | C726 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 276706 | DIESEL | HUMBOLDT | 1999-11-09 | 2000-06-23 | 2000-07-25 | PARKER IQAN | PARKER | A | A |  | Orovada Maintenance Crew | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE HEAVY DUTY PATROL,SANDER,WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET7YH319818 | 3028 | 13 | C767 | C251 | C767 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 195586 | DIESEL | WASHOE | 2000-02-29 | 2000-08-28 | 2001-02-06 | PARKER IQAN | PARKER | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | HENKE WING PLOW,TENCO,FLINK,SPRATRONICS | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1HTGGAET5YH319817 | 3029 | 13 | C725 | C123 | C725 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 144750 | DIESEL | NYE | 2000-04-28 | 2000-04-28 | 2011-11-02 | PARKER IQAN | PARKER | A | A |  | Beatty Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | ONE WAY HENKE,2000 SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET1YH319815 | 3030 | 13 | C726 | C370 | C726 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | 37131 | DIESEL | HUMBOLDT | 2000-03-28 | 2000-03-28 | 2016-04-22 | PARKER IQAN | PARKER | A | A |  | Winnemucca Maintenance Crew 1 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW,SANDER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET8YH319813 | 3033 | 13 | C723 | C336 | C723 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 362365 | DIESEL | ELKO | 2000-02-29 | 2000-06-28 | 2000-07-10 | PARKER IQAN | PARKER | A | A |  | Wendover Maintenance Crew | Wells | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 1991 PLOW,2000 SANDER,HENKE WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET7YH319821 | 3034 | 13 | C726 | C374 | C726 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 259859 | DIESEL | HUMBOLDT | 2000-03-31 | 2000-03-31 | 2000-04-12 | PARKER IQAN | PARKER | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 8 CU YD FLINK LMC1H SANDER,REVERSIBLE PLOW, TENCO TC-132,DE-ICING SPRAYER | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVAB6BV37DY06657 | 3035 | 24 | C720 | C154 | C720 | 2008 | TYMCO | D3T6 | SWEEPER | 76382 | DIESEL | CLARK | 2007-08-22 | 2008-03-05 | 2008-04-01 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAET4YH319825 | 3037 | 13 | C726 | C374 | C726 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 238765 | DIESEL | HUMBOLDT | 2000-03-28 | 2000-03-28 | 2000-04-12 | PARKER IQAN | PARKER | A | A |  | Winnemucca Maintenance Crew 2 | Winnemucca | District 3 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | SANDER 8 CU YD HOPPER TYPE F,PLOW REVERSIBLE, TENCO TC-132 | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1HTXGAHT21J001955 | 3038 | 15 | C722 | C271 | C722 | 2001 | INTL | 5600I | AWD SANDER TRUCK | 201345 | DIESEL | CARSON CITY | 2000-06-22 | 2000-10-17 | 2001-01-18 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 6 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE SNOW PLOW | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV01HH65843 | 3039 | 24 | C720 | C154 | C720 | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | 86833 | DIESEL | CLARK | 2000-07-12 | 2000-07-31 | 2000-08-14 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV21HH65844 | 3040 | 24 | C720 | C159 | C720 | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | 89037 | DIESEL | CLARK | 2000-07-12 | 2000-07-31 | 2000-08-14 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1A9N25DB7YRO59003 | 3041 | 24 | C723 | C322 | C723 | 2000 | MOBILE | M-8A | STREET SWEEPER | 1003526 | DIESEL | ELKO | 2000-07-07 | 2000-07-24 | 2000-08-14 |  |  | A | A |  | Contact Maintenance Crew | Wells | District 3 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1GTEK14W1YZ314168 | 3066 | 5 | C721 | C903 | C721 | 2000 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | 158592 | E-85 | CLARK | 2000-06-24 | 2000-06-26 | 2000-08-04 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F2YEE09580 | 3068 | 11H | C721 | C158 | C721 | 2000 | FORD | F-450 | 1 TON FLATRACK TRUCK | 218737 | DIESEL | CLARK | 2000-07-12 | 2000-08-04 | 2000-09-06 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FVABTAK01DH67476 | 3069 | 11B | C721 | C113 | C721 | 2001 | FREIGHTLNR | FL70 | CRANE TRUCK | 78794 | DIESEL | CLARK | 2000-07-07 | 2000-09-05 | 2001-01-08 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDWF32R78EB95336 | 3071 | 11J | C720 | C102 | C720 | 2008 | FORD | F-350 | UTILITY TRUCK BIO-DIESEL | 88013 | BIO DIESEL | CLARK | 2007-03-29 | 2007-08-23 | 2008-05-20 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot | 1FDWF32R78EB95336
1NPZL00X91D713042 | 3072 | 13 | C721 | C158 | C721 | 2001 | PETERBILT | 320 | TANDEM AXLE DUMP TRUCK | 48125 | DIESEL | CLARK | 2000-11-01 | 2000-12-01 | 2001-01-09 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GTEC14V2YE399081 | 3089 | 5 | C725 | C767 | C767 | 2000 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | 177322 | UNLEADED | CARSON CITY | 2000-06-24 | 2000-06-26 | 2000-07-20 |  |  | D | D |  | Equipment Shop | Reno | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1B4GT44LXYB675305 | 3093 | 4 | C727 | C802 | C727 | 2000 | DODGE | GRAND CARAVA | 7 PASSENGER VAN | 88202 | UNLEADED | CARSON CITY | 2000-04-03 | 2000-04-03 | 2000-07-21 |  |  | A | A |  | Transportation / Multimodal Planning (Landmark) | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
JT2BK12U410006998 | 3096 | 1 | C721 | C721 | C721 | 2001 | TOYOTA | PRIUS | 4 DOOR SEDAN/HYBRID ELECTRIC | 78203 | HYBRID | CLARK | 2000-07-26 | 2000-08-02 | 2000-08-29 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Pre-Pilot | Pre-Pilot | JT2BK12U410006998 |  |  |  |  | 11.22.2022
1GTHK24U51E165715 | 3112 | 11J | C767 | C767 | C767 | 2001 | GMC | SIERRA | UTILITY TRUCK 4X4 | 248792 | UNLEADED | CLARK | 2001-06-07 | 2001-06-20 | 2001-08-08 |  |  | A | A |  | Equipment Shop | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 3113 | 1 | C721 | A002 | #N/A | 2002 | TOYOTA | PRIUS | HYBRID ELECTRIC SEDAN | 60294 | HYBRID | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Office of the Director | Carson City | District 2 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  |  |  | #N/A
JT2BK12U220041735 | 3114 | 1 | C721 | C031 | C721 | 2002 | TOYOTA | PRIUS | HYBRID SEDAN | 60120 | HYBRID | CLARK | 2001-10-23 | 2001-11-07 | 2001-11-09 |  |  | A | A |  | Right of Way Las Vegas | Las Vegas | District 1 | Sedan | No | 2 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes |  |  | Full Project | Pre-Pilot | JT2BK12U220041735 | [5 empty] | 11/18/2022: Moving this vehicle to Full Project instead of unit number 233
1FTNX21F02EC20020 | 3119 | 3 | C721 | C101 | C721 | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 242742 | DIESEL | CLARK | 2001-07-30 | 2002-03-06 | 2002-03-06 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTNX21F02EC20020 |  |  | 11.21.2022 | 11.21.2022 | 11.21.2022
1FTSF30F33EA66434 | 3121 | 6 | C721 | C145 | C721 | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | 150777 | DIESEL | CLARK | 2002-08-28 | 2002-09-25 | 2002-12-04 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSF30F33EA66434 |  | Yes
1FDAF56F22EB70700 | 3122 | 11F | C720 | C102 | C720 | 2002 | FORD | F-550 | SHOP SERVICE TRUCK W/CRANE | 274743 | DIESEL | CLARK | 2002-04-22 | 2002-05-03 | 2002-05-10 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46F42EB70704 | 3124 | 11E | C721 | C124 | C721 | 2002 | FORD | F-450 | REBUILD DUMP TRUCK | 111486 | BIO DIESEL | CLARK | 2001-11-15 | 2002-05-14 | 2014-11-10 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAXT02H546739 | 3125 | 13H | C721 | C121 | C721 | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | 204603 | DIESEL | CLARK | 2001-11-16 | 2002-05-29 | 2002-07-01 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 8 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAXT12H549729 | 3126 | 13 | C720 | C127 | C720 | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | 155956 | DIESEL | CLARK | 2002-08-28 | 2003-01-23 | 2003-02-05 |  |  | A | A |  | Searchlight Maintenance Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | REVERSABLE PLOW,SANDER,WATERTANK | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT92H546738 | 3127 | 13H | C720 | C154 | C720 | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | 219433 | DIESEL | CLARK | 2001-11-16 | 2002-05-29 | 2002-06-11 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 8 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTGGAXT72H546737 | 3128 | 13H | C720 | C159 | C720 | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | 200913 | DIESEL | CLARK | 2001-11-16 | 2002-05-29 | 2002-06-11 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 8 | J1939 | [5 empty] | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1HTGGAXT83H549731 | 3129 | 13S | C721 | C151 | C721 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 111482 | DIESEL | CLARK | 2002-05-31 | 2002-08-28 | 2002-10-01 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV52DJ77555 | 3132 | 24 | C720 | C159 | C720 | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | 100980 | DIESEL | CLARK | 2002-05-17 | 2002-07-31 | 2002-08-09 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV32DJ77604 | 3133 | 24 | C720 | C159 | C720 | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | 96241 | DIESEL | CLARK | 2002-07-03 | 2002-07-31 | 2002-10-01 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FVAB3BV92DJ77543 | 3134 | 24 | C720 | C154 | C720 | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | 105198 | DIESEL | CLARK | 2002-05-17 | 2002-07-31 | 2002-08-09 |  |  | A | A |  | Las Vegas Maintenance Crew 5 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
49HAADBV72DK01504 | 3135 | 24 | C720 | C159 | C720 | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | 90535 | DIESEL | CLARK | 2002-07-03 | 2002-08-15 | 2002-08-26 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
49HAADBV52DK01503 | 3136 | 24 | C720 | C159 | C720 | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | 92316 | DIESEL | CLARK | 2002-07-03 | 2002-08-15 | 2002-09-05 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
49HAADBV92DK01505 | 3137 | 24 | C720 | C159 | C720 | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | 98943 | DIESEL | CLARK | 2002-07-03 | 2002-08-15 | 2002-09-05 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FDAF57F22EB79654 | 3138 | 11A | C723 | C723 | C723 | 2002 | FORD | F-550 | AERIAL TRUCK | 242328 | DIESEL | ELKO | 2001-12-05 | 2002-04-16 | 2002-05-10 |  |  | A | A |  | Elko District Repair Shop | Elko | District 3 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FDAF57F22EB79654 |  |  |  |  | 11.30.2022
1HTMPAFL63H570338 | 3149 | 11 | C720 | C142 | C720 | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | 59087 | DIESEL | CLARK | 2002-07-16 | 2002-07-29 | 2003-06-23 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTMPAFL83H570339 | 3150 | 11 | C720 | C142 | C720 | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | 62292 | DIESEL | CLARK | 2002-07-16 | 2002-07-29 | 2003-06-23 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1GKDT13S522399284 | 3151 | 01A | C721 | C721 | C721 | 2002 | GMC | ENVOY | AWD SUV | 86426 | UNLEADED | CLARK | 2002-05-01 | 2002-05-07 | 2002-05-07 |  |  | A | A |  | Las Vegas District Repair Shop | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1GKDT13S522399284 |  |  |  |  | 11.22.2022
1FTSX31F43EA05752 | 3158 | 6 | C767 | C255 | C767 | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | 204863 | DIESEL | WASHOE | 2002-09-11 | 2002-09-25 | 2003-01-07 |  |  | A | A |  | Reno Bridge Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1GDM7C1C82J513674 | 3169 | 24 | C722 | C270 | C722 | 2003 | GMC | T7500 | GMC T7500 W/WAYNE SWEEPER | 57211 | DIESEL | CARSON CITY | 2003-01-22 | 2003-03-04 | 2003-03-25 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1GDM7C1C32J513534 | 3172 | 24 | C722 | C270 | C722 | 2002 | GMC | T7500 | WAYNE WARRIOR SWEEPER | 94579 | DIESEL | CARSON CITY | 2003-01-22 | 2003-03-04 | 2003-03-25 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
#N/A | 3180 | 3 | C721 | C153 | #N/A | 2004 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 241917 | BIO DIESEL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | A | #N/A | Deleted - Nov 2022 | Las Vegas Maintenance Crew 4 | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Deleted |  | #N/A
1FDXF46P05EA24510 | 3181 | 11F | C721 | C113 | C721 | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | 140572 | BIO DIESEL | CLARK | 2003-07-02 | 2004-11-30 | 2005-02-12 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF47P15EA24515 | 3182 | 11F | C720 | C102 | C720 | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 BIO-DIESEL | 151395 | BIO DIESEL | CLARK | 2003-07-02 | 2004-11-30 | 2005-01-12 |  |  | A | A |  | Las Vegas Facilities Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46P35EA24520 | 3183 | 11H | C721 | C113 | C721 | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | 89624 | BIO DIESEL | CLARK | 2003-07-02 | 2004-11-02 | 2004-12-13 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46P15EA24516 | 3184 | 11E | C721 | C158 | C721 | 2005 | FORD | F-450 | DUMP TRUCK W/ARROWBOARD BIO-DSL | 272278 | BIO DIESEL | CLARK | 2003-07-02 | 2004-11-16 | 2004-12-15 | MONARCH |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDAF56P25EA24505 | 3185 | 11A | C721 | C113 | C721 | 2005 | FORD | F-550 | AERIAL TRUCK W/ARTICULATING DEVICE | 74484 | BIO DIESEL | CLARK | 2003-07-02 | 2005-04-12 | 2005-05-27 |  |  | A | A |  | Las Vegas Highway Lighting Crew | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46P24ED93108 | 3186 | 11D | C721 | C124 | C721 | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | 195054 | BIO DIESEL | CLARK | 2003-07-01 | 2004-11-23 | 2005-02-14 |  |  | A | A |  | Glendale Maintenance Crew | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPAL09X17D653136 | 3187 | 13 | C725 | C175 | C725 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 232728 | DIESEL | NYE | 2003-07-01 | 2006-09-29 | 2006-10-17 |  |  | A | A |  | Goldfield Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW ONE WAY,2012 HENKE WING PLOW | Telematics Device | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1V9PT213X31090007 | 3188 | 20 | C721 | C158 | C721 | 2004 | VECTOR | 58055VD | T/M CULVERT CLEANER | 629 | DIESEL | CLARK | 2003-07-02 | 2004-07-28 | 2004-09-21 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT26J335418 | 3189 | 25 | C721 | C158 | C721 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | 166614 | DIESEL | CLARK | 2003-07-01 | 2006-07-11 | 2006-07-24 |  |  | A | A |  | Las Vegas Storm Water Management | Las Vegas | District 1 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX46P25EA24523 | 3192 | 11E | C767 | C245 | C767 | 2005 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 144090 | BIO DIESEL | WASHOE | 2003-07-02 | 2004-10-26 | 2005-02-25 | MONARCH |  | A | A |  | Reno Landscape Crew 1 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2019 SNOWDOG SNOW PLOW 9',2019 SALTDOG SAND SPREADER 2.0 CU YD | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXW47P75EA25054 | 3193 | 11H | C767 | C243 | C767 | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | 114630 | BIO DIESEL | WASHOE | 2003-07-02 | 2004-11-12 | 2005-01-11 |  |  | A | A |  | #N/A | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
2FTPX18Z34CA81772 | 3194 | 5 | C727 | C727 | C727 | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 70844 | RFG | CARSON CITY | 2003-11-06 | 2004-06-18 | 2004-07-07 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX46P95EA24521 | 3196 | 11H | C722 | C227 | C722 | 2005 | FORD | F-450 | FLATRACK TRUCK | 299685 | DIESEL | DOUGLAS | 2003-07-02 | 2004-12-10 | 2005-04-20 |  |  | A | A |  | Gardnerville Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXX46P05EA24522 | 3197 | 11H | C722 | C271 | C722 | 2005 | FORD | F-450 | 1 TON FLATRACK TRUCK | 223836 | DIESEL | CARSON CITY | 2003-07-02 | 2004-11-02 | 2004-12-13 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1NPAL09X97D652588 | 3198 | 13 | C722 | C235 | C722 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 194420 | DIESEL | LYON | 2003-07-01 | 2006-10-19 | 2006-10-19 | PARKER | PARKER | A | A |  | Wellington Maintenance Crew | Carson City | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A
1NPAL09X77D652587 | 3199 | 13 | C767 | C251 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 133444 | DIESEL | WASHOE | 2003-07-01 | 2006-10-12 | 2006-10-25 | PARKER | PARKER | A | A |  | Reno Maintenance Crew 2 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1NPAL09X57D652586 | 3200 | 13 | C767 | C241 | C767 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | 166837 | DIESEL | WASHOE | 2003-07-01 | 2006-10-05 | 2006-10-18 | PARKER | PARKER | A | A |  | Reno Striping Crew 2 | Reno | District 2 |  | Yes Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Yes |  | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes | Yes |  | Pilot |  | #N/A
1XPFD49X34D832970 | 3201 | 14 | C728 | C280 | C728 | 2004 | PETERBILT | 378 | TRUCK TRACTOR | 149026 | DIESEL | CHURCHILL | 2003-07-01 | 2004-02-06 | 2004-05-24 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 9 | J1939 | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1HTWYSBT85J033323 | 3202 | 20 | C722 | C271 | C722 | 2004 | INTL | 7600 6X4 | CULVERT CLEANER | 30172 | DIESEL | CARSON CITY | 2003-07-01 | 2004-09-20 | 2005-03-31 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 6 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTXRSBT96J341698 | 3203 | 25 | C728 | C280 | C728 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | 68936 | DIESEL | CHURCHILL | 2003-07-01 | 2006-04-17 | 2006-05-16 |  |  | A | A |  | Fallon Maintenance Crew 1 | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT36J341695 | 3204 | 25 | C767 | C225 | C767 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | 86297 | DIESEL | LYON | 2003-07-01 | 2006-05-10 | 2006-05-16 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT76J341697 | 3205 | 25 | C722 | C270 | C722 | 2006 | INTL | 5900I | TRUCK , W/WATER TANK | 54886 | DIESEL | CARSON CITY | 2003-07-01 | 2006-07-11 | 2006-08-17 |  |  | A | A |  | Carson City Maintenance Crew 1 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT46J309029 | 3206 | 25 | C728 | C283 | C728 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | 84671 | DIESEL | PERSHING | 2003-07-01 | 2006-09-18 | 2006-09-29 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
3FRNF65W96V304872 | 3227 | 11H | C722 | C271 | C722 | 2006 | FORD | F-650 | FLATRACK TRUCK | 60965 | DIESEL | CARSON CITY | 2004-07-01 | 2006-08-03 | 2007-02-12 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 5 | OBDII | [5 empty] | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3FRNX65W36V370220 | 3228 | 11H | C728 | C283 | C728 | 2006 | FORD | F-650 | FLATRACK TRUCK | 102518 | DIESEL | PERSHING | 2004-07-01 | 2006-11-16 | 2007-02-14 |  |  | A | A |  | Lovelock Maintenance Crew | Fallon | District 2 |  | No | 5 | OBDII | [5 empty] | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3FRNX65W56V370221 | 3229 | 11H | C767 | C225 | C767 | 2006 | FORD | F-650 | FLATRACK TRUCK | 80470 | DIESEL | LYON | 2004-07-01 | 2006-08-01 | 2007-01-03 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | [5 empty] | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
3FRNX65W76V370219 | 3230 | 11H | C728 | C281 | C728 | 2006 | FORD | F-650 | FLATRACK TRUCK | 59677 | DIESEL | CHURCHILL | 2004-07-01 | 2006-08-03 | 2007-05-26 |  |  | A | A |  | Fallon Maintenance Crew 2 | Fallon | District 2 |  | No | 5 | OBDII | [5 empty] | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXX47P66EB73131 | 3231 | 11E | C767 | C225 | C767 | 2006 | FORD | F-450 | DUMP TRUCK 4X4 | 245478 | DIESEL | LYON | 2004-07-01 | 2006-06-21 | 2006-09-06 |  |  | A | A |  | Fernley Maintenance Crew | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2 YARD SANDER,SNOW PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXX47P86EB73132 | 3232 | 11E | C767 | C253 | C767 | 2006 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | 276719 | BIO DIESEL | WASHOE | 2004-07-01 | 2006-06-06 | 2006-09-06 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXX47P16EB73134 | 3233 | 11F | C722 | C272 | C722 | 2005 | FORD | F-450 | SERVICE TRUCK | 285572 | DIESEL | CARSON CITY | 2004-07-01 | 2006-02-01 | 2006-02-07 |  |  | A | A |  | Carson City Maintenance Crew 3 | Carson City | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1HTXRSBT26J309031 | 3234 | 25 | C722 | C271 | C722 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | 53826 | DIESEL | CARSON CITY | 2004-07-01 | 2006-09-18 | 2006-09-29 |  |  | A | A |  | Carson City Maintenance Crew 2 | Carson City | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT06J309027 | 3235 | 25 | C728 | C237 | C728 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | 39598 | DIESEL | MINERAL | 2004-07-01 | 2006-10-19 | 2006-10-19 |  |  | A | A |  | Hawthrone Maintenance Crew | Fallon | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1HTXRSBT26J309028 | 3236 | 25 | C767 | C250 | C767 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | 42172 | DIESEL | WASHOE | 2004-07-01 | 2006-10-19 | 2006-10-19 |  |  | A | A |  | Reno Maintenance Crew 1 | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  | Pump on/off sensor |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P36EC83506 | 3248 | 3 | C721 | C902 | C721 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 107250 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-01 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P56EC83507 | 3249 | 3 | C720 | C126 | C720 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 169330 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-01 |  |  | A | A |  | Mountain Springs Maintenance Crew | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTRF12256NB18521 | 3250 | 5 | C727 | C050 | C727 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 115232 | UNLEADED | CARSON CITY | 2005-07-01 | 2006-04-12 | 2006-05-15 |  |  | A | A |  | Maintenance and Asset Mgmt | Carson City | District 2 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20PX6EC83504 | 3252 | 3 | C720 | C152 | C720 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 158542 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-01 |  |  | A | A |  | Las Vegas Maintenance Crew 3 | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot |  | #N/A
1FTSF20P76EC83508 | 3254 | 3 | C721 | C145 | C721 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 173055 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-03 |  |  | A | A |  | Las Vegas Landscape Crew 1 | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTSF20P76EC83508 |  |  |  |  | 11.22.2022
1FTWF31P26ED02293 | 3256 | 6 | C721 | C021 | C721 | 2006 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | 75436 | BIO DIESEL | CLARK | 2005-07-01 | 2006-04-05 | 2006-05-01 |  |  | A | A |  | Materials Las Vegas Lab | Las Vegas | District 1 |  | No | 5 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTWF31P26ED02293 |  | Yes |  | 11.21.2022 | 11.21.2022
1FTSX21586ED02299 | 3257 | 3 | C727 | A073 | C727 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK | 39940 | UNLEADED | CARSON CITY | 2005-07-01 | 2006-04-19 | 2006-06-01 |  |  | A | A |  | Building & Grounds | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor |  |  |  |  | SPREADER BED MOUNT,SNOW V PLOW 4 WAY, | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FTSF20P56EC83510 | 3259 | 3 | C721 | C902 | C721 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 188216 | DIESEL | NYE | 2005-07-07 | 2006-03-03 | 2006-05-01 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P96EC83509 | 3260 | 3 | C767 | C767 | C767 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 192228 | BIO DIESEL | CLARK | 2005-07-01 | 2006-03-07 | 2006-05-01 |  |  | A | A |  | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P96EC83512 | 3262 | 3 | C721 | C926 | C721 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 139216 | BIO DIESEL | CLARK | 2005-07-07 | 2006-03-03 | 2006-05-01 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P46EC83515 | 3264 | 3 | C767 | C910 | C767 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 120340 | BIO DIESEL | WASHOE | 2005-07-07 | 2006-03-03 | 2006-04-10 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXF46R08EC00946 | 3265 | 11H | C720 | C142 | C720 | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | 191126 | BIO DIESEL | CLARK | 2005-11-02 | 2007-09-28 | 2007-10-09 |  |  | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot |  | #N/A |  |  | 11.21.2022
1HTWEAAN27J477970 | 3266 | 11 | C721 | C121 | C721 | 2007 | INTL | 7400 | WEED SPRAYER TRUCK | 22815 | DIESEL | CLARK | 2005-07-01 | 2007-05-01 | 2007-05-31 |  |  | A | A |  | Las Vegas Yard Stockpile Control | Las Vegas | District 1 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
5KKHAEDE17PX82330 | 3269 | 13 | C720 | C142 | C720 | 2007 | WESTERN ST | 4900FA | DUMP TRUCK W/SIDE DUMP BODY | 135896 | DIESEL | CLARK | 2005-07-01 | 2006-08-02 | 2007-04-18 | PARKER | PARKER | A | A |  | Las Vegas Striping Crew 3 | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | Parker Iqan |  |  |  | 2020 REBUILD -ATTENUATOR VEH MNT,2020 SAFE-STOP ATTENUATOR | Telematics Device | Yes |  | Attenuator Up Down Sensor | Yes - Forward and Rearward | Yes | Yes |  | Full Project |  | #N/A
1HTMPAFLX6H346719 | 3270 | 11 | C720 | C130 | C720 | 2006 | INTL | 4200 | BUTTON TRUCK W/UTILITY BODY | 97939 | DIESEL | CLARK | 2005-07-05 | 2006-03-13 | 2006-09-05 |  |  | A | A |  | South Las Vegas Yard and Stockpile Control | Las Vegas | District 1 |  | No | 5 | J1939 | [5 empty] | ARROW BOARD | Telematics Device |  |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1FTRF12236NB18520 | 3274 | 5 | C723 | C912 | C723 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | 177022 | UNLEADED | ELKO | 2005-07-01 | 2006-04-13 | 2006-05-25 |  |  | A | A |  | Construction Crew Elko | Elko | District 3 | ½ Ton Pickups | No | 3 | OBDII | [6 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FTRF12236NB18520 |  |  |  |  | 11.28.2022
1FTSX21566ED02298 | 3275 | 3 | C723 | C040 | C723 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 97794 | UNLEADED | ELKO | 2005-07-01 | 2006-04-13 | 2006-05-25 |  |  | A | A |  | Construction Administration | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
49HAADBV36DW46943 | 3294 | 24 | C767 | C234 | C767 | 2006 | FREIGHTLNR | SC-8000 | SELF PROPELLED P/U BROOM | 51020 | DIESEL | STOREY | 2006-06-07 | 2006-07-13 | 2007-01-19 |  |  | A | A |  | Virginia City Maintenance Crew | Reno | District 2 |  | No | 5 | J1939 | [6 empty] | Telematics Device |  |  | Broom Up Down Sensor, Hopper full indication |  | Yes | Yes |  | Full Project |  | #N/A
1FTSW21P86ED82403 | 3295 | 3 | C727 | C056 | C727 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 186628 | DIESEL | CARSON CITY | 2006-06-15 | 2006-07-10 | 2006-07-31 |  |  | A | A |  | Architectural | Carson City | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P47EB44390 | 3297 | 3 | C721 | C926 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 86618 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-16 | 2007-02-13 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FMEU73E97UA97417 | 3298 | 01A | C721 | C101 | C721 | 2007 | FORD | EXPLORER | SUV | 94578 | UNLEADED | CLARK | 2006-07-01 | 2007-01-31 | 2007-03-14 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMEU73E97UA97417 |  |  |  |  | 11.23.2022
1FMEU73E07UA97418 | 3299 | 01A | C767 | C767 | C721 | 2007 | FORD | EXPLORER | SUV | 82304 | RFG | WASHOE | 2006-10-12 | 2007-02-02 | 2007-03-28 |  |  | D | A |  | Equipment Shop | Reno | District 2 | AWD Passenger Vehicles | No | 2 | OBDII |  |  | GO9 |  |  |  | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1FMEU73E07UA97418
1FMEU73E27UA97419 | 3301 | 01A | C721 | C101 | C721 | 2007 | FORD | EXPLORER | SUV 4X4 | 56258 | UNLEADED | CLARK | 2006-07-01 | 2007-01-31 | 2007-02-14 |  |  | A | A |  | Las Vegas District Administration | Las Vegas | District 1 | AWD Passenger Vehicles | No | 2 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Pre-Pilot | Pre-Pilot | 1FMEU73E27UA97419 |  |  |  |  | 11.22.2022
1FTSF20P87EB44389 | 3302 | 3 | C767 | C767 | C720 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 196110 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-17 | 2007-03-27 |  |  | A | A |  | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20PX7EB44393 | 3303 | 3 | C767 | C767 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 195531 | DIESEL | NYE | 2006-07-01 | 2007-01-31 | 2007-05-17 |  |  | A | A |  | Equipment Shop | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P87EB44392 | 3304 | 3 | C721 | C902 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 180049 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-12 | 2007-02-14 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF20P67EB44391 | 3305 | 3 | C721 | C916 | C721 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 101640 | BIO DIESEL | CLARK | 2006-07-01 | 2007-01-12 | 2007-03-21 |  |  | A | A |  | Contruction Crew Las Vegas | Las Vegas | District 1 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1G1ZS57F57F286310 | 3306 | 1 | C727 | C727 | C727 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | 114820 | UNLEADED | CARSON CITY | 2007-03-20 | 2007-06-06 | 2007-06-13 |  |  | A | A |  | Carson City Motor Pool | Carson City | District 2 | Sedan | No | 2 | OBDII |  |  |  |  | Yes |  | Telematics Device |  |  |  |  | Yes |  |  | Full Project |  | #N/A
1GKFH154981182831 | 3308 | 4 | C727 | A067 | C727 | 2008 | GMC | SAVANA | CARGO VAN | 108697 | UNLEADED | CARSON CITY | 2007-11-20 | 2008-03-06 | 2008-08-27 |  |  | A | A |  | Information Services | Carson City | District 2 | Vans | No | 3 | OBDII | [6 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF21R48ED09226 | 3310 | 3 | C722 | C911 | C722 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | 118101 | BIO DIESEL | WASHOE | 2007-09-19 | 2008-03-06 | 2008-04-08 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF21R68ED09227 | 3311 | 3 | C722 | C907 | C722 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 122768 | DIESEL | CARSON CITY | 2007-09-19 | 2008-02-07 | 2008-04-08 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FTSF21R88ED09228 | 3312 | 3 | C722 | C911 | C722 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | 132623 | DIESEL | CARSON CITY | 2007-09-17 | 2008-02-26 | 2008-04-08 |  |  | A | A |  | Construction Crew Reno | Reno | District 2 | 3/4 Ton Pickups | No | 3 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1FDXW47R48ED51996 | 3313 | 11J | C767 | C253 | C767 | 2008 | FORD | F-450 | UTILITY TRUCK 4X4 BIO-DIESEL | 158723 | BIO DIESEL | WASHOE | 2007-09-20 | 2008-06-05 | 2008-10-16 |  |  | A | A |  | Reno Maintenance Crew 4 | Reno | District 2 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A
1FDXF46R78ED58118 | 3314 | 11E | C721 | C151 | C721 | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | 168524 | BIO DIESEL | CLARK | 2007-09-24 | 2008-04-21 | 2008-05-16 |  |  | A | A |  | Las Vegas Maintenance Crew 2 | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor |  |  |  |  | 2012 HINKER C-PLOW | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Pre-Pilot |  | #N/A
1FDXF46R58EE13102 | 3315 | 11S | C721 | C155 | C721 | 2008 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | 148700 | BIO DIESEL | CLARK | 2007-09-24 | 2008-08-04 | 2008-09-02 |  |  | A | A |  | Las Vegas Bridge Maintenance | Las Vegas | District 1 |  | No | 5 | OBDII | Roadwatch Sensor | [5 empty] | Telematics Device | Yes |  | No |  | Yes | Yes | No Up Down Sensors Needed | Full Project |  | #N/A |  | Yes
1NPTL00X69D782207 | 3318 | 13 | C720 | C159 | C720 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | 98548 | DIESEL | CLARK | 2007-12-04 | 2008-07-15 | 2009-03-19 |  |  | A | A |  | Las Vegas Sweeping Crew | Las Vegas | District 1 |  | No Final | 8 | J1939 | Roadwatch Sensor | [5 empty] | Telematics Device |  |  |  |  | Yes | Yes |  | Full Project |  | #N/A
1NPTL00X89D782208 | 3319 | 13S | C767 | C242 | C767 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 77789 | DIESEL | WASHOE | 2007-12-04 | 2008-07-11 | 2009-06-30 |  |  | A | A |  | Reno Pavement Markings | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | SPRAYTRONIC DE-ICER,PLOW REVERSIBLE,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A
1NPTL00XX9D782209 | 3320 | 13S | C767 | C242 | C767 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 87956 | DIESEL | WASHOE | 2007-12-04 | 2008-07-15 | 2009-06-16 |  |  | A | A |  | Reno Pavement Markings | Reno | District 2 |  | No | 8 | J1939 | Roadwatch Sensor |  |  |  |  | PLOW REVERSIBLE,2003 SANDERS,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,WATER TANK, SWAPLOADER,PLOW | Telematics Device |  |  | Plow Up Down Sensor |  | Yes | Yes |  | Pilot |  | #N/A |  | Yes
1NPTL00X99D782220 | 3327 | 13S | C725 | C176 | C725 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | 148813 | DIESEL | MINERAL | 2006-07-01 | 2008-07-31 | 2009-06-15 |  |  | A | A |  | Mina Maintenance Crew | Tonopah | District 1 |  | Yes Final | 8 | J1939 | Roadwatch Sensor |  |  |  |  | HENKE ONEWAY PLOW,SANDER SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Yes |  | Plow Up Down Sensor | Yes | Yes | Yes |  | Full Project |  | #N/A

## UnitMaster - Phase Calculation
Installer Type (0=Geotab, 1=Gofleet) | [15 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 |  | 1 | [8 empty] | Tier 1 1 $ - Geotab only install $0 under NASPO Tier 2 2 $ 260.00 Tier 3 4 $ 440.00 Tier 4 6 $ 660.00 Tier 5 9 $ 990.00 Tier 6 12 $ 1,320.00 Tier 7 15 $ 1,650.00 Special Req. Full Imp. Hrs 83.5 Install Hours 86.5 $9,515.00 Assumptions Geotab is able to install all IOX devices Cameras possibly being done by Geotab - at Geotab Rate Notes GO installs at $0 IOX-WRKS as Naspo rate Tier package based on Cost Minus 1hr Go Install Cost Geotab hourly rate $100 - TBD Install Hours no RW/GO
Time Requirement (hrs) | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 |  | 0.75 |  | 0.75 |  | 0.75 |  | 0.75 |  | 1 |  | 1 |  | 1 |  | 0.75 |  |  |  | 0.5 | 0.5 |  | 2
Qty of Components (ea.) | [15 empty] | 205 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 0 | 188 | 188 | 188 | 0 | 0 | 73 | 370 |  | 516 | 20 | 350 |  |  | 70140
Rate | [22 empty] | L | J | L | J | L | J | L | J | L | J | L | J | L | J | L | J | L | [6 empty] | include for project planning | [5 empty] | 0 | 0
AUX TYPE | [22 empty] | AUX 1-4 - IOX-AUXM - AUX 5-7 - IOX-WRKS
Aux Channel (1-8) | [22 empty] | 4 |  | 7 |  | 6 |  | 5 |  | 1 |  | 2 |  | 3 |  | 4 |  | 8
[21 empty] | Cameras |  | Digital Sensors
Federal MCC | NDOT Class code | Year | Make | Model | Description | Existing OBDII/J1939 | Existing Roadwatch SS | Existing Parker/CIRUS/FORCE AMERICA/EPOKE | Controller Model | Existing Associations/Hardware | Telematic Device / Telematics device for Winter Operations needed | Sensors needed | Wi-Fi HotSpot needed | Cameras needed | Lightbar Needed | OBDII | J1939 (9 pin) | Direct Wiring (3 wire) | Winter Operations With J1939 (9 pin) | Wi-Fi HotSpot | Forward Cameras | Rear Cameras | Attenuator Up Down | Federal MCC | Wing Plow Up/Down Down | Federal MCC | Front Plow Up/Down | Federal MCC | Belly Plow Up Down | Federal MCC | Broom Up Down | Federal MCC | Hopper full indication | Federal MCC | Pump on/off | Federal MCC | Snow Blower Activation | Federal MCC | Light Bar Activation | AX 1 -4 | AX 5-8 | AUX Check | IOX - AUXM | IOX - WRKS | Pressure Switches | Roadwatch RS232 BLE (Integration) | Estimated Install Time (hrs) | Check | Estimated Install Time (hrs) Incl. Roadwatch (USE for Project Plan) | Geotab Install (hrs) | Gofleet Install (hrs) | Install Package Tier 1 | Install Package (Excluding Tier 1) | Installation Package Price (Tier 1 = $0) | Planned Phase | Actual Phase | Unit Number | Locations | Comments
2 | 01A | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1 | Carson City
2 | 01A | 2016 | FORD | EXPLORER | SUV 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2 | Las Vegas
2 | 1 | 2019 | CHEVROLET | MALIBU HYB | 2019 SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 3 | Las Vegas
2 | 01A | 2007 | GMC | ENVOY | GMC ENVOY SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 10 | Reno
2 | 01A | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 11 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 12 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 13 | Tonopah
2 | 01A | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 17 | Las Vegas
2 | 01A | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 18 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 20 | Tonopah
5 | 6 | 2016 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 22 | Tonopah
2 | 1 | 2001 | TOYOTA | PRIUS | HYBRID SEDAN 4 DOOR | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Pre-Pilot |  | 26 | Las Vegas
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | NA | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 29 | Las Vegas
2 | 1 | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 31 | Las Vegas
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 32 | Tonopah
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | ONE-WAY PLOW,2017 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 34 | Tonopah
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 37 | Carson City
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,ONE WAY PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 38 | Las Vegas
8 | 25 | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 39 | Las Vegas
2 | 1 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 43 | Las Vegas
2 | 1 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 50 | Carson City
2 | 1 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 52 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 53 | Reno
8 | 12 | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,HIGHSPEED 11' PLOW,SANDER 5 YD | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 696 | Reno
2 | 1 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 55 | Carson City
2 | 1 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 56 | Ely
2 | 1 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 57 | Las Vegas
2 | 1 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 58 | Reno
2 | 1 | 2021 | CHEVROLET | MALIBU | 2021 CHEVROLET MALIBU 4 DR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 59 | Winnemucca
8 | 12 | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 YRD SANDER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 680 | Reno
8 | 13 | 1989 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE WING PLOW,REVERSIBLE 11' SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 1474 | Reno
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 68 | Elko
3 | 5 | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 72 | Reno
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 82 | Reno
2 | 01A | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 84 | Ely
3 | 3 | 2017 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 88 | Ely
3 | 5 | 2001 | GMC | TC15903 | 1/2 TON PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 89 | Reno
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 91 | Wells
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 94 | Ely
3 | 5 | 2001 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 96 | Reno
2 | 01A | 1998 | GMC | JIMMY | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 99 | Reno
2 | 01A | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Pilot | Pre-Pilot | 100 | Las Vegas
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 101 | Las Vegas
8 | 25 | 1976 | PETERBILT | MD359 | TRACTOR TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 102 | Elko
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 104 | Winnemucca
2 | 01A | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Pilot | Pre-Pilot | 105 | Las Vegas
2 | 01A | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 106 | Las Vegas
2 | 01A | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot | 107 | Las Vegas
2 | 01A | 2022 | FORD | EXPLORER | 2022 FORD EXPLORER SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 108 | Reno
2 | 01A | 2021 | JEEP | CHEROKEE | 2021 JEEP GRAND CHEROKEE | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot | 109 | Elko
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 111 | Ely
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 113 | Elko
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 114 | Wells
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 115 | Reno
2 | 01A | 2005 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 116 | Reno
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 120 | Elko
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 121 | Wells
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 122 | Las Vegas
5 | 10 | 2001 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 136 | Reno
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 137 | Ely
3 | 5 | 2007 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 139 | Carson City
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 140 | Elko
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 141 | Elko
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 142 | Ely
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 143 | Elko
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 146 | Las Vegas
2 | 1 | 2008 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 148 | Reno
3 | 5 | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 151 | Las Vegas
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 152 | Reno
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 153 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 154 | Elko
2 | 01A | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 155 | Carson City
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 156 | Wells
5 | 11H | 2001 | FORD | F-450 | REBUILD FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 157 | Las Vegas
5 | 11H | 2001 | FORD | F-450 | FLAT RACK TRUCK | OBDII | Roadwatch Sensor |  |  | DEICING UNIT,325 GALLON DE-ICING UNIT | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 160 | Winnemucca
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 162 | Elko
5 | 11H | 2001 | FORD | F-450 | FLAT RACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 163 | Las Vegas
5 | 11A | 2001 | FREIGHTLNR | 25K GVW | AERIAL LIFT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 164 | Ely
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 166 | Wells
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 167 | Elko | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,REVERSIBLE PLOW,2018 HENKE NOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 170 | Elko | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | REVERSIBLE PLOW,8 CU YD HENDERSON,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 172 | Elko | Confirm number of plows "Existing Associations/Hardware"
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 174 | Carson City
2 | 1 | 1998 | FORD | ESCORT | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Pilot | Pre-Pilot | 185 | Las Vegas
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 186 | Carson City
5 | 11F | 2001 | FORD | F-350 | 4X4 SERVICE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 188 | Carson City
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 189 | Fallon
OFF ROAD / NA | 42 | 2020 | KODIAK | 1200 | 2020 KODIAK ROTARY BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 191 | Carson City
5 | 11J | 2001 | FORD | F-350 | 4X4 UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 192 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 193 | Reno
8 | 12 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE 11 FT REVERSABLE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 194 | Elko
8 | 12 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE,2001 SANDER 5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 196 | Elko
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 200 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 205 | Reno
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | J1939 | Roadwatch Sensor |  |  | PLOW,HEAVY DUTY PATROL WING,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 206 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 209 | Carson City
2 | 1 | 2018 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 210 | Las Vegas
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 214 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 216 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 217 | Reno
6 | 11B | 1991 | INTL | F2574 | TANDEM AXLE CRANE TRUCK REBUILD | J1939 |  |  |  | SPRATRONICS DE ICER | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 1821 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 219 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 221 | Carson City
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | WING PLOW,8 YD,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 223 | Winnemucca
5 | 11J | 2007 | FORD | F-450 | 4X4 UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 224 | Reno
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,SANDER 8 YD,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 226 | Tonopah
3 | 4 | 2018 | CHEVROLET | EXPRESS | 2018 CHEV EXP 1T 15 PASS VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 227 | Carson City
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 228 | Las Vegas
6 | 28 | 2001 | INTL | 2574 | 2001 REBUILD INTL F2574 DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 229 | Tonopah
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 230 | Carson City
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 231 | Elko
5 | 11H | 2007 | FREIGHTLNR | FLD120 | FLATRACK TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 232 | Carson City
5 | 11F | 2007 | FORD | F-550 | SERVICE TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 233 | Las Vegas
8 | 12 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 512 | Reno
OFF ROAD / NA | 42 | 2019 | KODIAK | CR1200S | ROTARY PLOW | J1939 |  |  |  |  | Telematics Device |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 235 | Reno
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK 7532,WING PLOW,HENKE 12' RIGHTHAND,2014 VARITECH AI-1850 BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 236 | Tonopah
5 | 11A | 2006 | GMC | SIERRA | SIGNSHOP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 237 | Tonopah
5 | 11E | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 238 | Carson City
5 | 11A | 2008 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 239 | Reno
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 240 | Reno
6 | 11B | 2007 | FREIGHTLNR | FDL120 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | ATTENUATOR W/VERTICAL LIFT ARROW BOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 241 | Las Vegas
OFF ROAD / NA | 42 | 2019 | KODIAK | CR1200S | 2019 KODIAK ROTARY PLOW | J1939 |  |  |  |  | Telematics Device |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 243 | Carson City
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1988 SANDER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 244 | Reno
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 245 | Carson City
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | ONE WAY PLOW,SANDER,DE-ICING SPRAYER,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 246 | Ely
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,FLINK 8 YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 248 | Elko
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 250 | Reno
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 251 | Las Vegas
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK 8 YD SANDER,JENSEN SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 254 | Fallon
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE 4422,FLINK 7511,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 256 | Tonopah
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 257 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 258 | Elko
3 | 4 | 2018 | CHEVROLET | EXPRESS | 2018 3/4 TON VAN 12 PASSENGER | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 259 | Carson City
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 260 | Elko
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 261 | Las Vegas
OFF ROAD / NA | 42 | 2019 | KODIAK | CR1200S | 2019 KODIAK 1200 SNOW BLOWER | J1939 |  |  |  |  | Telematics Device |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 262 | Reno
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE,FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 263 | Reno
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 264 | Carson City
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW WING,ONE WAY,8 YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 265 | Ely
8 | 13S | 2002 | INTL | 2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor |  |  | SANDER SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 266 | Las Vegas
6 | 15 | 2001 | INTL | F5000 | AWD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 267 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 268 | Las Vegas
2 | 1 | 1998 | FORD | ESCORT | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Deleted | Deleted | 269 | Las Vegas
5 | 24 | 2001 | WITTKE | WIZARD FC-70 | SELF PROPELLED ROAD BROOM | J1939 |  |  |  | BUCKET, 71 DITCH CLEANING | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 271 | Winnemucca
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 273 | Carson City
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 274 | Elko
2 | 01A | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 276 | Carson City
3 | 5 | 2018 | CHEVROLET | SILVERADO | 2018 1/2 TON CHEVY SILVERADO 1500 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 277 | Las Vegas
2 | 01A | 2016 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 278 | Carson City
8 | 12 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK SANDER,CLEDHILL PLOW MDL 20931 | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 514 | Reno
5 | 11E | 2007 | FORD | F-450 | 1 TON DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 281 | Las Vegas
5 | 11E | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 285 | Carson City
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 286 | Winnemucca
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 287 | Las Vegas
5 | 11E | 2007 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 288 | Las Vegas
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 CHEVY 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 289 | Las Vegas
5 | 11F | 2007 | FORD | F-350 | SERVICE TRUCK 4X4 | OBDII |  |  |  | 2018 REAR BUMPER CRANE | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 292 | Ely
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 293 | Tonopah
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 295 | Tonopah
8 | 13S | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | WATER TANK SWAPLOADER,PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,FLAT RACK, SWAPLOADER,2014 LITE READER 1230F-4,TRUCK MOUNTED ATTENUATOR | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 297 | Tonopah
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 298 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 299 | Las Vegas
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 300 | Las Vegas
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 301 | Winnemucca
8 | 13S | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 304 | Tonopah
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 305 | Carson City
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 309 | Fallon
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 310 | Tonopah
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 311 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 314 | Carson City
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 317 | Las Vegas
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 318 | Winnemucca
8 | 13S | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 319 | Las Vegas
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK W/4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 320 | Winnemucca
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 321 | Las Vegas
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 322 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 327 | Carson City | Confirm number of plows "Existing Associations/Hardware"
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2014 PROFILING SYSTEM | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 324 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 325 | Las Vegas
8 | 12 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Pilot |  | 784 | Reno
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 328 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 329 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 330 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 332 | Tonopah
8 | 12 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | ONE WAY PLOW,5 YARD SLIDE IN SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 794 | Reno
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 335 | Elko
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 336 | Elko
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,REVERSIBLE PLOW,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 593 | Elko | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,PLOW WING,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 340 | Ely
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 341 | Las Vegas
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 8 YD SANDER,PLOW,2006 HENKE PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 342 | Winnemucca
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 345 | Carson City
5 | 11J | 2016 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 346 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 347 | Las Vegas
5 | 11J | 2016 | FORD | F-550 | UTILITY TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 348 | Carson City
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 349 | Las Vegas
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 350 | Las Vegas
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 352 | Ely
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 366 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 367 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 368 | Tonopah
8 | 12 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,5 YRD FLINK MOD 10 LMC .5H | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 805 | Reno
5 | 76 | 2001 | FORD | E-350 | 1 TON VAN W/FALLING WEIGHT DEFLECT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 377 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot New | Pre-Pilot | 383 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 385 | Tonopah
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 386 | Las Vegas
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 387 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 389 | Reno
8 | 25 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 390 | Fallon
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 391 | Las Vegas
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot New |  | 392 | Las Vegas
6 | 11B | 1999 | INTL | F257A | CRANE TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 1135 | Reno
8 | 25 | 2007 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 394 | Carson City
8 | 25 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 395 | Fallon
8 | 25 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 396 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot New | Pre-Pilot | 399 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 400 | Las Vegas
2 | 1 | 2002 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 0 | 1 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 401 | Las Vegas
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 402 | Las Vegas
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 403 | Las Vegas
2 | 01A | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 404 | Elko
5 | 11E | 2016 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 405 | Tonopah
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 406 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 407 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 408 | Reno
6 | 20 | 2016 | PETERBILT | 567 | VACTOR 2100 CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 409 | Las Vegas
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 412 | Carson City
2 | 01A | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 415 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 417 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 420 | Elko
3 | 3 | 1998 | CHEVROLET | CC209 | 3/4 TON PICKUP TRUCK W/SVC BODY | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 422 | Carson City
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 423 | Las Vegas
3 | 4 | 1999 | GMC | TG3140 | 1 TON CARGO VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 425 | Reno
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 426 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 428 | Elko
3 | 5 | 2008 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 429 | Winnemucca
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 430 | Wells
3 | 3 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 431 | Reno
3 | 3 | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 436 | Winnemucca
3 | 4 | 1999 | CHEVROLET | CG21406 | 12 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 437 | Reno
6 | 77 | 1988 | MACK | MR688 | MACK STRIPER REBUILD | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 438 | Tonopah
5 | 6 | 2008 | FORD | F-350 | ONE TON PICKUP TRUCK W/4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 439 | Ely
3 | 4 | 2002 | GMC | SAVANA | PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 442 | Elko
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 443 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 444 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 450 | Reno
5 | 11E | 2016 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 451 | Reno
6 | 20 | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 452 | Tonopah
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 453 | Fallon
5 | 24 | 2017 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 456 | Reno
8 | 13H | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR TANDEM AXLE SIDE DUMP | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 458 | Las Vegas
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor |  | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 1 | 3 | Tier 1 | Tier 3 | 440 | Full Project |  | 461 | Tonopah
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 462 | Las Vegas
3 | 5 | 2002 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 464 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 466 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 474 | Reno
3 | 5 | 2002 | GMC | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 475 | Carson City
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 480 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 481 | Elko
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 482 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 485 | Elko
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 486 | Elko
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 489 | Elko
6 | 20 | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 490 | Elko
OFF ROAD / NA | 55B | 2006 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 493 | Winnemucca
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 494 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 495 | Carson City
5 | 11H | 2008 | FORD | F-450 | 1 TON FLATRACH TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 497 | Ely
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 498 | Las Vegas
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 502 | Reno
8 | 13 | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | TENCO 11FT REVERSIBLE PLOW,8 YARD FLINK SANDER,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 2778 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 504 | Reno
5 | 11J | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 505 | Las Vegas
5 | 11H | 2008 | FORD | F-650 | FLATRACK TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 507 | Reno
8 | 12 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 510 | Ely
8 | 13 | 1999 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE WING PLOW,1991 PLOW,1991 SANDER,TENCO 11 FT. REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 2779 | Reno
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE WING PLOW,TENCO,FLINK,SPRATRONICS | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 3028 | Reno
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor |  | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 1 | 3 | Tier 1 | Tier 3 | 440 | Full Project |  | 515 | Tonopah
8 | 12 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 516 | Winnemucca
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 519 | Reno
5 | 11H | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 525 | Tonopah
8 | 13 | 2001 | INTL | F2574 | TANDEM AXLE DUMP TRUCK/FRINK | J1939 | Roadwatch Sensor |  |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 218 | Reno
5 | 11S | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | 400 GAL SPRAY TANK/SLIDE-IN | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 531 | Las Vegas
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 532 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 533 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 534 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 535 | Las Vegas
6 | 11B | 1992 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  |  | 2014 LITEREADER 1230F-4 SIGN BOARD,2007 SCORPION TL-3TRUCK MNTD. ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 537 | Tonopah
5 | 11H | 1992 | INTL | 4700 | FLATRACK TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 538 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 539 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 540 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 541 | Carson City
5 | 11H | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 542 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 543 | Carson City
5 | 11S | 2002 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 545 | Las Vegas
5 | 11H | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 547 | Winnemucca
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 548 | Las Vegas
2 | 1 | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #REF! | 2 | 1 | 1 | Tier 1 | Tier 2 | 260 | Full Project |  | 550 | Reno
8 | 13 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,HENKE,HENKE WING PLOW,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 3.75 | #REF! | 5.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Pilot |  | 611 | Reno | Confirm number of plows "Existing Associations/Hardware"
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 553 | Carson City
5 | 11F | 2016 | FORD | F-350 | SHOP SERVICE TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 556 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 557 | Las Vegas
5 | 11E | 2002 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 558 | Fallon
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2020 HENKE AUGER CARTRIDGE SANDER,2020 REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 559 | Fallon
5 | 11H | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 560 | Tonopah
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 561 | Elko
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 562 | Tonopah
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 564 | Tonopah
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 2018 REVERSIBLE PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 956 | Carson City | Confirm number of plows "Existing Associations/Hardware"
5 | 11S | 2002 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOKLIFT | OBDII | Roadwatch Sensor |  |  | ARROW BOARD, T/M,DUMPBED SL95 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 567 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 568 | Tonopah
5 | 11E | 2002 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 569 | Reno
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 570 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 571 | Reno
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | PLOW REVERSIBLE ALASKAN,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 575 | Elko
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 577 | Las Vegas
8 | 12 | 2002 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,5 CU YD SANDER W/PRE WET & GUARD,FRONT BROOM ATTACHMENT | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 580 | Ely
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 581 | Tonopah
8 | 12 | 2002 | INTL | 5500 | SINGLE AXLE DUMP TRUCK AWD | J1939 | Roadwatch Sensor |  |  | HENKE PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 582 | Reno
8 | 13 | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 583 | Wells
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 584 | Elko
8 | 13 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE,FLINK SANDER,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 3.75 | #REF! | 5.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 585 | Tonopah
8 | 13 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE REVERSIBLE,PLOW WING,FLINK SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 587 | Winnemucca
8 | 13 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 12' ONE WAY HENKE,FLINK Model #LMC5H15-NVS4E01 | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 600 | Reno
5 | 11H | 1992 | GMC | TC7H0 | FLATRACK TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 589 | Reno
8 | 13 | 2002 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REV PLOW REBUILD,1850 GALLON SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 590 | Tonopah
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 592 | Las Vegas
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD,SLIDE IN PRAYER,PLOW,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 962 | Fallon | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE PLOW,8 YRD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 594 | Fallon
3 | 5 | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pre-Pilot |  | 596 | Elko
5 | 11H | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 598 | Tonopah
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 599 | Las Vegas
OFF ROAD / NA | 42 | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Pilot |  | 726 | Reno
5 | 11H | 1992 | INTL | 4700 | FLATRACK TRUCK | J1939 |  |  |  | 2021 LITEREADER ARROW BOARD | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 601 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 603 | Las Vegas
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 604 | Carson City
5 | 11H | 2021 | FORD | F-450 | 2021 FORD F-450 4X4 CREW CAB FLATRACK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 605 | Tonopah
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 606 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 608 | Las Vegas
6 | 77 | 2006 | PETERBILT | 320 | LINE STRIPER TRUCK | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 609 | Las Vegas
2 | 01A | 2006 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 610 | Carson City
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 986 | Carson City | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE,SANDER FLINK W PREWET | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 612 | Reno
8 | 13 | 2003 | MACK | RD6885 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 588 | Reno
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2020 HENKE SINGLE SANDER,2020 HENKE ONE WAY PLOW,2020 HENKE WING PLAY | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 616 | Ely
8 | 25 | 2002 | INTL | F2574 | TANDEM AXLE WATER TRUCK REBUILD | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 617 | Tonopah
8 | 13S | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK HOOK LIFT | J1939 | Roadwatch Sensor |  |  | HENKE REVERSIBLE,SANDER,DUMP BED | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 618 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 620 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot | 621 | Las Vegas
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2020 HENKE SINGLE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 623 | Winnemucca
8 | 13 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | ONE WAY PLOW,FLINK,PLOW WING,BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 625 | Tonopah
8 | 13 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK 8 YD W/PRE WET SYSTEM,PLOW,WING PLOW,VARITECH A1-1750-GAS-1LB | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 626 | Tonopah
8 | 13 | 2002 | MACK | RD688S | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 12' ONE WAY PLOW,8 YRD FLINK SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 629 | Fallon
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 631 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 632 | Las Vegas
8 | 13 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK 8 CU YD SANDER,WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 633 | Ely
8 | 13 | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 8 CU YD,HENKE REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 634 | Winnemucca
5 | 11S | 2021 | FORD | F-450 | 2021 FORD 40450 1 TON DUMPBED SWAPLOADER | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 636 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 637 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 641 | Carson City
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 642 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 644 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 645 | Reno
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 646 | Las Vegas
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 648 | Reno
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 650 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1342 | Winnemucca | Confirm number of plows "Existing Associations/Hardware"
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | ARROW BOARD, T/M/LITEREADER | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 653 | Las Vegas
5 | 11E | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 1 TON DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 654 | Las Vegas
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 656 | Carson City
3 | 5 | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 659 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 660 | Elko
5 | 24 | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 662 | Las Vegas
5 | 11E | 2008 | FORD | F-250 | DUMP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 664 | Winnemucca
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 665 | Winnemucca
5 | 11J | 2008 | FORD | F-450 | UTILITY TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 667 | Las Vegas
5 | 11F | 2009 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DSL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 668 | Reno
5 | 11F | 2008 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 669 | Carson City
8 | 25 | 2020 | WESTERN ST | 4900 | 2020 WESTERN STAR 4900FS WATER TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 670 | Las Vegas
8 | 12 | 2009 | PETERBILT | 367 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | BONNELL SANDER 5 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 671 | Elko
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 672 | Elko
5 | 24 | 2002 | ELGIN | EAGLE | ELGIN EAGLE S/P SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 673 | Las Vegas
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | 5 CU YD SANDER,PLOW WING,PLOW REVERSIBLE ALASKAN,5 CU YD FLINK SANDER HOPPER-TYPE W,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 675 | Wells
8 | 25 | 2020 | WESTERN ST | 4900 | 2020 WESTERN STAR 4900SF WATER TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 676 | Las Vegas
8 | 12 | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SCHMIDT 12' PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 677 | Tonopah
8 | 12 | 1987 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SWENSON SANDER,11' ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 678 | Tonopah
8 | 13S | 2017 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER 8 CUBIC YARDS,WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 679 | Elko
6 | 77 | 2003 | MACK | MR688S | LINE STRIPER 700 GALLON | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pilot |  | 1089 | Reno
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | PLOW WING,SANDER 8 YARD,2000 PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 682 | Elko
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 684 | Elko
8 | 13S | 2009 | PETERBILT | 367 | TANDEM AXLE HYDRAULICS W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | LARSON 5 CU YD,SANDER,REVERSIBLE PLOW,FLATRACK SWAPLOADER,2006 WORKMAN WATER TANK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 685 | Winnemucca
7 | 83 | 2003 | PETERBILT | 357 | UNDERBRIDGE INSPECTION TRUCK | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pilot |  | 1100 | Carson City
8 | 12 | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE PLOW,SANDER,FLINK 8 CU YD SANDER,SANDER 8 YARD,PLOW WING,SALT BRINE TANK | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 691 | Tonopah
8 | 12 | 1986 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENDERSON SANDER,1986 PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 693 | Tonopah
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 694 | Carson City
8 | 25 | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 695 | Las Vegas
9 | 14 | 2004 | PETERBILT | 378 | TRUCK TRACTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 1388 | Reno
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 698 | Las Vegas
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Deleted | Deleted | 699 | Las Vegas
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 702 | Fallon
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 706 | Wells
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 707 | Reno
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 711 | Las Vegas
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 714 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 716 | Las Vegas
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 717 | Fallon
6 | 11B | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 1274 | Reno
OFF ROAD / NA | 42 | 2002 | KODIAK | CR35S | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 730 | Carson City
2 | 1 | 2016 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 736 | Las Vegas
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 739 | Fallon
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 740 | Reno
8 | 13S | 2009 | PETERBILT | 367 | TANDEM AXLE DUMB TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 742 | Las Vegas
8 | 13S | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | SWAPLOADER SANDER,ONE WAY PLOW,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 743 | Tonopah
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 748 | Reno
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 749 | Fallon
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 752 | Wells
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 753 | Reno
3 | 5 | 2016 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 755 | Reno
8 | 12 | 1994 | INTL | F2574 | REBUILD SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 12' RIGHT HAND PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 757 | Fallon
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 761 | Carson City
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW WING,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 763 | Carson City
8 | 12 | 1994 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,TENCO,5 YRD HENDERSON SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 764 | Fallon
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 769 | Reno
3 | 4 | 2017 | CHEVROLET | EXPRESS | 15 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 771 | Las Vegas
6 | 77 | 2002 | EZ LINER | 320 | FREEWAY LINE STRIPER | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 772 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 773 | Reno
3 | 4 | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 774 | Carson City
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 776 | Fallon
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 778 | Las Vegas
8 | 13 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 779 | Tonopah
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE CAB & CHASSIS | J1939 | Roadwatch Sensor |  |  | SANDER 8 YARD,PLOW WING,PLOW REVERSIBLE ALASKAN | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 3.75 | #REF! | 5.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 780 | Ely
5 | 11S | 2021 | FORD | F-450 | 2021 F-450 1 TON SWPLOADER DUMP BODY | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 781 | Las Vegas
5 | 11S | 2021 | FORD | F-450 | 2021 F-450 1 TON SWPLOADER DUMP BODY | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 782 | Las Vegas
9 | 14 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 783 | Ely
8 | 25 | 2006 | INTL | 5900I | 2006 WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Pilot |  | 393 | Reno
9 | 14 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 785 | Fallon
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 786 | Carson City
5 | 24 | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 787 | Tonopah
2 | 01A | 2017 | FORD | EXPLORER | 4X4 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 790 | Ely
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 792 | Reno
9 | 14 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 793 | Wells
8 | 25 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Pilot |  | 1442 | Reno
9 | 14 | 2008 | PETERBILT | 367 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 796 | Ely
8 | 25 | 1983 | AUTOCAR | KM64F | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 797 | Ely
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 800 | Las Vegas
2 | 1 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot | 802 | Reno
8 | 25 | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Pilot |  | 2374 | Reno
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 807 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 809 | Carson City
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 810 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 811 | Reno
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 813 | Fallon
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 814 | Elko
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 816 | Reno
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 817 | Reno
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 821 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 822 | Reno
8 | 12 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1995 SANDER,1995 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 823 | Tonopah
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 826 | Reno
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 5 CU YARD | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 827 | Las Vegas
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 828 | Carson City
3 | 4 | 2003 | GMC | SAVANA | 12 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 830 | Carson City
3 | 4 | 2003 | GMC | SAVANA | 12 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 831 | Carson City
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 832 | Carson City
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 4X2 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 834 | Las Vegas
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 835 | Reno
8 | 13 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 836 | Fallon
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 838 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 840 | Carson City
8 | 13 | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,REVERSIBLE PLOW,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 841 | Carson City
8 | 12 | 1985 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 CU. YD SANDER,TYNCO REVERSIBLE | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 842 | Reno
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 843 | Carson City
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 846 | Reno
6 | 15 | 2017 | PETERBILT | 367 | TANDEM AXLE PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 848 | Reno
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 850 | Las Vegas
3 | 5 | 2003 | GMC | SIERRA | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 854 | Carson City
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 860 | Elko
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 862 | Elko
5 | 11H | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 864 | Las Vegas
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 866 | Elko
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 869 | Carson City
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 870 | Reno
5 | 11E | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 4X4 1 TON DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 871 | Wells
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 872 | Winnemucca
8 | 13 | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE WING PLOW,PLOW,SANDER,8 YARD FLINK SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 873 | Reno
8 | 13 | 1994 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HEAVY DUTY PATROL WING PLOW,11' REVERSIBLE LEWTON MDL RO1144NV,FLINK MDL #LMC5H-15NV-39 | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 877 | Carson City
3 | 5 | 1999 | GMC | TC15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 878 | Tonopah
5 | 11H | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 882 | Las Vegas
8 | 13 | 1994 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 1994 PLOW,HENKE WING PLOW,8 YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 884 | Tonopah
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 892 | Reno
8 | 13 | 1994 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1994 WING PLOW,PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 3.75 | #REF! | 5.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 894 | Reno
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 895 | Elko
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 896 | Elko
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 898 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 899 | Reno
5 | 11F | 2003 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 902 | Reno
5 | 11H | 1996 | INTL | 4700 | FLAT RACK TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 905 | Las Vegas
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 906 | Reno
6 | 11B | 2003 | INTL | 7600 | FLATRACK TRUCK W/CRANE | J1939 |  |  |  | 2018 ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 909 | Elko
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK REBUILD | J1939 | Roadwatch Sensor |  |  | 10FT PLOW REVERSIBLE,MESSAGE BOARD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 910 | Tonopah
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 913 | Reno
5 | 11A | 2017 | FORD | F-550 | AERIAL TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 914 | Elko
5 | 11F | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 4X4 SERVICE TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot | 916 | Elko
5 | 11A | 2003 | INTL | 7600 | AERIAL LIFT TRUCK BIO-DSL | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 917 | Reno
5 | 11E | 2017 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 921 | Winnemucca
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 923 | Reno
5 | 11F | 2017 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | 2018 WESTERN MULE REAR BUMPER CRANE | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 925 | Ely
5 | 11H | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 926 | Ely
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO 1500 | OBDII |  |  |  | JENSEN-MODEL 43058 | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 927 | Reno
3 | 5 | 2018 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 928 | Reno
5 | 11J | 2003 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 931 | Reno
5 | 11E | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 4X4 1 TON DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot | 932 | Elko
5 | 11J | 2003 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 933 | Reno
5 | 11J | 2003 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot | 936 | Las Vegas
5 | 11H | 2021 | RAM | 5500 | 2021 DODGE 5500 FLATRACK 4 X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 937 | Ely
5 | 11J | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 939 | Elko
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON CHEVY SILVERADO | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 940 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 941 | Reno
5 | 11J | 2017 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 942 | Ely
5 | 11F | 2004 | FORD | F-450 | UTILITY TRUCK W/CRANE 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 943 | Winnemucca
5 | 6 | 2008 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 945 | Reno
3 | 3 | 2009 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 946 | Carson City
5 | 11H | 2021 | RAM | 5500 | 2021 DODGE 5500 FLATRACK 4 X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 948 | Ely
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2007 HENKE PLOW REVERSIBLE,FLINK SANDER 8 YARD | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 950 | Las Vegas
8 | 13 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 952 | Winnemucca
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/ HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 15 FOOT SWAPLOADER DUMP BODY,2006 HENKE PLOW REVERSIBLE,2006 FLINK SANDER 8 YARD,SWAPLOADER WATER TANK | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 954 | Winnemucca
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 | SANDER EPOKE,HEAVY DUTY PATROL WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 955 | Carson City
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1355 | Elko | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 958 | Ely
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | DE-ICING SPRAYER,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 961 | Ely
6 | 15 | 1989 | INTL | 5070 | AWD DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 11' REVERSIBLE PLOW,MONROE A39-52-10 ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1521 | Carson City | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 900 GALLON DE-ICING SPRAYER,PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 963 | Ely
8 | 13 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 964 | Wells
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 323 | Reno | Confirm number of plows "Existing Associations/Hardware"
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 YD,1996 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 967 | Ely
3 | 3 | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 968 | Carson City
3 | 3 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 969 | Fallon
5 | 11A | 2020 | DODGE | 5500 | 2020 DODGE RAM 5500 FLATRACK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 973 | Elko
5 | 11H | 2021 | RAM | 5500 | 2021 DODGE 5500 FLATRACK 4 X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 975 | Ely
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE WING PLOW,PLOW ONE WAY,SANDER 8 YARD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 977 | Tonopah
8 | 12 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1995 PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 978 | Elko
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 979 | Fallon
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,2020 HENKE PLOW,2020 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 984 | Wells
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE TRK MTED WING PLOW,SANDER 8 YARD,PLOW REVERSIBLE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 985 | Winnemucca
8 | 13 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2279 | Winnemucca | Confirm number of plows "Existing Associations/Hardware"
9 | 14 | 2003 | KENW | W900B | TRACTOR TRUCK | J1939 |  |  |  | 1995 SANDER | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 987 | Reno
5 | 11H | 1991 | INTL | 4700 | SINGLE AXLE FLATRACK TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 988 | Carson City
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 989 | Fallon
3 | 3 | 2017 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 992 | Carson City
3 | 4 | 2017 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 993 | Carson City
5 | 24 | 2002 | WITTKE | FC-70 | STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 994 | Winnemucca
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 995 | Carson City
5 | 24 | 2003 | TYMCO | 600 | SWEEPER DUSTLESS | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 996 | Ely
2 | 1 | 2013 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 1002 | Tonopah
2 | 01A | 2013 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1003 | Las Vegas
5 | 11E | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1004 | Fallon
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1006 | Tonopah
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1008 | Carson City
5 | 11J | 2020 | RAM | 5500 | 2020 RAM 5500 4X4 UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1009 | Winnemucca
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1011 | Las Vegas
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1012 | Las Vegas
5 | 11E | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1015 | Fallon
6 | 11B | 1986 | INTL | 2574 | REBUILD CRANE TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1021 | Carson City
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot New |  | 1023 | Las Vegas
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1025 | Reno
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1026 | Reno
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1027 | Reno
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1028 | Carson City
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1029 | Fallon
8 | 13 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2280 | Winnemucca | Confirm number of plows "Existing Associations/Hardware"
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1033 | Elko
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1996 SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1034 | Tonopah
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1036 | Elko
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1037 | Ely
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1038 | Carson City
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1039 | Winnemucca
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1043 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1044 | Reno
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1048 | Carson City
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1049 | Carson City
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1053 | Carson City
5 | 11F | 1991 | GMC | TC31A | SERVICE TRUCK W/FLATBED | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1054 | Tonopah
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1059 | Carson City
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1061 | Elko
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SWENSON 1996 SANDER,ONE WAY | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 1062 | Las Vegas
8 | 12 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,8 Yard Sander | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 1063 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1064 | Tonopah
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1067 | Las Vegas
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1070 | Las Vegas
5 | 11H | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1072 | Tonopah
6 | 11B | 1987 | INTL | F2574 | CRANE TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1073 | Winnemucca
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1075 | Las Vegas
8 | 13 | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | MODEL #12-99 TENCO 12' REVERSIBLE,8 YARD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1076 | Ely
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1078 | Las Vegas
8 | 13 | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK SANDER MODEL 15LMC5H | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1079 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1083 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1084 | Las Vegas
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1086 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot New | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1088 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 333 | Reno | Confirm number of plows "Existing Associations/Hardware"
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1090 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1091 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1093 | Las Vegas
6 | 77 | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1094 | Elko
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1095 | Reno
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1096 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1097 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICK UP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1099 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 339 | Reno | Confirm number of plows "Existing Associations/Hardware"
2 | 01A | 2004 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1102 | Elko
3 | 3 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1104 | Winnemucca
3 | 3 | 2018 | FORD | F-250 | 2018 FORD F-250 LB EXT CAB 4X4 FFUEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1105 | Winnemucca
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1106 | Elko
6 | 28 | 1994 | INTL | 2574 | DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1107 | Ely
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1108 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1109 | Las Vegas
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1112 | Elko
2 | 1 | 2004 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1113 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1115 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1117 | Las Vegas
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1118 | Elko
8 | 13 | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | ATTENUATOR TRUCK MOUNTED,FLINK 8CU YD-15 LMC 5H | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1119 | Carson City
3 | 3 | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1120 | Winnemucca
2 | 01A | 2004 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1122 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1124 | Las Vegas
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1125 | Winnemucca
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1126 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1127 | Las Vegas
3 | 5 | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1128 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1129 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1131 | Las Vegas
6 | 28 | 1995 | INTL | 2574 | TRUCK W/ASPHALT PATCHER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1132 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1134 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW UNDERBODY,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 1327 | Reno | Confirm number of plows "Existing Associations/Hardware"
8 | 13 | 2018 | PETERBILT | 367 | 2018 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | HENKE SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1137 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1139 | Las Vegas
8 | 25 | 1980 | MACK | RS685 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1142 | Tonopah
5 | 11H | 2021 | RAM | 4500 | 2021 DODGE RAM 4500 FLATRACK 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1143 | Reno
5 | 11D | 1999 | GMC | TC31403 | COMPACTOR TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1144 | Las Vegas
5 | 11E | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1147 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1151 | Las Vegas
3 | 4 | 2004 | CHEVROLET | EXPRESS | 12 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1152 | Ely
5 | 11H | 2021 | RAM | 5500 | 2021 DODGE RAM 5500 FLATRACK 4 X 4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1153 | Carson City
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1155 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1157 | Las Vegas
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON VHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1158 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | 2014 PROFILING SYSTEM PANASONIC TOUGHBOO | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot | 1159 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1161 | Elko
3 | 3 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1162 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1164 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1165 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1166 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1169 | Elko
2 | 01A | 2017 | FORD | EXPLORER | 4X4 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1170 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1171 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1173 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1174 | Elko
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1178 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1179 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1180 | Elko
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pre-Pilot New |  | 1182 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1183 | Elko
5 | 11H | 2017 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1184 | Las Vegas
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1185 | Elko
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1186 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1187 | Reno
3 | 5 | 2004 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1188 | Reno
8 | 13 | 1995 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1995 SANDER,HEAVY DUTY PATROL WING,FRINK 12' PLOW ONE WAY | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1189 | Carson City
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1191 | Ely
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1193 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1194 | Ely
5 | 11E | 1999 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1196 | Las Vegas
3 | 3 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1197 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1198 | Winnemucca
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1200 | Reno
6 | 11G | 1984 | INTL | F2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  |  | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1201 | Las Vegas
5 | 11E | 1999 | FORD | F-450 | DUMP TRUCK W/TARP | OBDII | Roadwatch Sensor |  |  | SANDER | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1203 | Las Vegas
8 | 13 | 1995 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 12' ONE WAY,11 FT REVERSIBLE SNOW PLOW,SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1204 | Reno
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVRADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1205 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1206 | Reno
5 | 11E | 2017 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1207 | Reno
5 | 11J | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot | 1212 | Las Vegas
5 | 11F | 1989 | INTL | 2574 | SERVICE TRUCK W/CRANE | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 1213 | Elko
5 | 11H | 2017 | FORD | F-450 | 2017 FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1214 | Elko
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1215 | Elko
5 | 6 | 2013 | FORD | F-350 | 1 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1216 | Reno
8 | 12 | 1989 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1989 PLOW,SWENSON | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1217 | Las Vegas
5 | 10 | 2013 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1218 | Reno
6 | 20 | 1998 | INTL | 4900 | 1998 CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1219 | Elko
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW,2019 HENKE SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1220 | Elko
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW,SANDER,2018 HENKE SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3004 | Wells | Confirm number of plows "Existing Associations/Hardware"
5 | 11E | 2013 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1222 | Wells
3 | 5 | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1223 | Reno
3 | 5 | 2017 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1224 | Wells
5 | 11H | 2013 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1227 | Wells
5 | 11E | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1228 | Reno
5 | 11E | 2017 | FORD | F-450 | CAMERA TRUCK | OBDII | Roadwatch Sensor |  |  | CULVERT INSPECTION CAMERA | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1231 | Elko
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3198 | Carson City | Confirm number of plows "Existing Associations/Hardware"
5 | 11E | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | TRAILER OFFICE 60' X 24',2014 SNOW DOGG SNOW PLOW KIT EX-80,2014 SALT DOGG MODEL SHIP 2000X | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 280 | Reno | Existing Plows available but sensors not request by NDOT
5 | 11H | 2013 | FORD | F-450 | FLATRACK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1235 | Elko
5 | 11H | 2013 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | 2021 ASPHALT HOTBOX | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1239 | Winnemucca
6 | 20 | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1240 | Las Vegas
5 | 11E | 2013 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1241 | Ely
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1242 | Winnemucca
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1243 | Fallon
6 | 20 | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1244 | Elko
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1246 | Carson City
3 | 5 | 2013 | FORD | F-150 | 2013 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1248 | Reno
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 966 | Reno
3 | 5 | 2013 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1250 | Reno
3 | 3 | 2013 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1251 | Carson City
3 | 5 | 2017 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1252 | Reno
5 | 24 | 2018 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1254 | Las Vegas
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1255 | Carson City
3 | 3 | 2018 | CHEVROLET | SILVERADO | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1257 | Reno
5 | 24 | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1258 | Las Vegas
5 | 24 | 2018 | ELGIN | EAGLE | 2018 SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1259 | Las Vegas
5 | 11E | 2017 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1261 | Las Vegas
5 | 11F | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1263 | Las Vegas
8 | 13 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,ONE WAY PLOW,WING PLOW PPW9HD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1264 | Ely
5 | 11H | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | MESSAGE SIGN, VEHICLE MOUNTED | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1265 | Las Vegas
5 | 11A | 2005 | INTL | 7400 | AERIAL TRUCK W/PLATFORM | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1267 | Winnemucca
9 | 14 | 1991 | GMC | WG42 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1268 | Reno
6 | 11B | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1269 | Ely
2 | 01A | 2018 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1270 | Carson City
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 2014 VARITECH 403 V | Telematics device for Winter Operations |  | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 4.25 | #REF! | 6.25 | 1 | 3.25 | Tier 1 | Tier 3 | 440 | Pilot |  | 1356 | Reno
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1275 | Las Vegas
6 | 15 | 2020 | PETERBILT | 567 | 2020 TANDEM AXLE 4X4 SANDER/PLOW TRUCK | J1939 | Roadwatch Sensor |  |  | 2018 HENKE 40-65-12NV ONE WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1279 | Reno
6 | 15 | 2019 | PETERBILT | 367 | 2019 AWDTANDEM AXLE SANDER/PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1280 | Carson City
3 | 3 | 2018 | CHEVROLET | 2500 | 2018 3/4 TON CHEVY SILVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1281 | Carson City
6 | 11B | 2005 | FREIGHTLNR | M2 112 | CRANE TRUCK W/FLATBED | J1939 |  |  |  | LITEREADER ARROW BOARD V/M,2020 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1284 | Ely
3 | 5 | 2019 | FORD | F-150 | 2019 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1287 | Las Vegas
5 | 24 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1297 | Reno
5 | 24 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1298 | Reno
5 | 24 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1299 | Reno
5 | 24 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER DSL | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1300 | Carson City
8 | 13 | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1301 | Tonopah
8 | 13H | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 |  |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1302 | Las Vegas
5 | 11D | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 1304 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900 | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1305 | Tonopah
5 | 24 | 2015 | ELGIN | EAGLE | ELGIN EAGLE SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1308 | Reno
5 | 11S | 2005 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | SWAPLOADER DUMP BODY,SWAPLOADER FLATRACK | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1312 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1313 | Reno
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE 1-WAY PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1314 | Tonopah
5 | 11F | 2005 | FORD | F-450 | SERVICE TRUCK W/CRANE | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1316 | Tonopah
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE EXP11NV REV PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1317 | Reno
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE EXP11NV REV SNOW PLOW,2019 HENKE POSTLESS PATROL WING,2019 HENDERSON V BOX SPREADER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1318 | Fallon
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE PPW9HD POSTLESS WING PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1319 | Carson City
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1320 | Reno
5 | 11F | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1322 | Elko
6 | 11B | 1988 | INTL | 2574 | CRANE TRUCK W/FLATBED | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1324 | Fallon
6 | 11G | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | 2021 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1325 | Las Vegas
8 | 12 | 1993 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,1993 SANDER 5 YD 10',ATTENUATOR, V/M | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 503 | Winnemucca | Existing Plows available but sensors not request by NDOT
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  | 2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1328 | Reno
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1329 | Fallon
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1330 | Reno
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW WING,SANDER 8 CUBIC YARDS,REVERSIBLE | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1331 | Wells
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1332 | Fallon
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | REVERSIBLE PLOW,2018 HENKE SAND SPREADER,2019 HENKE WING PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1333 | Wells
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1334 | Elko
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1335 | Ely
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1336 | Ely
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK WORKMAN SWAPLOADER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1338 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1339 | Reno
5 | 11H | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | 2015 ARROW BOARD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1340 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2021 HENKE PLOW,2019 HENKE 1-WAY SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1341 | Ely
5 | 11E | 2002 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | SALTDOGG SHPE2000X SANDER,SNOWDOGG EX-85 PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 565 | Carson City | Existing Plows available but sensors not request by NDOT
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW ONE WAY,SANDER 8 YARD,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1343 | Ely
6 | 11G | 1990 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  |  | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1345 | Las Vegas
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SWAPLOADER WATER TANK,ONE WAY PLOW,SANDER 8 YARD,DUMP BODY SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1346 | Tonopah
8 | 13S | 2018 | MACK | GR64FR | 2018 MACK GRANITE TANDEM AXLE HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | SSC6100 |  | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1347 | Elko
8 | 13H | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXEL DUMP TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1350 | Las Vegas
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1351 | Elko
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1352 | Fallon
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 2272 | Reno
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2014 SNOW DOGG SNOW PLOW EX-80,2014 SNOW DOGG SHPE 2000 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 614 | Reno | Existing Plows available but sensors not request by NDOT
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | VARITECH 1750 GALLON TANK,SANDER 8 YARD,HEAVY DUTY WING PLOW,ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 2274 | Reno
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1358 | Fallon
5 | 11F | 1996 | GMC | SIERRA | SERVICE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1359 | Reno
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE REV SNOW PLOW,2019 HENKE PPW9HD 9' POSTLESS PATROL WIN | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1361 | Fallon
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1362 | Fallon
8 | 13S | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | DUMP BODY SWAPLOADER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 1363 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE SANDER 400 GAL. PRE-WET,2019 HENKE EXP11NV REV SNOW PLOW | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1364 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 HENKE EXP11NV REVERSIBLE SNOW PLOW,2019 HENKE SANDER 400 GAL. PRE-WET | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1366 | Las Vegas
5 | 11F | 1992 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1367 | Reno
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,SPRATRONICS DE ICER,PLOW REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1368 | Elko
8 | 12 | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 4.25 | #REF! | 6.25 | 1 | 3.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1370 | Winnemucca
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1372 | Elko
OFF ROAD / NA | 55B | 2009 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1374 | Elko
8 | 12 | 1991 | INTL | 4700 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 4.25 | #REF! | 6.25 | 1 | 3.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1375 | Winnemucca
5 | 24 | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1378 | Fallon
5 | 24 | 2019 | ELGIN | EAGLE | 2019 SELF PROPELLED P/U BROOM | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1381 | Elko
6 | 15 | 1995 | INTL | D3057 | AWD DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | STAINLESS 7 YD SANDER,1995 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1386 | Ely
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SPRATRONICS DE ICER,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1387 | Elko
6 | 28 | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 2464 | Fallon
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1390 | Las Vegas
5 | 11E | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1391 | Las Vegas
5 | 24 | 2018 | ELGIN | EAGLE | STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1395 | Las Vegas
5 | 11F | 1999 | DODGE | 3500 | 1 TON SERVICE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1397 | Las Vegas
5 | 24 | 2018 | ELGIN | EAGLE | STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1399 | Fallon
5 | 11J | 2018 | FORD | F-450 | 2018 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1403 | Las Vegas
5 | 11E | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1404 | Las Vegas
5 | 11D | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1405 | Las Vegas
5 | 11D | 2018 | FORD | F-450 | COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1406 | Las Vegas
5 | 24 | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1407 | Las Vegas
5 | 11F | 1999 | DODGE | 3500 | SERVICE TRUCK W/CRANE | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1409 | Las Vegas
5 | 11E | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1410 | Las Vegas
5 | 11E | 2018 | FORD | F-450 | 2018 FORD F-450 DUMP CREW V10 DRW 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1411 | Reno
5 | 11J | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1413 | Reno
5 | 11J | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1414 | Reno
5 | 11J | 2018 | FORD | F-350 | 2018 UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1417 | Reno
5 | 24 | 2004 | ELGIN | CROSSWIND | PM10 CROSSWIND STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1418 | Las Vegas
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1969 BOUMAN SANDER,1996 PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1419 | Las Vegas
5 | 11E | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1421 | Winnemucca
5 | 11E | 2018 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1424 | Winnemucca
5 | 11F | 2018 | DODGE | RAM 5500 | SERVICE TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1425 | Elko
3 | 5 | 2019 | FORD | F-150 | 2019 FORD F150 1/2 TON EXT CAB S/B | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1426 | Las Vegas
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 11' LAWTON STR DBL SWING,FLINK 10' LMC5H 5CU YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 3.75 | #REF! | 5.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 1427 | Las Vegas
5 | 11H | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1428 | Elko
5 | 11H | 2018 | FORD | F-450 | 2018 FORD F-450 V10 CREW FLAT RACK DRW | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1429 | Elko
9 | 14 | 1991 | INTL | 9300 | REBUILD TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1430 | Ely
5 | 11J | 2018 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1432 | Elko
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE,1996 SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1434 | Wells
5 | 11E | 2018 | FORD | F-450 | 2018 FORD F450 SNGL AXEL DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1438 | Las Vegas
3 | 3 | 2018 | FORD | F-250 | 2018 FORD F250 3/4T 4X4 CREW | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1441 | Las Vegas
OFF ROAD / NA | 55B | 2007 | PSTN BULLY | SCOUT | SNOW CAT | None- wired direct |  |  |  | BLADE 6-WAY | Telematics Device |  |  |  | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 2583 | Reno
3 | 3 | 2018 | FORD | F-250 | 2018 FORD F250 3/4T TRUCK 4X4 CREW CAB | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1444 | Winnemucca
5 | 11A | 2018 | FORD | F-450 | AERIAL TRUCK F-450 1 TON | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1445 | Ely
5 | 11E | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1447 | Las Vegas
3 | 3 | 2011 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1448 | Carson City
5 | 11F | 1999 | GMC | TK310 | AWD SERVICE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1450 | Winnemucca
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | HINKER C-PLOW 8802 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 652 | Las Vegas | Existing Plows available but sensors not request by NDOT
8 | 12 | 1996 | INTL | SA475 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 4.25 | #REF! | 6.25 | 1 | 3.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1454 | Winnemucca
8 | 12 | 1995 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1995 PLOW,1995 SANDER,2021 SCORPION ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1031 | Elko | Existing Plows available but sensors not request by NDOT
5 | 11E | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1457 | Reno
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1470 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 3199 | Reno
5 | 11E | 2018 | FORD | F-450 | 2018 FORD F-450 1T V10 DUMP EXT CAB 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1476 | Las Vegas
5 | 11E | 2018 | FORD | F-450 | 2018 1-2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1480 | Las Vegas
5 | 11A | 2011 | PETERBILT | 367 | PETERBILT 6X6 AERIAL LIFT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1482 | Reno
5 | 24 | 2011 | FREIGHTLNR | M2 | 2011 FREIGHTLINER M2 | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1486 | Reno
5 | 11E | 2017 | FORD | F-450 | 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | CULVERT INSPECTION CAMERA,2018 SNOWDOGG EX80II SNOW PLOW,2018 SALTDOGG SANDER SHPE2000 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1234 | Reno | Existing Plows available but sensors not request by NDOT
5 | 24 | 2011 | FREIGHTLNR | M2 | ELGIN EAGLE SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1491 | Reno
3 | 5 | 1998 | GMC | TK109 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1500 | Carson City
2 | 01A | 2018 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1505 | Las Vegas
2 | 01A | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1508 | Carson City
2 | 01A | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1511 | Reno
8 | 12 | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 1512 | Reno
2 | 01A | 2018 | FORD | EXPLORER | 2018 FORD EXPLORER 3.5L V6 4WD | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1516 | Elko
8 | 13 | 1996 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,1990 HENDERSON SANDER 10 YD,ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1518 | Ely
5 | 11E | 2018 | FORD | F-450 | 2018 FORD F-450 1 TON DUMP 4X4 | OBDII | Roadwatch Sensor |  |  | 2018 SNOWDOGG 9' STRAIGHT PLOW,2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1452 | Reno | Existing Plows available but sensors not request by NDOT
2 | 01A | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1527 | Elko
3 | 3 | 2012 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1529 | Las Vegas
3 | 5 | 2012 | FORD | F-150 | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1533 | Las Vegas
2 | 01A | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1534 | Carson City
2 | 01A | 2019 | JEEP | CHEROKEE | 2019 JEEP CHEROKEE SUV 4X4 UNLEAD | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1537 | Reno
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1545 | Las Vegas
2 | 01A | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1549 | Carson City
2 | 01A | 2018 | JEEP | CHEROKEE | 2019 JEEP GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1550 | Carson City
2 | 01A | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1553 | Reno
3 | 5 | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 1555 | Las Vegas
2 | 01A | 2018 | JEEP | CHEROKEE | 2018 JEEP GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1558 | Carson City
2 | 01A | 2018 | JEEP | CHEROKEE | 2018 GRAND CHEROKEE SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1560 | Carson City
8 | 25 | 1989 | MACK | RD688 | 3500 GALLON WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1562 | Wells
8 | 25 | 1990 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1563 | Winnemucca
8 | 12 | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | MODEL #12-99 TENCO,1999 SANDER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 1565 | Reno
8 | 12 | 2000 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 11' SWING PLOW,SANDER | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 3.75 | #REF! | 5.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 1569 | Las Vegas
8 | 13 | 1996 | INTL | 2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENDERSON CHIEF 5 YARD,1996 PLOW,HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1570 | Reno
2 | 01A | 2018 | JEEP | CHEROKEE | 2019 JEEP LATITUDE CHEROKEE SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1583 | Reno
2 | 01A | 2018 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1589 | Reno
3 | 5 | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1591 | Las Vegas
6 | 28 | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1593 | Elko
2 | 01A | 2019 | JEEP | CHEROKEE | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1595 | Carson City
3 | 3 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1605 | Fallon
5 | 24 | 2014 | TYMCO | DST6 | INTL TYMCO SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1612 | Carson City
6 | 28 | 1989 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1613 | Wells
5 | 11S | 2014 | FORD | F-450 | DUMP TRUCK W/SWAPLOADER BIODSL | OBDII | Roadwatch Sensor |  |  | 2014 WILLIAMSEN SWAPLOADER BED | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1614 | Las Vegas
3 | 3 | 2018 | CHEVROLET | SILVERADO | 2018 CHEVEROLET SIVERADO 2500 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1615 | Elko
8 | 13 | 2021 | WESTERN ST | 4900SF | 2021 WESTERN STAR 4900SF TANDEM AXEL DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor |  | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 1 | 3 | Tier 1 | Tier 3 | 440 | Full Project |  | 1624 | Elko
8 | 13 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SANDER,HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1628 | Ely
5 | 24 | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1630 | Wells
5 | 24 | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1631 | Wells
8 | 13 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1632 | Fallon
6 | 11G | 1986 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | 1986 SANDER | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1633 | Ely
5 | 24 | 1996 | SWEEPRITES | SR330 | SELF PROPELLED STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1638 | Ely
6 | 77 | 2003 | MACK | MR688S | 700 GALLON PAINT STRIPER | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1639 | Ely
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1640 | Las Vegas
8 | 13 | 2021 | WESTERN ST | 4900SF | 2021 WESTERN STAR 4900SF TANDEM AXEL DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor |  | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 1 | 3 | Tier 1 | Tier 3 | 440 | Full Project |  | 1641 | Fallon
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2016 WING PLOW,1991 PLOW,FLINK 8 YD | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1642 | Winnemucca
2 | 01A | 2018 | FORD | EXPEDITION | 2018 FORD EXPEDITION SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1643 | Reno
6 | 28 | 1996 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1649 | Ely
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 8 YRD FLINK,REVERSIBLE JENSEN MDL 34058 | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1650 | Fallon
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | VARITECH 1750 GAL BRINE TANK,MONROE 11' REVERSIBLE PLOW 540-58-11,PLOW REVERSIBLE ALASKA EXPRESSWAY,2014 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1651 | Carson City
3 | 5 | 2018 | CHEVROLET | 1500 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1653 | Carson City
3 | 5 | 2018 | CHEVROLET | SILVERADO | 18 CHEVY SILVERADO 1/2 T CREW CAB 4X2 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1656 | Las Vegas
3 | 5 | 2018 | CHEVROLET | 2500 | 2018 CHEVY SILVERADO 1/2T CREW CAB SB V8 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1658 | Las Vegas
5 | 11D | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1659 | Las Vegas
3 | 5 | 2018 | CHEVROLET | 2500 | 2018 CHEV SILVERADO 1/2T CREW CAB SB V8 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1664 | Las Vegas
5 | 11A | 2017 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1665 | Las Vegas
6 | 28 | 1996 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1668 | Wells
3 | 5 | 2019 | FORD | F-150 | 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1669 | Las Vegas
8 | 12 | 1988 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENDERSEN 5 CU YD SANDER,11' SNOW PLOW, REVERSIBLE, LAWTON EQUIPM | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1670 | Carson City
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,BRINE DISTRIBUTOR | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 1671 | Reno
5 | 11J | 2019 | FORD | F-350 | 2019 FORD F-350 4X4 UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1673 | Reno
3 | 3 | 2019 | FORD | 250 | 2019 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1675 | Winnemucca
3 | 3 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1676 | Carson City
3 | 5 | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1678 | Las Vegas
3 | 5 | 2018 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1679 | Las Vegas
3 | 5 | 2018 | FORD | 150 | 2018 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1680 | Reno
8 | 25 | 1991 | INTL | F2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1682 | Wells
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 8 YRD FLINK SANDER,12' PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1684 | Fallon
2 | 01A | 2018 | FORD | EXPLORER | 2018 FORD EXPL SUV 1/2T 5.3 4WD 6 PASS | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1686 | Tonopah
5 | 11H | 2020 | FORD | F-450 | 2020 FORD F-450 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1687 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 3200 | Reno
3 | 3 | 2019 | FORD | F-250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1689 | Tonopah
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2000 SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1690 | Elko
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 8 YD SANDER,SPRATRONICS DE ICER,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1691 | Wells
6 | 28 | 1986 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1692 | Winnemucca
3 | 5 | 2018 | CHEVROLET | 1500 | 2018 1/2 TON PICK UPS | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1693 | Las Vegas
3 | 5 | 2018 | FORD | F-150 | 2018 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1694 | Reno
3 | 3 | 2019 | FORD | 250 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1695 | Reno
3 | 3 | 2019 | FORD | 250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1697 | Fallon
5 | 11E | 2018 | FORD | F-450 | 2018 1 - 2 TON DUMP/GARBAGE TRCK | OBDII | Roadwatch Sensor |  |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1456 | Fallon | Existing Plows available but sensors not request by NDOT
2 | 01A | 2005 | GMC | ENVOY | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1700 | Las Vegas
2 | 01A | 2005 | GMC | ENVOY | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1701 | Las Vegas
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2000 PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1702 | Elko
8 | 25 | 2018 | MACK | GR64F | 2018 WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1704 | Las Vegas
8 | 13 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 2000 PLOW PLOWS,REBUILD 2006 SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1705 | Ely
8 | 13 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE 12FT RGHT HAND DISCHARGE,REVERSIBLE,REBUILD 2008 HENDERSON SANDER/HOPPER TYP | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1706 | Elko
8 | 25 | 2018 | MACK | GR64F | 2018 WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1707 | Tonopah
8 | 25 | 2019 | INTL | HX620 | 2019 INT'L HX 620 WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 1708 | Las Vegas
3 | 3 | 2019 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1710 | Elko
3 | 4 | 2019 | CHEVROLET | EXPRESS | PASSANGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1711 | Winnemucca
2 | 1 | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1712 | Las Vegas
3 | 3 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1714 | Reno
5 | 11E | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1715 | Fallon
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE JENSEN PLOW,8 YRD FLIMK SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1722 | Fallon
2 | 1 | 2005 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 1724 | Carson City
8 | 13 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | REBUILD 2000 SANDER,REBUILD 2000 PLOWS,REBUILD 1999 PLOWS | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1728 | Ely
6 | 28 | 1993 | INTL | 2574 | DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1730 | Winnemucca
2 | 01A | 2018 | JEEP | CHEROKEE | 2018 GRAND CHAEROKEE SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1737 | Carson City
2 | 1 | 2019 | CHEVROLET | MALIBU | 2019 CHEV MALIBU 1.5L TURBO | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 1741 | Carson City
5 | 11A | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 AERIAL LIFT | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1742 | Las Vegas
2 | 01A | 2019 | CHEVROLET | TRAVERSE | 2019 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1743 | Carson City
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1744 | Las Vegas
5 | 11J | 2006 | FORD | F-350 | UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1745 | Carson City
3 | 3 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1748 | Reno
3 | 3 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1749 | Reno
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1750 | Las Vegas
9 | 14 | 2000 | INTL | 9900 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1751 | Carson City
6 | 20 | 2000 | INTL | 2674 | CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1752 | Las Vegas
9 | 14 | 1994 | INTL | F9200 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1757 | Tonopah
3 | 3 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1759 | Las Vegas
3 | 3 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1761 | Ely
3 | 3 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1763 | Ely
3 | 3 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICKUP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1766 | Carson City
3 | 5 | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1767 | Reno
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1768 | Las Vegas
3 | 3 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1769 | Las Vegas
3 | 3 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 1771 | Elko
OFF ROAD / NA | 42 | 1996 | KODIAK | 6060- | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 1773 | Reno
3 | 3 | 2019 | CHEVROLET | SILVERADO | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1778 | Elko
3 | 3 | 2019 | CHEVROLET | 2500 | 2019 3/4 TON PICK UP | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1780 | Elko
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1782 | Reno
5 | 76 | 1996 | CYBR | SFT50 | REBUILT 2021 INTERNATIONAL CYBERNETICS SKID TRAILER | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1788 | Carson City
3 | 3 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1789 | Las Vegas
3 | 5 | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1791 | Fallon
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1792 | Reno
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1795 | Reno
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1796 | Reno
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1798 | Reno
3 | 3 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1801 | Las Vegas
3 | 5 | 2005 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1803 | Elko
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1804 | Reno
3 | 3 | 2005 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1805 | Reno
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | LITEREADER MESSAGE BOARD V MNT | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1807 | Las Vegas
8 | 25 | 2021 | WESTERN ST | 4900 | 2021 WESTERN STAR 4900 WATER TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1808 | Elko
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1814 | Reno
7 | 83 | 2009 | PETERBILT | 367 | UNDER BRIDGE TRUCK | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pilot |  | 1353 | Carson City
3 | 5 | 2019 | FORD | F-150 | 2019 FORD 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1823 | Reno
8 | 25 | 2021 | WESTERN ST | 4900 | 2021 WESTERN STAR 4900 WATER TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1825 | Las Vegas
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1 TON PICK UP 4X2 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1827 | Las Vegas
6 | 28 | 2021 | FREIGHTLNR | 114SD | 2021 FREIGHTLINER 114SD TANDEM AXEL DISTRIBTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1828 | Tonopah
5 | 11A | 2005 | FORD | F-550 | FLANNIGAN SHOP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1829 | Elko
5 | 11J | 2006 | FORD | F-450 | UTILITY TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1830 | Carson City
5 | 24 | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1832 | Elko
3 | 5 | 2019 | FORD | F-150 | 2019 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1833 | Elko
6 | 11B | 1986 | INTL | F2574 | CRANE TRUCK CONVERTED | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1834 | Tonopah
5 | 11H | 2005 | FORD | F-450 | FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1835 | Tonopah
5 | 11C | 2005 | PETERBILT | 335 | FUEL LUBE TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1836 | Las Vegas
5 | 11D | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1837 | Las Vegas
5 | 11D | 2005 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1838 | Las Vegas
5 | 11E | 2007 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1840 | Carson City
2 | 01A | 2018 | FORD | EXPLORER | 2018 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1844 | Reno
5 | 24 | 1999 | MOBILE | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 1847 | Winnemucca
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1849 | Reno
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1850 | Reno
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1851 | Carson City
5 | 11E | 2020 | FORD | F-450 | 2020 FORD F-450 1-2 TON DUMP/GARBAGE TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1852 | Las Vegas
9 | 14 | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1853 | Elko
9 | 14 | 2019 | WESTERN | 4900SF | 2019 TRANSPORT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1854 | Carson City
5 | 11E | 2007 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1856 | Reno
5 | 11F | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1857 | Las Vegas
5 | 11F | 2019 | FORD | F-550 | 2019 F550 CRANE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1858 | Las Vegas
5 | 11F | 2019 | FORD | F-550 | F-550 SERVICE TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1859 | Fallon
5 | 11D | 2019 | FORD | F-450 | 2019 FORD COMPACTOR TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1860 | Las Vegas
5 | 11E | 2019 | FORD | F-450 | 2019 FORD 1/2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1862 | Las Vegas
5 | 11S | 2007 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | FLATRACK BODY SWAPLOADER,DUMP BODY SWAPLOADER,ARROWBOARD VEHICLE MOUNTED | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 1863 | Las Vegas
8 | 13 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | TWO-WAY SWING PLOW,FLINK SANDER 8 CU YD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1865 | Winnemucca
5 | 11E | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1866 | Reno
5 | 11F | 2008 | FORD | F-650 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1868 | Elko
5 | 11F | 2005 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1869 | Reno
5 | 11J | 2006 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1872 | Ely
5 | 11E | 2019 | FORD | F-450 | 2019 FORD F-450 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1874 | Carson City
3 | 5 | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1876 | Reno
5 | 11E | 2019 | FORD | F-450 | 2019 1 TON DUMP/GARBAGE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1877 | Reno
5 | 11E | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1879 | Ely
5 | 11E | 2019 | FORD | F-450 | 2019 1-2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1881 | Ely
5 | 11E | 2019 | FORD | F-450 | 2019 1/2 TON DUMP/GARBAGE TRUCK | OBDII | Roadwatch Sensor |  |  | 2020 LITEREADER ARROWBOARD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1882 | Ely
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot | 1883 | Carson City
5 | 11F | 2006 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1884 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1886 | Las Vegas
9 | 14 | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1887 | Tonopah
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1888 | Las Vegas
3 | 5 | 2019 | CHEVROLET | 1500 | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1889 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1890 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1891 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1892 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1893 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1895 | Elko
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,REVERSIBLE PLOW,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1896 | Elko
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE TRUCK | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 | PLOW WING,JENSEN REVERSIBLE PLOW,SANDER EPOKE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1897 | Reno
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD SWAPLOADER,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1898 | Tonopah
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 | SANDER 8 YARD,PLOW ONE WAY,EPOKE SANDER,2021 HENKE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1899 | Carson City
5 | 11A | 2016 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1900 | Las Vegas
9 | 14 | 1988 | KENW | T800 | REBUILD TRANSPORT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1901 | Winnemucca
5 | 11A | 2015 | FORD | F-550 | FLANNIGAN SHOP TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1903 | Las Vegas
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1904 | Fallon
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | ARROW BOARD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1905 | Tonopah
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | ARROW BOARD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1906 | Tonopah
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1908 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  | SKIDSTER PICKUP BROOM | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 1909 | Las Vegas
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1911 | Tonopah
6 | 11B | 2015 | WESTERN ST | 4900SF | FLATRACK W/CRANE | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1912 | Las Vegas
6 | 11G | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | 2001 ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1914 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | FLINK SANDER,HEAVY DUTY WING PLOW,PLOW REVERSIBLE | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1915 | Carson City
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1916 | Tonopah
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1917 | Las Vegas
8 | 13 | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW WING,PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1918 | Elko
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1919 | Las Vegas
5 | 24 | 2015 | ELGIN | EAGLE | SELF PROPELLED DUSTLESS SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1920 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1921 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1922 | Las Vegas
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1923 | Reno
8 | 13S | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | SPRAYTRONIC DE-ICER,PLOW REVERSIBLE,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 3319 | Reno
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW,8 YD STAINLESS STEEL SANDER,PLOW ONE WAY,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1925 | Winnemucca
5 | 11A | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1926 | Reno
6 | 11G | 1988 | INTL | 2574 | ATTENUATOR TRUCK SINGLE AXLE | J1939 |  |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1928 | Las Vegas
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1929 | Las Vegas
3 | 5 | 2019 | CHEVROLET | SILVERADO | 2019 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1930 | Las Vegas
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1932 | Las Vegas
5 | 11A | 2015 | FORD | F-550 | AERIAL LIFT TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1934 | Fallon
8 | 13S | 2006 | WESTERN ST | 4900 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,DUMP BODY SWAPLOADER,WATERTANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1935 | Las Vegas
5 | 11D | 2015 | FORD | F-450 | TRASH COMPACTOR 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1936 | Reno
5 | 11D | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1937 | Reno
5 | 11D | 2015 | FORD | F-450 | COMPACTOR TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1938 | Carson City
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1939 | Fallon
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1940 | Reno
6 | 20 | 2005 | INTL | 7600 | CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1942 | Elko
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1943 | Fallon
8 | 12 | 1996 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SNOW PLOW,ATTENUATOR, V/M,2000 SNOW PLOW | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 1489 | Winnemucca | Existing Plows available but sensors not request by NDOT
5 | 11J | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  | 2018 SNOWDOGG 9' TE STRAIGHT PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1699 | Ely | Existing Plows available but sensors not request by NDOT
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | SNOWPLOW 8' | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1947 | Reno | Existing Plows available but sensors not request by NDOT
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 1952 | Reno
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | SNOW PLOW,ARROW BOARD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1948 | Reno | Existing Plows available but sensors not request by NDOT
5 | 11F | 2016 | FORD | F-550 | SERVICE TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1954 | Fallon
5 | 11H | 2016 | PETERBILT | 337 | SINGLE AXLE FLATRACK TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1955 | Reno
8 | 13S | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | PLOW REVERSIBLE,2003 SANDERS,DUMP BODY SWAPLOADER,FLAT RACK SWAPLOADER,WATER TANK, SWAPLOADER,PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Pilot |  | 3320 | Reno
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 1959 | Elko
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | 2014 SNOW PLOW SNOW DOGG,2014 SALT DOGG SPREADER | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1949 | Carson City | Existing Plows available but sensors not request by NDOT
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1961 | Wells
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK W/LIFT GATE | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1962 | Wells
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1963 | Elko
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | 2018 SALTDOGG SANDER 2.0 CUYD ELECT | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1964 | Elko
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1965 | Wells
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1966 | Elko
5 | 11H | 2019 | FORD | F-450 | 2019 FLATRACK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1967 | Elko
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 1968 | Elko
2 | 01A | 2015 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1969 | Carson City
5 | 11J | 2019 | FORD | F-450 | 2019 UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1970 | Las Vegas
3 | 3 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK W/ CAMPERSHELL 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1971 | Carson City
3 | 3 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1972 | Carson City
3 | 3 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1973 | Carson City
3 | 3 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1974 | Carson City
3 | 3 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1976 | Carson City
3 | 4 | 2015 | CHEVROLET | EXPRESS | CARGO VAN 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1977 | Carson City
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1978 | Carson City
5 | 11H | 2019 | FORD | F-450 | 2019 FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1979 | Elko
5 | 11F | 2019 | FORD | F-450 | 2019 1 TON SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1981 | Carson City
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1982 | Winnemucca
5 | 11F | 2019 | FORD | F-450 | 2019 SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 1984 | Las Vegas
OFF ROAD / NA | 55B | 2005 | TUCKER | 2000BXL265 | SNOW CAT | None- wired direct |  |  |  | 6 WAY STRAIGHT BLADE | Telematics Device |  |  |  | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 1997 | Ely
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2001 | Elko
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2003 | Carson City
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2005 | Carson City
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2006 | Carson City
8 | 13S | 2019 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | SSC6100 | FLAT RACK SWAPLOADER | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2007 | Las Vegas
8 | 13 | 2018 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2014 | Las Vegas
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2015 | Elko
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2016 | Carson City
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2017 | Elko
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2018 | Elko
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2019 | Las Vegas
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2020 | Elko
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2021 | Elko
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2023 | Reno
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2024 | Carson City
3 | 5 | 2014 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2025 | Reno
5 | 11F | 2015 | FORD | F-350 | 1 TON SERVICE TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 1924 | Reno
2 | 01A | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2039 | Reno
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | ONE WAY PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2041 | Tonopah
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2046 | Las Vegas
5 | 24 | 2016 | ELGIN | EAGLE | SELF PROPELLED SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.5 | #REF! | 2.5 | 0 | 2.5 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2052 | Las Vegas
2 | 01A | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2054 | Reno
6 | 11B | 2019 | WESTERN ST | 4900SF | 2019 WESTERN STAR FLAT RACK | J1939 |  |  |  | 2021 SCORPION ATTENUATOR,2021 LITEREADER ARROWBOARD | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 2056 | Elko
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2058 | Tonopah
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2059 | Tonopah
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2060 | Fallon
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2062 | Reno
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2063 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2064 | Carson City
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW,2020 ASPHALT HOTBOX | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2065 | Carson City
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE ALASKAN REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 4.75 | #REF! | 6.75 | 0 | 4.75 | 0 | Tier 4 | 660 | Pilot | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2067 | Reno
8 | 13 | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | PLOW,SANDER,2021 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2068 | Elko
2 | 01A | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2069 | Carson City
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2070 | Carson City
8 | 13 | 2019 | WESTERN ST | 4900SF | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE ONE WAY PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2071 | Ely
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE NV REV /NO OFFSET,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2072 | Winnemucca
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2019 FLINK SANDER,2019 HENKE REV PLOW,2019 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2073 | Winnemucca
5 | 11 | 2019 | KENWORTH | T440 | 2021 KENWORTH T400 | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2074 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2077 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2078 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2079 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot New | Pre-Pilot | 2080 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2081 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2082 | Las Vegas
2 | 1 | 2006 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 2083 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot New | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2085 | Las Vegas
5 | 11 | 2016 | FREIGHTLNR | M2 112 | HERBICIDE SPRAY TRUCK | J1939 |  |  |  | INJECTION SPRAYER | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2087 | Carson City
5 | 11H | 2016 | FORD | F-550 | 1 1/2 TON FLATRACK TRUCK W/LIFTGATE | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2088 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2090 | Las Vegas
5 | 11C | 2016 | FORD | F-550 | LUBE TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2091 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2092 | Fallon
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2093 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2094 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2095 | Carson City
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2096 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2097 | Carson City
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2099 | Reno
2 | 01A | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2102 | Ely
8 | 25 | 1987 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 2103 | Las Vegas
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2104 | Reno
2 | 01A | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2106 | Reno
2 | 01A | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2107 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2110 | Ely
2 | 01A | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2115 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2116 | Tonopah
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2117 | Winnemucca
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2118 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2119 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2120 | Las Vegas
2 | 1 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2121 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2122 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2123 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2124 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot New | Pre-Pilot | 2128 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot New |  | 2131 | Las Vegas
2 | 1 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 2132 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2135 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2136 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2137 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2138 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2139 | Tonopah
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2140 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2141 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2142 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot New | Pre-Pilot | 2151 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2152 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2154 | Las Vegas
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2155 | Carson City
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2156 | Fallon
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2157 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2158 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2159 | Carson City
5 | 11F | 2015 | FORD | F-350 | SERVICE TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 2160 | Reno
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SNOW PLOW,SANDER W/PREWET SYSTEM | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2162 | Tonopah
6 | 20 | 2016 | PETERBILT | 567 | CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Pilot |  | 370 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2165 | Carson City
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2166 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2167 | Elko
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2168 | Reno
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2170 | Las Vegas
6 | 28 | 1988 | FORD | 9000 | OIL DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2172 | Las Vegas
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2173 | Ely
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2175 | Las Vegas
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2179 | Reno
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2180 | Las Vegas
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2181 | Ely
3 | 5 | 1998 | GMC | C1070 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2183 | Carson City
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2189 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2193 | Las Vegas
5 | 11E | 2015 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | ROCK PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 1953 | Fallon | Existing Plows available but sensors not request by NDOT
3 | 5 | 2020 | FORD | F-150 | 2020 F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2198 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2201 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2203 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2204 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2205 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2206 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot New | Pre-Pilot | 2207 | Las Vegas
5 | 11C | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2209 | Fallon
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | REVERSIBLE PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2210 | Ely
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2215 | Las Vegas
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | ONE WAY PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2219 | Ely
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2220 | Ely
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2221 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2222 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2228 | Las Vegas
5 | 11J | 2008 | FORD | F-450 | UTILITY TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2231 | Fallon
5 | 11H | 2008 | FORD | F-450 | FLATRACK TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2232 | Winnemucca
2 | 1 | 2015 | FORD | FOCUS | ELECTRIC SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Pre-Pilot |  | 2234 | Las Vegas
2 | 1 | 2015 | FORD | FOCUS | ELECTRIC SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Pre-Pilot |  | 2237 | Las Vegas
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 2238 | Las Vegas
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2239 | Las Vegas
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2240 | Las Vegas
2 | 01A | 2015 | FORD | EXPLORER | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2241 | Carson City
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2242 | Las Vegas
5 | 11H | 2015 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  | HENKE 11 FT REV SNOW PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 1960 | Elko | Existing Plows available but sensors not request by NDOT
3 | 3 | 2016 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2245 | Reno
3 | 3 | 2015 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2246 | Carson City
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2247 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2248 | Las Vegas
5 | 11F | 2008 | FORD | F-550 | SERVICE TRUCK W/AUTOCRANE | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2249 | Carson City
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2251 | Elko
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2252 | Las Vegas
5 | 11J | 2008 | FORD | F-350 | UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2254 | Winnemucca
5 | 11F | 2008 | FORD | F-450 | 1 TON SERVICE TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2256 | Tonopah
8 | 12 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2257 | Las Vegas
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2258 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2259 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK W/CAMPERSHELL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2260 | Carson City
5 | 11C | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2261 | Ely
8 | 12 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SKID MOUNTED STAINLESS WATER TANK 1200,SANDER 5 CUBIC YARDS,PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2262 | Reno
8 | 12 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 5 CUBIC YARDS,PLOW ONE WAY,REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2263 | Fallon
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  | 2013 LIGHT READER 1230 F-4 | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2264 | Reno
5 | 11 | 1990 | INTL | 4700 | T/M WEED SPRAYER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2265 | Las Vegas
5 | 11 | 1990 | INTL | 4700 | INTL TRUCK W/WEED SPRAYER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2266 | Reno
5 | 11C | 1990 | INTL | 4900 | LUBE TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2267 | Las Vegas
8 | 12 | 2008 | WESTERN ST | 4900FA | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW ONE WAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2268 | Carson City
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW REVERSIBLE,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2269 | Wells
8 | 13 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW ONE WAY,SANDER 8 YARD,2012 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2270 | Tonopah
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1989 SANDER HOPPER-TYPE 8 CU YD,PLOW REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2271 | Elko
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 1956 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2273 | Reno
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE 11FT REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 2038 | Reno
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD,TRUCK MOUNTED WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2275 | Carson City
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | VARITECH BRINE DISTRIBUTION TANK,PLOW REVERSIBLE,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2276 | Reno
8 | 13S | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | DUMP BODY SWAP-LOADER,WATER TANK WRKMAN SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2277 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW REVERSIBLE,SANDER 8 YARD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2278 | Fallon
5 | 11E | 2016 | FORD | F-450 | 1 TON DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | 2018 SNOWDOGG 9' STRAIGHT PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2196 | Ely | Existing Plows available but sensors not request by NDOT
5 | 11E | 2007 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | HINKER C- PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2243 | Las Vegas | Existing Plows available but sensors not request by NDOT
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2281 | Reno
8 | 13 | 2007 | WESTERN ST | 4900FA | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SANDER 8 YARD,REVERSABLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2282 | Las Vegas
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2283 | Winnemucca
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 8 CUBIC YARDS,PLOW ALASKAN EXPRESSWAY | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2284 | Ely
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2285 | Elko
8 | 12 | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER 5 CUBIC YARDS,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2286 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2287 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2288 | Reno
8 | 12 | 1991 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW REVERSIBLE,5 CUBIC YARD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2289 | Winnemucca
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW ONE WAY,SANDER 8 CUBIC YARDS | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2290 | Ely
8 | 25 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2291 | Elko
8 | 13 | 1991 | INTL | 2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | JENSEN REVERSIBLE,8 CU YD | Telematics device for Winter Operations |  | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 4.25 | #REF! | 6.25 | 1 | 3.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2292 | Elko
8 | 25 | 1991 | INTL | F2574 | WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2293 | Ely
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2294 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2295 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2297 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2298 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2299 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2300 | Winnemucca
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2301 | Reno
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2302 | Reno
9 | 14 | 2007 | PETERBILT | 378 | TRACTOR TRUCK W/MANUAL TRANS | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2304 | Las Vegas
9 | 14 | 2007 | PETERBILT | 378 | TRUCK TRACTOR W/MANUAL TRANS | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2305 | Las Vegas
6 | 15 | 2007 | PETERBILT | 357 | AWD TRUCK W/EPOKE SANDER | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 | PLOW SLOTTED TRIP,PLOW ONE WAY,JENSEN 12 FT ONE-WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2306 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2307 | Reno
5 | 11E | 2019 | FORD | F-450 | 2019 FORD F-450 DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2308 | Las Vegas
2 | 01A | 2020 | JEEP | GRAND CHEROK | 2020 JEEP CHEROKEE 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2310 | Reno
8 | 25 | 1990 | INTL | 2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2314 | Ely
6 | 28 | 1990 | MACK | MR690 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2315 | Elko
6 | 28 | 1990 | INTL | 2574 | OIL DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2316 | Ely
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2317 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2318 | Las Vegas
8 | 25 | 1991 | INTL | F2574 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2319 | Winnemucca
6 | 28 | 1991 | INTL | 2574 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2331 | Fallon
9 | 14 | 2019 | WESTERN | 4900SF | TRANSPORT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2334 | Elko
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  | PROFILING SYSTEM | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2335 | Carson City
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2336 | Carson City
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | REVERSIBLE PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 2163 | Reno
8 | 25 | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2359 | Elko
8 | 25 | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2360 | Tonopah
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2362 | Carson City
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2365 | Carson City
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2366 | Carson City
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 1/2 TON PICK UP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2368 | Carson City
2 | 01A | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2373 | Carson City
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 54 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2375 | Carson City
2 | 01A | 2020 | FORD | EXPLORER | 2020 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2377 | Las Vegas
5 | 11F | 2020 | RAM | 5500 | 2020 DODGE RAM 5500 UTILITY TRUCK WITH CRANE ASSEMBLY | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2379 | Elko
2 | 01A | 2020 | JEEP | GRAND CHEROK | 2020 JEEP GRAND CHEROKEE 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2380 | Carson City
6 | 77 | 2022 | PETERBILT | 520 | 2022 PETERBILT 520 FREEWAY LINE STRIPE | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2381 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2382 | Las Vegas
8 | 25 | 2006 | INTL | 5900I | WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 2385 | Las Vegas
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2386 | Winnemucca
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2387 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2390 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2391 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2392 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 2X2 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot New | Pre-Pilot | 2393 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2395 | Las Vegas
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2396 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2397 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2398 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2399 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2400 | Carson City
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2401 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2402 | Reno
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2403 | Elko
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2404 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2405 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2406 | Reno
3 | 5 | 2020 | FORD | F-150 | 2020 FORD F-150 4X2 PICKUP | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2407 | Las Vegas
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2408 | Elko
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2409 | Winnemucca
3 | 5 | 2020 | FORD | F-150 | 2020 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2410 | Elko
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2421 | Las Vegas
3 | 5 | 2015 | CHEVROLET | SILVERADO | 1/2 TON PICKUP TRUCK E-85 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2423 | Las Vegas
5 | 11F | 2016 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2429 | Carson City
5 | 10 | 2016 | FORD | F-350 | 1 TON TRUCK W/UTILITY BODY | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2448 | Carson City
6 | 28 | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2463 | Ely
8 | 13 | 2017 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | SANDER,REVERSIBLE PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 62 | Reno
6 | 77 | 1991 | MACK | MR688 | LINE STRIPER | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2474 | Winnemucca
6 | 28 | 2007 | PETERBILT | 367 | DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2479 | Winnemucca
8 | 13 | 1992 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE WING PLOW,SANDER,2001 HENKE REV WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2487 | Reno
5 | 24 | 2020 | ELGIN | EAGLE | 2020 SELF PROPELLED TENNANT BR | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 2491 | Elko
2 | 1 | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Pilot | Pre-Pilot | 2525 | Elko
2 | 1 | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Pilot | Pre-Pilot | 2528 | Elko
3 | 3 | 2020 | FORD | F-250 | 2020 FORD F-250 3/4 TON PICK UP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2531 | Elko
2 | 1 | 2020 | CHEVROLET | MALIBU | 2020 CHEVROLET MALIBU | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 2535 | Winnemucca
5 | 6 | 2020 | FORD | F-350 | FORD F-350 1 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2537 | Carson City
3 | 4 | 2020 | CHEVROLET | EXPRESS | 2020 CHEVROLET EXPRESS 15 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2544 | Las Vegas
OFF ROAD / NA | 42 | 1999 | KODIAK | CR65 | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 2545 | Reno
5 | 11E | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2549 | Reno
5 | 11E | 2020 | FORD | F-450 | 2020 F-450 4X4 DUMP TRUCK | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2550 | Fallon
6 | 15 | 2017 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | ONE WAY PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 66 | Reno
5 | 76 | 1992 | DYNA | TEST | FALLING WEIGHT DEFLECTOMETER | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2619 | Carson City
3 | 5 | 2022 | FORD | F-150 | 2022 FORD F-150 SHORT BED CREW CAB 4 X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2621 | Carson City
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2647 | Las Vegas
5 | 76 | 2018 | DYNA | 8000 | 2018 SKID TESTER | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2666 | Carson City
5 | 11A | 1997 | GMC | 3500H | AERIAL TRUCK W/MAN LIFT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2670 | Las Vegas
8 | 12 | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 1989 SANDER,HENKE 11' REVERSIBLE PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 2675 | Las Vegas
8 | 12 | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE PLOW,5 YRD | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 2676 | Reno
8 | 12 | 1997 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,1997 SANDER | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 2677 | Las Vegas
8 | 25 | 1997 | INTL | 2574 | 1997 REBUILT TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,8 YRD SANDER CHIEF | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 2679 | Ely
9 | 14 | 1996 | FORD | 9501 | TRACTOR TRUCK | J1939 |  |  |  | BREAKER ATTACHMENT | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2680 | Las Vegas
6 | 15 | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 2011 HENKE 10 ONE-WAY SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2682 | Reno
6 | 15 | 1997 | INTL | 5000 | REBUILD AWD SANDER TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | ONE WAY PLOW TRUCK PATROL | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2684 | Reno
5 | 24 | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | OBDII |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 2685 | Fallon
6 | 28 | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Deleted | Deleted | 2691 | Reno
6 | 28 | 1997 | VOLVO | WG42 | MAINTENANCE DISTRIBUTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2692 | Tonopah
OFF ROAD / NA | 42 | 1997 | KODIAK | CR400 | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 2700 | Elko
5 | 10 | 1998 | GMC | K3094 | SURVEY UNIT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2733 | Las Vegas
6 | 11B | 1998 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  |  | ARROW SIGNBOARD, T/M,SCORPION ATTENUATOR TRK MNT | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 2741 | Elko
5 | 11J | 1998 | GMC | TK314 | UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2742 | Reno
5 | 11J | 1998 | GMC | W5R04 | UTILITY TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2754 | Las Vegas
3 | 3 | 1998 | GMC | SIERRA | 3/4 TON PICKUP TRUCK W/SVC BODY AWD | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2761 | Elko
8 | 12 | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,5 YD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2764 | Elko
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2000 FLINK SANDER,11 REVERSIBLE | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2765 | Elko
8 | 12 | 1998 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,PLOW,SANDER 5 CU YD,2020 SCORPION VEH MNT ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 2766 | Elko | Existing Plows available but sensors not request by NDOT
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2767 | Ely
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 YD Flink,11 FT. REVERSIBLE SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2768 | Wells
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSIBLE JENSEN PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2769 | Reno
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | FLINK LCM 10NV-59 SANDER,PLOW,ATTENUATOR, TM,ARROW SIGNBOARD, T/M | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 2770 | Wells | Existing Plows available but sensors not request by NDOT
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,5 YD,ATTENUATOR, TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 2771 | Wells | Existing Plows available but sensors not request by NDOT
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 CU YD SANDER,PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2772 | Ely
8 | 12 | 1999 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2773 | Las Vegas
8 | 13 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,PLOW TENCO WING,8 CU YD SANDER,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2774 | Winnemucca
8 | 13 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW,8 YD FLINK | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2775 | Wells
8 | 13 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE TRK MTED WING PLOW,SANDER 8 CU YD,PLOW REVERSIBLE,PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2776 | Winnemucca
8 | 13 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 2011 HENKE ONE-WAY 10 SNOW PLOW,FLINK/MDL 15 LM C5H 8 CU YRD | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2777 | Carson City
8 | 25 | 2017 | PETERBILT | 567 | TANDEM AXLE WATER TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Pilot |  | 690 | Reno
6 | 20 | 2017 | KENWORTH | T440 | CULVERT CLEANER TRUCK | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Pilot |  | 1249 | Reno
8 | 13 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 YD SANDER,PLOW,11FT JENSEN REVERSIBLE SNOW PLOW,8 YRD,SPRAYER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2780 | Carson City
8 | 13 | 1999 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 8 YD,HENKE REVERSIBLE,PLOW WING | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2783 | Wells
9 | 14 | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2785 | Winnemucca
9 | 14 | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2786 | Carson City
9 | 14 | 1998 | INTL | F9300 | TRACTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2787 | Reno
6 | 15 | 1999 | INTL | F5000 | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  |  | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 2788 | Las Vegas
6 | 15 | 1999 | INTL | F5000 | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  |  | ONE-WAY PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2789 | Reno
5 | 24 | 1997 | FORD | H8132 | SELF PROPELLED ROAD BROOM | OBDII |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 2795 | Reno
5 | 24 | 1998 | ATHEY | M-8A | SELF PROPELLED PICKUP BROOM | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 2799 | Carson City
5 | 24 | 1998 | MOBILE | M-8A | SP PICKUP BROOM HIGH DUMP | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 2801 | Las Vegas
6 | 28 | 1999 | INTL | SA25740 | DISTRIBUTOR TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2803 | Carson City
OFF ROAD / NA | 55B | 1981 | TUCKER | SNOWCAT | SNOW CAT | None- wired direct |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2810 | Tonopah
OFF ROAD / NA | 42 | 1998 | KODIAK | CR65 | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Full Project |  | 2826 | Reno
5 | 11A | 2019 | FREIGHTLNR | M2 | 2019 AERIAL LIFT TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2904 | Las Vegas
3 | 5 | 1999 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2906 | Reno
5 | 11A | 2018 | DODGE | 5500 | 2018 AERIAL LIFT TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2907 | Elko
6 | 15 | 2016 | PETERBILT | 367 | AWD TANDEM AXLE PLOW TRUCK | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 | SNOW PLOW | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2909 | Reno
6 | 15 | 2016 | PETERBILT | 367 | AWD TANDEM AXLE 6X6 PLOW TRUCK | J1939 | Roadwatch Sensor | EPOKE | Sirius SH4900 |  | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | #REF! | 6 | 0 | 4 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 2910 | Reno
5 | 11A | 2019 | FORD | F-550 | 2019 ARIEL LIFT TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2911 | Carson City
2 | 1 | 2000 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Pre-Pilot |  | 2912 | Las Vegas
3 | 5 | 2021 | FORD | F-150 | 2021 FORD F-150 1/2 TON PICKUP | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2913 | Las Vegas
2 | 01A | 2021 | FORD | EXPLORER | 2021 FORD EXPLORER 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2915 | Las Vegas
3 | 4 | 2021 | FORD | T-350 | 2021 FORD T-350 12 PASSENGER TRANSIT VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2916 | Las Vegas
3 | 3 | 2021 | FORD | F-250 | 2021 FORD F-250 SHORT BED PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2919 | Elko
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SNOW PLOW,2001 FLINK SANDER,2018 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 2920 | Las Vegas
3 | 3 | 2021 | FORD | F-250 | 2021 FORD F-250 SHORT BED PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2922 | Wells
3 | 3 | 2021 | FORD | F-250 | 2021 FORD F-250 SHORT BED PICKUP 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2923 | Elko
3 | 3 | 2022 | FORD | F-250 | 2022 FORD F250 EXTENDED CAB SHORT BED 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2925 | Las Vegas
3 | 3 | 2021 | FORD | F-250 | 2021 FORD F-250 LONG BED 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2926 | Carson City
2 | 01A | 2000 | GMC | JIMMY | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2927 | Las Vegas
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE SWAP LOADER | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | ONE WAY PLOW,SANDER,DUMP BODY | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2928 | Tonopah
3 | 3 | 2021 | FORD | F-250 | 2021 FORD F-250 EXTENDED CAB SHORT BED 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2930 | Winnemucca
3 | 3 | 2021 | FORD | F-250 | 2021 FORD F-250 CREW CAB SHORT BED 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 2931 | Elko
3 | 4 | 2000 | GMC | TG31405 | AWD CARGO VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2932 | Tonopah
3 | 5 | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2943 | Winnemucca
3 | 5 | 2022 | FORD | F-150 | 2022 FORD F-150 SHORT BED CREW CAB 4 X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 2945 | Carson City
3 | 5 | 2000 | GMC | SIERRA | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 2951 | Elko
3 | 5 | 2000 | GMC | SIERRA | 1/2 TON PICKUP AWD | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2975 | Reno
5 | 10 | 2000 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2984 | Las Vegas
5 | 10 | 2000 | FORD | F-350 | SURVEY UNIT | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2987 | Las Vegas
5 | 11H | 2001 | INTL | 4700 | FLAT RACK TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2989 | Reno
5 | 11F | 2001 | INTL | 4700 | FLAT RACK W/CRANE | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 2991 | Elko
6 | 11B | 2001 | INTL | F2574 | CRANE TRUCK W/FLATRACK | J1939 |  |  |  | ATTENUATOR TRUCK MOUNTED | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 2993 | Winnemucca
5 | 11E | 2000 | FORD | F-450 | DUMP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 2995 | Las Vegas
5 | 11S | 2000 | FORD | F-450 | REBUILD 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  | SWAPLOADER DUMP BODY | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 2996 | Las Vegas
8 | 13 | 2016 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SNOW PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 2998 | Wells
5 | 11 | 2000 | FORD | F-450 | REBUILD MISC TRUCK - BOX TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3001 | Reno
5 | 11E | 2005 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2019 SNOWDOG SNOW PLOW 9',2019 SALTDOG SAND SPREADER 2.0 CU YD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3192 | Reno | Existing Plows available but sensors not request by NDOT
5 | 11E | 2000 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | ARROW BOARD | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 3005 | Las Vegas
8 | 12 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | 5 YD FLINK,HENKE 4530 | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3015 | Tonopah
8 | 12 | 2001 | INTL | 2574 | SINGLE AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | SANDER,PLOW,8 YD SANDER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3017 | Ely
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | TENKO 1 WAY PLOW,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3018 | Ely
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE WING PLOW,VARITECH 1750 GAL BRINE TANK,PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3019 | Reno
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 8 CU YD FLINK LMC1H SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3020 | Carson City
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 2000 SANDER,SPRATRONICS DE ICER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 3021 | Reno
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | TENCO PLOW,FLINK SANDER 8 CU YRD | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3022 | Carson City
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3023 | Ely
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | FLINK 8 CU YD SANDER,11' TENCO PLOW,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3024 | Reno
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE TRK MTED WING PLOW,PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3025 | Winnemucca
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | REVERSIBLE,FLINK 8 CUBIC YARD SANDER,PLOW WING | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3026 | Wells
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | HENKE HEAVY DUTY PATROL,SANDER,WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3027 | Winnemucca
OFF ROAD / NA | 42 | 2020 | KODIAK | 1200 | ROTARY SNOW BLOWER | None- wired direct |  |  |  |  | Telematics Device | Snow Blower Activation | Yes |  | Yes | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.75 | #REF! | 3.75 | 1 | 2.75 | Tier 1 | Tier 3 | 440 | Pilot |  | 234 | Reno
8 | 13 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | ONE WAY HENKE,2000 SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3029 | Tonopah
8 | 13 | 2000 | INTL | F2574 | REBUILD TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | PLOW,SANDER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3030 | Winnemucca
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 1991 PLOW,2000 SANDER,HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3033 | Wells
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 8 CU YD FLINK LMC1H SANDER,REVERSIBLE PLOW, TENCO TC-132,DE-ICING SPRAYER | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3034 | Winnemucca
5 | 24 | 2008 | TYMCO | D3T6 | SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3035 | Las Vegas
8 | 13 | 2000 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | SANDER 8 CU YD HOPPER TYPE F,PLOW REVERSIBLE, TENCO TC-132 | Telematics device for Winter Operations | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3037 | Winnemucca
6 | 15 | 2001 | INTL | 5600I | AWD SANDER TRUCK | J1939 | Roadwatch Sensor |  |  | HENKE SNOW PLOW | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3038 | Carson City
5 | 24 | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3039 | Las Vegas
5 | 24 | 2001 | WITTKE | WIZARD FC-70 | STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3040 | Las Vegas
5 | 24 | 2000 | MOBILE | M-8A | STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3041 | Wells
3 | 5 | 2000 | GMC | TK15703 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3066 | Las Vegas
5 | 11H | 2000 | FORD | F-450 | 1 TON FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3068 | Las Vegas
6 | 11B | 2001 | FREIGHTLNR | FL70 | CRANE TRUCK | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3069 | Las Vegas
5 | 11J | 2008 | FORD | F-350 | UTILITY TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Full Project | Pre-Pilot | 3071 | Las Vegas
8 | 13 | 2001 | PETERBILT | 320 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3072 | Las Vegas
3 | 5 | 2000 | GMC | TC15903 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3089 | Reno
3 | 4 | 2000 | DODGE | GRAND CARAVA | 7 PASSENGER VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3093 | Carson City
2 | 1 | 2001 | TOYOTA | PRIUS | 4 DOOR SEDAN/HYBRID ELECTRIC | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Pilot | Pre-Pilot | 3096 | Las Vegas
5 | 11J | 2001 | GMC | SIERRA | UTILITY TRUCK 4X4 | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3112 | Reno
2 | 1 | 2002 | TOYOTA | PRIUS | HYBRID SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | Full Project | Pre-Pilot | 3114 | Las Vegas
3 | 3 | 2002 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 3119 | Las Vegas
5 | 6 | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 3121 | Las Vegas
5 | 11F | 2002 | FORD | F-550 | SHOP SERVICE TRUCK W/CRANE | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3122 | Las Vegas
5 | 11E | 2002 | FORD | F-450 | REBUILD DUMP TRUCK | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3124 | Las Vegas
8 | 13H | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3125 | Las Vegas
8 | 13 | 2002 | INTL | F2574 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | REVERSABLE PLOW,SANDER,WATERTANK | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 3126 | Las Vegas
8 | 13H | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3127 | Las Vegas
8 | 13H | 2002 | INTL | F2574 | TANDEM AXLE SIDE DUMP TRUCK | J1939 |  |  |  | 2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 5.5 | #REF! | 5.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 3128 | Las Vegas
8 | 13S | 2003 | INTL | F2574 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Plow Up Down Sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | #REF! | 5 | 1 | 2 | Tier 1 | Tier 2 | 260 | Full Project |  | 3129 | Las Vegas
5 | 24 | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3132 | Las Vegas
5 | 24 | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3133 | Las Vegas
5 | 24 | 2002 | TYMCO | 600 DST | DUSTLESS STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3134 | Las Vegas
5 | 24 | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3135 | Las Vegas
5 | 24 | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3136 | Las Vegas
5 | 24 | 2002 | CROSSWIND | SC8000 | REGENERATIVE STREET SWEEPER | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3137 | Las Vegas
5 | 11A | 2002 | FORD | F-550 | AERIAL TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 3138 | Elko
5 | 11 | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3149 | Las Vegas
5 | 11 | 2003 | INTL | 4200 | BUTTON TRUCK W/FLATRACK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3150 | Las Vegas
2 | 01A | 2002 | GMC | ENVOY | AWD SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 3151 | Las Vegas
5 | 6 | 2003 | FORD | F-350 | 1 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3158 | Reno
5 | 24 | 2003 | GMC | T7500 | GMC T7500 W/WAYNE SWEEPER | OBDII |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3169 | Carson City
5 | 24 | 2002 | GMC | T7500 | WAYNE WARRIOR SWEEPER | OBDII |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3172 | Carson City
3 | 3 | 2004 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Deleted | Deleted | 3180 | Las Vegas
5 | 11F | 2005 | FORD | F-450 | SERVICE TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3181 | Las Vegas
5 | 11F | 2005 | FORD | F-450 | SERVICE TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3182 | Las Vegas
5 | 11H | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2020 LITERREADER ARROW BOARD 1030F-4 | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3183 | Las Vegas
5 | 11E | 2005 | FORD | F-450 | DUMP TRUCK W/ARROWBOARD BIO-DSL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3184 | Las Vegas
5 | 11A | 2005 | FORD | F-550 | AERIAL TRUCK W/ARTICULATING DEVICE | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3185 | Las Vegas
5 | 11D | 2004 | FORD | F-450 | COMPACTOR TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3186 | Las Vegas
8 | 13 | 2007 | PETERBILT | 357 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  | PLOW ONE WAY,2012 HENKE WING PLOW | Telematics Device | Plow Up Down Sensor Wing Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 3187 | Tonopah
6 | 20 | 2004 | VECTOR | 58055VD | T/M CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2.75 | #REF! | 2.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3188 | Las Vegas
8 | 25 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3189 | Las Vegas
5 | 11E | 2006 | FORD | F-450 | DUMP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  | 2 YARD SANDER,SNOW PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3231 | Reno | Existing Plows available but sensors not request by NDOT
5 | 11H | 2005 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3193 | Reno
3 | 5 | 2004 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3194 | Carson City
5 | 11H | 2005 | FORD | F-450 | FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3196 | Reno
5 | 11H | 2005 | FORD | F-450 | 1 TON FLATRACK TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3197 | Carson City
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK | OBDII | Roadwatch Sensor |  |  | SPREADER BED MOUNT,SNOW V PLOW 4 WAY, | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3257 | Carson City | Existing Plows available but sensors not request by NDOT
8 | 13 | 2020 | WESTERN ST | 4900SF | 2020 WESTERN STAR 4900SF | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX | 2020 HENKE SINGEL AUGER CARTRIDGE SANDER,2020 HENKE REVERSIBLE PLOW,2020 HENKE WING PLOW | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Pilot |  | 526 | Reno
8 | 13S | 2020 | WESTERN ST | 4900 | TANDEM AXEL HOOKLIFT | J1939 | Roadwatch Sensor | FORCE AMERICA | SSC6100 | SANDER, REVERSIBLE PLOW, DUMP BODY | Telematics device for Winter Operations | Plow Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Pilot |  | 552 | Reno
9 | 14 | 2004 | PETERBILT | 378 | TRUCK TRACTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3201 | Fallon
6 | 20 | 2004 | INTL | 7600 6X4 | CULVERT CLEANER | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3202 | Carson City
8 | 25 | 2006 | INTL | 5900I | TRUCK W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3203 | Fallon
8 | 25 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3204 | Reno
8 | 25 | 2006 | INTL | 5900I | TRUCK , W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3205 | Carson City
8 | 25 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3206 | Fallon
5 | 11H | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3227 | Carson City
5 | 11H | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3228 | Fallon
5 | 11H | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3229 | Reno
5 | 11H | 2006 | FORD | F-650 | FLATRACK TRUCK | OBDII |  |  |  | MESSAGE SIGN TRUCK MOUNTED | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3230 | Fallon
5 | 11E | 2008 | FORD | F-450 | DUMP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  | 2012 HINKER C-PLOW | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 3314 | Las Vegas | Existing Plows available but sensors not request by NDOT
5 | 11E | 2006 | FORD | F-450 | DUMP TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3232 | Reno
5 | 11F | 2005 | FORD | F-450 | SERVICE TRUCK | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3233 | Carson City
8 | 25 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3234 | Carson City
8 | 25 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3235 | Fallon
8 | 25 | 2006 | INTL | 5900I | TRUCK, W/WATER TANK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device | Pump on/off sensor |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2.75 | #REF! | 4.75 | 1 | 1.75 | Tier 1 | Tier 2 | 260 | Full Project |  | 3236 | Reno
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3248 | Las Vegas
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3249 | Las Vegas
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3250 | Carson City
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 3252 | Las Vegas
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 3254 | Las Vegas
5 | 6 | 2006 | FORD | F-350 | 1 TON PICKUP TRUCK BIO-DIESEL | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 3256 | Las Vegas
8 | 13 | 2019 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1221 | Ely | Plow sensor requested but existing Plow hardware not available
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3259 | Las Vegas
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3260 | Reno
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3262 | Las Vegas
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3264 | Reno
5 | 11H | 2008 | FORD | F-450 | FLATRACK TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pre-Pilot |  | 3265 | Las Vegas
5 | 11 | 2007 | INTL | 7400 | WEED SPRAYER TRUCK | J1939 |  |  |  |  | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3266 | Las Vegas
8 | 13 | 2007 | WESTERN ST | 4900FA | DUMP TRUCK W/SIDE DUMP BODY | J1939 | Roadwatch Sensor | Parker Iqan | MD3 | 2020 REBUILD -ATTENUATOR VEH MNT,2020 SAFE-STOP ATTENUATOR | Telematics Device | Attenuator Up Down Sensor | Yes | Yes - Forward and Rearward | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 5.5 | #REF! | 7.5 | 1 | 4.5 | Tier 1 | Tier 4 | 660 | Full Project |  | 3269 | Las Vegas
5 | 11 | 2006 | INTL | 4200 | BUTTON TRUCK W/UTILITY BODY | J1939 |  |  |  | ARROW BOARD | Telematics Device | No |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3270 | Las Vegas
3 | 5 | 2006 | FORD | F-150 | 1/2 TON PICKUP TRUCK | OBDII |  |  |  |  | Telematics Device |  |  |  | Yes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1.25 | #REF! | 1.25 | 0 | 1.25 | 0 | Tier 2 | 260 | Pre-Pilot | Pre-Pilot | 3274 | Elko
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3275 | Carson City
5 | 24 | 2006 | FREIGHTLNR | SC-8000 | SELF PROPELLED P/U BROOM | J1939 |  |  |  |  | Telematics Device | Broom Up Down Sensor, Hopper full indication |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 3.5 | #REF! | 3.5 | 1 | 2.5 | Tier 1 | Tier 3 | 440 | Full Project |  | 3294 | Reno
3 | 3 | 2006 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3295 | Carson City
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3297 | Las Vegas
2 | 01A | 2007 | FORD | EXPLORER | SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 3298 | Las Vegas
2 | 01A | 2007 | FORD | EXPLORER | SUV | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Full Project | Pre-Pilot - Ownership transferred from USAFleet to GoFleet | 3299 | Reno
2 | 01A | 2007 | FORD | EXPLORER | SUV 4X4 | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 0 | 2.25 | 0 | Tier 3 | 440 | Pre-Pilot | Pre-Pilot | 3301 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3302 | Reno
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3303 | Reno
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3304 | Las Vegas
3 | 3 | 2007 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3305 | Las Vegas
2 | 1 | 2007 | CHEVROLET | MALIBU | 4 DOOR SEDAN | OBDII |  |  |  |  | Telematics Device |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #REF! | 1 | 1 | 0 | Tier 1 | 0 | 0 | Full Project |  | 3306 | Carson City
3 | 4 | 2008 | GMC | SAVANA | CARGO VAN | OBDII |  |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3308 | Carson City
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3310 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3311 | Reno
3 | 3 | 2008 | FORD | F-250 | 3/4 TON PICKUP TRUCK 4X4 | OBDII | Roadwatch Sensor |  |  |  | Telematics Device |  | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3312 | Reno
5 | 11J | 2008 | FORD | F-450 | UTILITY TRUCK 4X4 BIO-DIESEL | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3313 | Reno
8 | 13 | 2020 | WESTERN ST | 4900SF | 2019 TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor | CIRUS | SpreadSmart RX |  | Telematics device for Winter Operations | Plow Up Down Sensor Wing Up Down Sensor Barometric Pressure Sensor Humidity Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 5.75 | #REF! | 7.75 | 1 | 4.75 | Tier 1 | Tier 4 | 660 | Full Project |  | 1232 | Las Vegas | Plow sensor requested but existing Plow hardware not available
5 | 11S | 2008 | FORD | F-450 | 1 TON PICKUP TRUCK W/HOOK LIFT | OBDII | Roadwatch Sensor |  |  |  | Telematics Device | No | Yes |  | Yes | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3.25 | #REF! | 5.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Full Project |  | 3315 | Las Vegas
8 | 13 | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK | J1939 | Roadwatch Sensor |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2.25 | #REF! | 4.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Full Project |  | 3318 | Las Vegas
9 | 14 | 2020 | KENWORTH | W900L | 2020 KENWORTH W900L TRANSPORT TRACTOR | J1939 |  |  |  |  | Telematics Device |  |  |  | Yes | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2.25 | #REF! | 2.25 | 1 | 1.25 | Tier 1 | Tier 2 | 260 | Pilot |  | 1688 | Reno
7 | 83 | 2020 | WESTERN ST | 4900 | UNDERBRIDGE INSPECTION TRUCK | J1939 |  |  |  |  | Telematics Device |  | Yes |  | Yes | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3.25 | #REF! | 3.25 | 1 | 2.25 | Tier 1 | Tier 3 | 440 | Pilot |  | 2350 | Carson City
8 | 13S | 2009 | PETERBILT | 367 | TANDEM AXLE DUMP TRUCK W/HOOK LIFT | J1939 | Roadwatch Sensor |  |  | HENKE ONEWAY PLOW,SANDER SWAPLOADER,DUMP BODY SWAPLOADER,WATER TANK SWAPLOADER | Telematics Device | Plow Up Down Sensor | Yes | Yes - Forward Only | Yes | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | #REF! | 7 | 1 | 4 | Tier 1 | Tier 3 | 440 | Full Project |  | 3327 | Tonopah